## Safety
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION | [5 empty] | Document No.:
[8 empty] | Revision No.: |  | 0
Revision Date:
[9 empty] | DATE: | 2026-01-13
Safety and Personnel
Safety Topic: | Hot work permits,traffic and parking
Safety Statistics: |  | Direct | Indirect | Subcontractors |  |  |  | Total Direct | Total Indirect | TOTAL
(Cumm.) Work Hours |  | 25845 | 5378 | 1141 |  |  |  | 25845 | 6519 | 32364
(Period) Safe Work Hours |  | 1099 | 147 | 291 |  |  |  | 1099 | 438 | 1537
Total Safe Work Hours To-Date |  | 26944 | 5525 | 1432 | 0 | 0 | 0 | 26944 | 6957 | 33901
Incidents: |  | Period | To Date | Description
First Aids |  | 0 | 0
Incidents |  | 0 | 0 | 0
Recordable |  | 0 | 0
| Lost Time | 0 | 0
| Property Damage | 0 | 1
Near Misses |  | 0 | 0
Head Count: |  | Craft Type | Count | Subcontrator
Total |  | Indirects | 10 | 0
Total |  | Directs | 121 | 1
Request for additional manpower to be mobilized
List trade/name, work area
N/A
Weather Report: MUST INCLUDE ANY IMPACT TO SCHEDULE, STANDOWNS, ETC. |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Date |  | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18
Hi |  | 63 | 69
Low |  | 27 | 30
| Rain Inches | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weather: |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Date | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
| Hi | [5 empty] | NA | NA
| Lo | [5 empty] | NA | NA
| Rain | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
Formulas:
Indirect = [Direct]+1
Indirect = +[Direct]+1
Subcontractors = [Indirect]+1
Thursday = [Subcontractors]+1

## Field Report
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION |  |  |  |  | Document No.:
[7 empty] | Revision No.: |  | 0
Revision Date:
[8 empty] | DATE: | 2026-01-13
Schedule:
Project Completion:
|  | BASELINE SCHEDULE | CURRENT SCHEDULE | VAR FROM SCHD (DAYS +/-) | Status
| Award Contract | 2025-07-16 | 2025-07-21 | -5
| Mobilization | 2025-10-01 | 2025-10-01 | 0
| Site Work Fill and Compact Start | 2025-11-21 | 2025-11-12 | 9
| Site Work Fill and Compact Finish | 2025-12-12 | 2025-12-06 | 2
| Laydown Yard Start | 2025-10-06 | 2025-10-03 | 3
| Laydown Yard Finish | 2025-11-29 | 2025-11-18 | 11
| Drill Piers Start | 2025-11-07 | 2025-11-07 | 0
| Drill Pier Finish | 2025-11-26 | 2025-11-21 | 5
| Sill Slab Start | 2025-11-14 | 2025-11-10 | 4
| Sill Slab Finish | 2025-12-02 | 2025-11-22 | 10
| GT/SCR Foundations Start | 2025-12-05 | 2025-11-26 | 9
| GT/SCR Foundations Complete | 2026-01-07 | 2025-12-31 | 7
| Helical Piles Start | 2025-11-10 | 2025-11-11 | -1
| Helical Piles Finish | 2025-12-03 | 2025-12-05 | -2
0
|  | TO DATE SCHEDULED | TO DATE ACTUAL | VAR FROM TO DATE SCHD PCT | PERCENT GAIN FOR WEEK SCHD | PERCENT GAIN FOR WEEK ACTUAL
| UG Piping |  |  | 0% | 0% | 0%
Duct Banks |  |  |  | 0% | 0% | 0%
| Civil |  |  | 0% | 0% | 0%
| Piping / Equipment |  |  | 0% | 0% | 0%
| E&I |  |  | 0% | 0% | 0%
| Percent Complete Overall |  |  | 0% | 0% | 0%
|  | #REF! | #REF! | #REF! | #REF! | #REF!
| Performance (PF = E / A ) | #REF! | #REF! | #REF! | #REF! | #REF!
Work Schedule: |  | SCHEDULED DAYS LAST WEEK | ACTUAL LAST WEEK | VAR FROM SCHD (LAST WEEK) | VAR FROM SCHD (TO DATE)
| Number of Work Days | 7 | 7 | 0 | 0
| Total Work Hours | 68 | 68 | 0 | 0
Impacts to Schedule:
No. HOURS AFFECTED
|  | TODAY | TO DATE
| Construction | 0 | 0
| Evacuations/Exclusions | 0 | 0
| Permits | 0 | 0
| Equip/Material | 0 | 0
| Site Conditions/Obstruction | 0 | 0
| Safety Stoppage | 0 | 0
| Weather/Wind Delay | 2.5 | 5
Completed and Planned Actvities
Completed Today:
•Spread fill on pad site North of Piperack 100, setting embeds GT 1 and compaction test on pad sites. Fitting and welding CS UG pipe, building signs for laydown yard. Laying out TM 2500s
Planned Tomorrow:
•Backfilling North of piperack, compaction tests for areas north of pipe rack, receive trucks from NJ and materials for new construction.
Issues/Areas of Concerns
LIST ANY POTENTIAL IMPACT TO SCHEDULE:
•See impact tickets tab
Materials Required:
•See QTAB for quantities remaining.
Current Procurement and Receiving:
Deliveries:
Next Day Procurement and Receiving:
Deliveries:
Photos
Attach pictures to the report

## FCO.RFI
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION | [5 empty] | Document No.:
[8 empty] | Revision No.: |  | 0
Revision Date:
[9 empty] | DATE: | 2026-01-13
Engineering:
Engineering Issues/RFI's/NCR's
Due to the nature of the Piperack moving, the Engineers added two piles on the west end to tie the project together. This change order includes all of the labor, material, and time to complete the additional (2).
Field Change Orders (FCO): |  | Period | To Date
| Transmitted | 1 | 1
| Approved | 0 | 2
| Rejected | 0 | 0
| Outstanding | 0 | 0
Contractor | Change Order Number | Description | Status | Date to Client | Hours | Labor $ | Material $ | Subcontract $ | Per Diem | Approved Totals
Audubon | 1 | Added 19 Piles | Approved | 2025-10-30 |  |  | 61742 |  |  | 543042
Audubon | 2 | Added 8 Piles | TBD | TBD |  |  | 42752 |  |  | 585794
E&H | 3 | Seal Slabs | Approved | 2025-11-08
Audubon | 4 | Added 2 Piles | TBD | TBD | TBD | TBD | 11219 | TBD | TBD | 554261
Total | Total |  |  |  | 0 | 0 | 115713 | 0 | 0 | 1683097

## Cnst Equip
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION |  |  |  |  | Document No.:
[7 empty] | Revision No.: |  | 0
Revision Date:
[8 empty] | DATE: | 2026-01-13
Construction Equipment
| Rental Equipment |  | RPS / Contractor | Qty | On Rent Date | On Rent Finish
| Forklift |  | 84
| 12k (55'r each) - laydown |  | Momentum
12k (55'r each) - field grub
185CFM Air Compressor
| 2000 Gallon Water Truck |  | Momentum
Concrete Mixer
Gas Rammer
Plate Comp
Light Plants
Pallet Jack
Manlift
45' Articulating Boom
60' Articulating Boom
85' Articulating Boom
80' Straight Boom
| 85' Articulating Boom |  | RPS / Contractor | Qty | On Rent Date | On Rent Finish
| SKID STEER |  | Momentum
| Skid Steer Pallet Forks |  |  | 1 | 2025-10-20
Mini Ex (10-11k)
10k Track Excavator
| 20k Track Excavator (Cab & Air) |  |  | 1 | 2025-10-20
3 yard loader
| 84" roller |  | Momentum
3K W/B Padfoot Roller
2500lb Track Loader
1900lb Track Loader
| 850P Dozer |  | Momentum
| 750L Dozer |  | Momentum
| 260E ADT |  | Momentum
| 824L Wheel Loader |  | Momentum
| 135P Excavator |  | Momentum
| Bomag BW211 Pad Compactor |  | Momentum
| Bomag BW211 Smooth Compactor |  | Momentum | 1 | 2025-10-21
| 850P Dozer |  | Momentum
| 850P Dozer |  | Momentum
| 310E ADT |  | Momentum

## QAQC
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION |  |  |  | Document No.:
[6 empty] | Revision No.: |  | 0
Revision Date:
[7 empty] | DATE: | 2026-01-13
QA/QC:
Highlights and Activities:
Civil
This should list QC activities/inspections. This content should be on "Completed Activities" | update MTR's documents.
update logs for concrete and density.
inspection on GTG's for point & patch work is complete.
Welding:
| Total Field Welds |  | Welds Progressed to Date | Welds Remaining | % Complete
Field Weld Count |  |  |  | 0 | 0%
| Field Weld VT Count | Field Weld RT Count | Total Rejected / Repairs | Reject Rate (Last Week) | Reject Rate (Current)
N.D.E. |  |  | 0 | 0% | 0%
Non-Conformance Report Status:
| NCR's to Date | NCR's Open | NCR's Pending | NCR's Closed
| 2025-12-20 |  |  | 1

## QTY Progress
INSTALLED QUANTITIES REPORT | [6 empty] | Period | 2026-01-13
E&H EXCAVATIONS |  |  | Period |  |  | JTD
Progress Item | UOM | Current Budg | Plan | Actual | % Earned | Plan | Actual | % Earned
Temp Facilities Area | CY | 45714 | 0 | 0 | 0% | 26428 | 29823 | 65.24%
Pad Site | CY | 47483 | 0 | 0 | 0% | 44000 | 47483 | 100%
Drill Piers GT | CY | 203 | 0 | 0 | 0% | 392 | 203 | 100%
Drill Piers SCR | CY | 97 | 0 | 0 | 0% | 96.6 | 96 | 98.97%
GT Seal Slab | CY | 90 | 0 | 0 | 0% | 90 | 90 | 100%
SCR Seal Slab | CY | 140 | 0 | 0 | 0% | 105 | 140 | 100%
AUDUBON |  |  | Period |  |  | JTD
Progress Item | UOM | Current Budg | Plan | Actual | % Earned | Plan | Actual | % Earned
Helical Piers | EA | 171 | 0 | 0 | 0% | 128 | 171 | 100%
Concrete Pedestals | EA | 171 | 0 | 0 | 0% | 120 | 153 | 89.47%

## E&H - QTY Plan
Y4
[5 empty] | Thru | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday |  | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| Discipline | AREA | UOM |  | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | Total
6800 | Sitework | Temp Facilities Area | CY | Plan | 7598 | 1536 | 1628 | 1886 | 1572 | 1572 | 1572 | 0 | 1572 | 1572 | 1572 | 1572 | 1572 | 1204 | [78 empty] | 26428 | Budgeted
HR |  |  |  | Earned | 7598 | 1536 | 1628 | 2028 | 1965 | 2739 | 1513 | 0 | 1412 | 1959 | 1572 | 2396 | 2350 | 670 |  | 281 | 176 | [75 empty] | 29823 | Installed
HR |  |  |  | Forecast | [10 empty] | 1075.4392 | 1075.4392 | 1075.4392 | 823.6824 |  | 300 | 300 | [75 empty] | 4650 | Forecast
| Sitework | Temp Facilities Area | % Complete | Plan | 28.75% | 5.812% | 6.16% | 7.136% | 5.948% | 5.948% | 5.948% | 0% | 5.948% | 5.948% | 5.948% | 5.948% | 5.948% | 4.556% | 0% | 0% | 0% | 0% | [74 empty] | 100% | Budgeted
|  |  |  | Earned | 28.75% | 5.812% | 6.16% | 7.674% | 7.435% | 10.36% | 5.725% | 0% | 5.343% | 7.413% | [82 empty] | 84.68% | Installed
|  |  |  | Forecast | [10 empty] | 4.069% | 4.069% | 4.069% | 3.117% | 0% | 1.135% | 0.011352 | 0 | [74 empty] | 17.59% | Forecast
HR | Sitework | Pad Site | CY | Plan | [5 empty] | 5000 | 5000 | 10000 | 5000 | 5000 | 5000 | [81 empty] | 35000 | Budgeted
HR |  |  |  | Earned | [10 empty] | 300 | 300 | 300 | 300 |  | 1151 | 1915 | 2238 | 1005 | 1998 | 404 | 0 | 525 | 2256 | 3470 |  |  | 1440 | 650 | 1754 | 2490 | 2440 | 2296 | 2930 | 0 | 0 | 3624 | 3872 | 0 |  |  |  | 550 | 550 | 550 | 550 | [18 empty] | 1120 | 1140 | 2100 | 2100 | 1165 | [23 empty] | 47483 | Installed
HR |  |  |  | Forecast | [15 empty] | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1250 | 2500 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 2500 | 2500 | 1500 | 1500 | 1250 | 1250 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | [23 empty] | 500 | 500 | 500 | [25 empty] | 44000 | Forecast
| Sitework | Pad Site | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 14.29% | 14.29% | 28.57% | 14.29% | 14.29% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [73 empty] | 100% | Budgeted
|  |  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8571% | 0.8571% | 0.8571% | 0.8571% | 0% | 3.289% | 5.471% | 6.394% | 2.871% | [73 empty] | 21.45% | Installed
|  |  |  | Forecast | [15 empty] | 4.706% | 4.706% | 4.706% | 4.706% | 4.706% | 4.706% | 2.941% | 5.882% | 5.882% | 2.941% | 2.941% | 2.941% | 2.941% | 2.941% | 5.882% | 5.882% | 3.529% | 3.529% | 2.941% | 2.941% | [57 empty] | 82.35% | Forecast
1069 | Civil | Drill Piers GT | CY | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 46 | 0 | 46 | 0 | 51 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [69 empty] | 392 | Budgeted
HR |  |  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 |  | 60 | 0 | 46 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [69 empty] | 203 | Installed
HR |  |  |  | Forecast | [13 empty] | 37 | [78 empty] | 37 | Forecast
| Civil | Drill Piers GT | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 11.73% | 0% | 0% | 11.73% | 0% | 11.73% | 0% | 13.01% | 51.79% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [69 empty] | 0% | Budgeted
|  |  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 11.73% | 0% | 0% | 15.31% | 0% | 11.73% | 0% | 13.01% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [69 empty] | 51.79% | Installed
|  |  |  | Forecast | [11 empty] | 0% | 0% | 9.439% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [69 empty] | 9.439% | Forecast
758 | Civil | Drill Piers SCR | CY | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.2 |  | 32.2 |  | 32.2 | [72 empty] | 96.6 | Budgeted
HR |  |  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 32 | 0 | 0 | 28 | 0 | 0 | [8 empty] | 4 | [60 empty] | 96 | Installed
HR |  |  |  | Forecast | [15 empty] | 32.2 |  | 32.2 |  | 32.2 | [11 empty] | 4 | [60 empty] | 100.6 | Forecast
| Civil | Drill Piers SCR | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 33.33% | 0% | 33.33% | 0% | 0% | 0% | [69 empty] | 100% | Budgeted
|  |  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.163% | 0% | 8.163% | 0% | 0% | 7.143% | 0% | 0% | [69 empty] | 23.47% | Installed
|  |  |  | Forecast | [15 empty] | 32.01% | 0% | 32.01% | 0% | 32.01% | 0% | 0% | 0% | [69 empty] | 96.02% | Forecast
HR | Civil | GT Seal Slab | CY | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |  | 30 |  | 30 | [74 empty] | 90 | Budgeted
HR |  |  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | [69 empty] | 90 | Installed
HR |  |  |  | Forecast | [13 empty] | 30 |  | 30 |  | 30 | [74 empty] | 90 | Forecast
| Civil | GT Seal Slab | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 33.33% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | [69 empty] | 100% | Budgeted
|  |  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.653% | 0% | 7.653% | 0% | 7.653% | 0% | 0% | 0% | 0% | 0% | [69 empty] | 22.96% | Installed
|  |  |  | Forecast | [92 empty] | 0% | Forecast
HR | Civil | SCR Seal Slab | CY | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 70 |  | 35 | [71 empty] | 105 | Budgeted
HR |  |  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 35 |  |  | 35 | [7 empty] | 35 | [60 empty] | 105 | Installed
HR |  |  |  | Forecast | [20 empty] | 35 |  | 70 | [8 empty] | 35 | [60 empty] | 140 | Forecast
| Civil | SCR Seal Slab | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 0% | 33.33% | 0% | 0% | [69 empty] | 100% | Budgeted
|  |  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.929% | 0% | 0% | [69 empty] | 8.929% | Installed
|  |  |  | Forecast | [92 empty] | 0 | Forecast
MH | OVERALL | OVERALL | OVERALL | Plan | 7598 | 1536 | 1628 | 1886 | 1572 | 6572 | 6618 | 10000 | 6572 | 6618 | 6572 | 1618 | 1572 | 1285 | 203 | 62.2 | 0 | 62.2 | 70 | 32.2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [56 empty] | 62111.6 | Budgeted
MH |  |  |  | Earned | 7598 | 1536 | 1628 | 2028 | 1965 | 2739 | 1559 | 0 | 1412 | 2019 | 1872 | 2742 | 2650 | 1051 | 0 | 1494 | 2091 | 2300 | 1005 | 1998 | 467 | 0 | 525 | 2291 | 3470 | 0 | 0 | 1440 | 650 | 1754 | 2490 | 2479 | 2296 | 2930 | 0 | 0 | [56 empty] | 60479 | Installed
MH |  |  |  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.4392 | 1075.4392 | 1075.4392 | 890.6824 | 0 | 2362.2 | 2300 | 2062.2 | 2000 | 2032.2 | 2035 | 1250 | 2570 | 2500 | 1250 | 1250 | 1250 | 1250 | 1250 | 2500 | 2500 | 1539 | 1500 | 1250 | 1250 | 0 | [56 empty] | 40017.6 | Forecast
MH | OVERALL | OVERALL | OVERALL | Plan | 12.23% | 2.473% | 2.621% | 3.036% | 2.531% | 10.58% | 10.66% | 16.1% | 10.58% | 10.66% | 10.58% | 2.605% | 2.531% | 2.069% | 0.3268% | 0.1001% | 0% | 0.1001% | 0.1127% | 0.05184% | 0.05635% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [56 empty] | 100% | Budgeted
MH |  |  |  | Earned | 12.23% | 2.473% | 2.621% | 3.265% | 3.164% | 4.41% | 2.51% | 0% | 2.273% | 3.251% | 3.014% | 4.415% | 4.267% | 1.692% | 0% | 2.405% | 3.367% | 3.703% | 1.618% | 3.217% | 0.7519% | 0% | 0.8453% | 3.689% | 5.587% | 0% | 0% | 2.318% | 1.047% | 2.824% | 4.009% | 3.991% | 3.697% | 4.717% | 0% | 0% | [56 empty] | 97.37% | Installed
MH |  |  |  | Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.731% | 1.434% | 0% | 3.803% | 3.703% | 3.32% | 3.22% | 3.272% | 3.276% | 2.013% | 4.138% | 4.025% | 2.013% | 2.013% | 2.013% | 2.013% | 2.013% | 4.025% | 4.025% | 2.478% | 2.415% | 2.013% | 2.013% | 0% | [56 empty] | 0.60966 | Forecast
Formulas:
Tuesday = [Monday]+1
Monday = [Sunday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
Sunday = [Saturday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1

## Audubon - QTY Plan
|  |  |  | Saturday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Discipline | AREA | UOM |  | 2025-11-01 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | Total
Civil | Helical Piers | EA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 10 | 10 | 10 |  |  |  | 10 | 10 | 8 | 0 |  | 5 | 5 | [5 empty] | 11 | 16 | 7 | 9 | [9 empty] | 171 | Budgeted
|  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 34 | 21 | 11 | 18 | 0 | 7 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11 | 16 | 7 | 9 | [9 empty] | 171 | Earned
|  |  | Forecast | [9 empty] | 9 |  | 8.9474 | 8.9474 | 8.9474 | 0 | 8.9474 | 8.9474 | 8.9474 | 8.9474 | 8.9474 | 8.9474 | 8.9474 | 8.9474 | 7.1579 | 0 | 4.4737 | 4.4737 | 4.4737 | [5 empty] | 11 | 16 | 7 | 9 | [9 empty] | 171 | Forecast
Civil | Helical Piers | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.848% | 5.848% | 5.848% | 5.848% | 5.848% | 5.848% | 0% | 5.848% | 5.848% | 5.848% | 0% | 0% | 0% | 5.848% | 5.848% | 4.678% | 0% | 0% | 2.924% | 2.924% | 0% | 0% | 0% | 0% | 0% | 6.433% | 9.357% | 4.094% | 5.263% | 0% | 0% | 0% | 0% | [5 empty] | 100% | Budgeted
|  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.848% | 19.88% | 12.28% | 6.433% | 10.53% | 0% | 4.094% | 8.772% | 7.018% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.433% | 9.357% | 4.094% | 5.263% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 100% | Earned
|  |  | Forecast | [8 empty] | 0% | 5.263% | 0% | 5.232% | 5.232% | 5.232% | 0% | 5.232% | 5.232% | 5.232% | 5.232% | 5.232% | 5.232% | 5.232% | 5.232% | 4.186% | 0% | 2.616% | 2.616% | 2.616% | 0% | 0% | 0% | 0% | 0% | 6.433% | 9.357% | 4.094% | 5.263% | 0% | 0% | 0% | 0% | 0% |  |  |  |  | 100% | Forecast
Civil | Concrete Pedestals | EA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 |  | 0 |  |  | 9 |  |  |  | 22 | 20 |  |  |  |  | 171 | Budgeted
|  |  | Earned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 16 | 0 | 0 | 28 | 0 | 0 | 20 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 |  | 9 |  |  |  | 16 | [5 empty] | 153 | Earned
|  |  | Forecast | [12 empty] | 20 |  |  |  | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 |  |  |  |  | 9 |  |  |  | 22 | 20 |  |  |  |  | 171 | Forecast
Civil | Concrete Pedestals | % Complete | Plan | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.7% | 0% | 0% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 0% | 0% | 0% | 0% | 5.263% | 0% | 0% | 0% | 12.87% | 11.7% |  |  |  |  | 100% | Budgeted
|  |  | Earned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.7% | 0% | 0% | 0% | 0% | 11.7% | 0% | 0% | 9.357% | 0% | 0% | 16.37% | 0% | 0% | 11.7% | 0% | 0% | 14.04% | 0% | 0% | 0% | 0% | 0% | 0% | 5.263% | 0% | 0% | 0% | 9.357% | 0% |  |  |  |  | 89.47% | Earned
|  |  | Forecast | [12 empty] | 11.7% | 0% | 0% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 11.7% | 0% | 0% | 0% | 0% | 0% | 0% | 5.263% | 0% | 0% | 0% | 12.87% | 11.7% |  |  |  |  | 100% | Forecast
Formulas:
Tuesday = [Monday]+1
Monday = [Wednesday]+5
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1

## E&H - Daily Report
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION | [5 empty] | Document No.:
[8 empty] | Revision No.: |  | 0
Revision Date:
[6 empty] | PO# | 15209 |  | DATE: | 2026-11-13
Safety and Personnel
Safety Topic: | Cold weather work
Safety Statistics: |  | Direct | Indirect | Subcontractors |  |  |  | Total Direct | Total Indirect | TOTAL
Previous Safe (Cumm.) Work Hours |  | 19744 | 2009 |  |  |  |  | 19744 | 2009 | 21753
This Week (Period) Safe Work Hours |  | 854 | 96 |  |  |  |  | 854 | 96 | 950
Total Safe Work Hours To-Date |  | 20598 | 2105 | 0 | 0 | 0 | 0 | 20598 | 2105 | 22703
Incidents: |  | Period | To Date | Description
First Aids |  | 0 | 0
Incidents |  | 0 | 0
Recordable |  | 0 | 0
| Lost Time | 0 | 0
| Property Damage | 0 | 1
Near Misses |  | 0 | 0
Head Count: |  | Craft Type | Count | Subcontrator | Hrs |  | Per Diem (Y/N)
|  | Sr. Project Management | 1 |  | 0 |  | Y
|  | Superintendent - Civil | 1 |  | 12 |  | Y
|  | Site Manager | 1 |  | 12 |  | Y
|  | Superintendent - Piping | 1 |  |  |  | Y
|  | Superintendent - Mech | 1 |  | 12 |  | Y
Superintendent - E&I
Planner
Project Scheduler
|  | Quality Manager | 1 |  | 12 |  | Y
|  | HSE Supervisor | 2 |  | 12 |  | Y
Office Manager
Timekeeper
|  | Warehouse GF | 1 |  | 12 |  | Y
|  | Warehouseman | 1 |  | 12 |  | Y
|  | Warehouse Crew | 3 |  | 36 |  | Y
|  | Operators J1 | 2 |  | 24 |  | Y
Operators J2
|  | Tool Room Attendant | 1 |  | 12 |  | Y
|  | Civil GF | 1 |  | 12 |  | Y
|  | Civil J1 | 24 |  | 276 |  | Y
|  | Civil J2 | 14 |  | 132 |  | Y
|  | Pipe GF | 1 |  | 12 |  | Y
|  | Pipe Foreman | 1 |  | 12 |  | Y
|  | Pipe J1 | 7 |  | 84 |  | Y
|  | Pipe J2 | 5 |  | 60 |  | Y
|  | Combo Welder | 5 |  | 48 |  | Y
|  | Iron J1 | 10 |  | 120 |  | Y
|  | Iron J2 | 2 |  | 24 |  | Y
|  | Millwright J1 | 1 |  | 12 |  | Y
Helper
|  | 17.08 | 1.92
Request for additional manpower to be mobilized
List trade/name, work area
See Man Power Req tab
Weather Report: MUST INCLUDE ANY IMPACT TO SCHEDULE, STANDOWNS, ETC. |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Date |  | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18
Hi |  | 63 | 68
Low |  | 37 | 45
Rain Inches
Weather: |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Date | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
| Hi | [5 empty] | NA | NA
| Lo | [5 empty] | NA | NA
| Rain | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
Engineering:
Engineering Issues/RFI's/NCR's
Field Change Orders (FCO): |  | Period | To Date
| Transmitted | 0 | 0
| Approved | 0 | 0
| Rejected | #REF! | 0
| Outstanding | 0 | 0
| Change Order Number | Description | Status | Date to Client | Hours | Labor $ | Material $ | Subcontract $ | Per Diem | Approved Totals
| Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Procurement and Receiving:
Deliveries:
PO Status and Subcontracts:
Schedule:
|  | BASELINE SCHEDULE 10-1-2025 | CURRENT SCHEDULE 11-14-2025 | VAR FROM SCHD (DAYS +/-) | Status
| Award Contract | 2025-07-16 | 2025-07-21 | -5
| Mobilization | 2025-10-01 | 2025-10-01 | 0
| Site Work Fill and Compact Start | 2025-11-21 | 2025-11-12 | 9
| Site Work Fill and Compact Finish | 2025-12-12 | 2025-12-06 | 2
| Laydown Yard Start | 2025-10-06 | 2025-10-03 | 3
| Laydown Yard Finish | 2025-11-29 | 2025-11-18 | 11
| Drill Piers Start | 2025-11-07 | 2025-11-07 | 0
| Drill Pier Finish | 2025-11-26 | 2025-11-21 | 5
| Sill Slab Start | 2025-11-14 | 2025-11-10 | 4
| Sill Slab Finish | 2025-12-02 | 2025-11-22 | 10
| GT/SCR Foundations Start | 2025-12-05 | 2025-11-26 | 9
| GT/SCR Foundations Complete | 2026-01-07 | 2025-12-31 | 7
| Electrical Duct Bank Installation |  |  | 0
| Electrical Duct Bank Complete |  |  | 0
0
|  | TO DATE SCHEDULED | TO DATE ACTUAL | VAR FROM TO DATE SCHD PCT | PERCENT GAIN FOR WEEK SCHD | PERCENT GAIN FOR WEEK ACTUAL
| UG Piping |  |  | 0% | 0% | 0%
Duct Banks |  |  |  | 0% | 0% | 0%
| Civil |  |  | 0% | 0% | 0%
| Piping / Equipment |  |  | 0% | 0% | 0%
| E&I |  |  | 0% | 0% | 0%
| Percent Complete Overall |  |  | 0% | 0% | 0%
|  | #REF! | #REF! | #REF! | #REF! | #REF!
| Performance (PF = E / A ) | #REF! | #REF! | #REF! | #REF! | #REF!
Work Schedule: |  | SCHEDULED DAYS LAST WEEK | ACTUAL LAST WEEK | VAR FROM SCHD (LAST WEEK) | VAR FROM SCHD (TO DATE)
| Number of Work Days | 7 | 7 | 0 | 0
| Total Work Hours | 84 | 84 | 0 | 0
Impacts to Schedule:
No. HOURS AFFECTED
|  | TODAY | TO DATE
| Construction | 0 | 0
| Evacuations/Exclusions | 0 | 0
| Permits | 0 | 0
| Equip/Material | 0 | 0
| Site Conditions/Obstruction | 0 | 0
| Safety Stoppage | 0 | 0
| Weather/Wind Delay | 0 | 0
Construction Equipment
| Rental Equipment |  | RPS / Contractor | Qty | On Rent Date | On Rent Finish
Forklift
| 12k (55'r each) - laydown |  |  | 1 | 2025-10-20
12k (55'r each) - field grub
185CFM Air Compressor
| 2000 Gallon Water Truck |  |  | 1 | 2025-10-20
Concrete Mixer
Gas Rammer
Plate Comp
Light Plants
Pallet Jack
Manlift
45' Articulating Boom
60' Articulating Boom
85' Articulating Boom
80' Straight Boom
85' Articulating Boom
| SKID STEER |  |  | 1 | 2025-10-21
Skid Steer Pallet Forks
Mini Ex (10-11k)
10k Track Excavator
20k Track Excavator (Cab & Air)
3 yard loader
| 84" roller |  |  | 1 | 2025-10-20
3K W/B Padfoot Roller
2500lb Track Loader
1900lb Track Loader
| 850P Dozer |  |  | 1 | 2025-10-01
| 750L Dozer |  |  | 1 | 2025-10-01
| 260E ADT |  |  | 1 | 2025-10-02 | 2026-01-05
| 824L Wheel Loader |  |  | 1 | 2025-10-03 | 2026-01-05
| 135P Excavator |  |  | 1 | 2025-10-13
| Bomag BW211 Pad Compactor |  |  | 1 | 2025-10-13 | 2025-11-03
| Bomag BW211 Smooth Compactor |  |  | 1 | 2025-10-13 | 2026-01-05
| 850P Dozer |  |  | 1 | 2025-10-27
| 850P Dozer |  |  | 1 | 2025-10-27 | 2026-01-05
| Kubota M5 and Disc |  |  | 1 | 2025-12-17
| 310E ADT |  |  | 1 | 2025-10-13 | 2026-01-05
| 250P Excavator |  |  | 1 | 2025-11-20
QA/QC:
Highlights and Activities:
Civil
This should list QC activities/inspections. This content should be on "Completed Activities"
Welding:
| Total Field Welds |  | Welds Progressed to Date | Welds Remaining | % Complete
Field Weld Count |  |  |  | 0 | 0%
| Field Weld VT Count | Field Weld RT Count | Total Rejected / Repairs | Reject Rate (Last Week) | Reject Rate (Current)
N.D.E. |  |  | 0 | 0% | 0%
Non-Conformance Report Status:
| NCR's to Date | NCR's Open | NCR's Pending | NCR's Closed
| 0 | 0 | 0 | 0
Completed and Planned Actvities
Completed Today:
Spread fill on pad site North of Piperack 100, setting embeds GT 1 and compaction test on pad sites. Fitting and welding CS UG pipe, building signs for laydown yard. Laying out TM 2500s
.
Planned Tomorrow:
Backfilling North of piperack, compaction tests for areas north of pipe rack, receive trucks from NJ and materials for new construction.
Materials Requiered:
See QTAB for quantities remaining.
Issues/Areas of Concerns
LIST ANY POTENTIAL IMPACT TO SCHEDULE:
See impact tickets tab
Photos
Attach pictures to the report
Formulas:
Indirect = [Direct]+1
Indirect = +[Direct]+1

## Audubon - Daily Report
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION | [5 empty] | Document No.:
[8 empty] | Revision No.: |  | 0
Revision Date:
[9 empty] | DATE: | 2025-12-17
Safety and Personnel
Safety Topic: | Materials handling
Safety Statistics: |  | Direct | Indirect | Subcontractors |  |  |  | Total Direct | Total Indirect | TOTAL
(Cumm.) Work Hours |  | 2059 | 775 | 253 |  |  |  | 2059 | 1028 | 3087
(Period) Safe Work Hours |  | 55 | 11 | 11 |  |  |  | 55 | 22 | 77
Total Safe Work Hours To-Date |  | 2114 | 786 | 264 | 0 | 0 | 0 | 2114 | 1050 | 3164
Incidents: |  | Period | To Date | Description
First Aids |  | 0 | 0
Incidents |  | 0 | 0
Recordable |  | 0 | 0
| Lost Time | 0 | 0
| Property Damage | 0 | 0
Near Misses |  | 0 | 0
Head Count: |  | Craft Type | Count | Subcontrator | Hrs |  | Per Diem (Y/N)
Total |  | Indirects | 2 |  | 11
Total |  | Directs | 5 | 1 | 11
Request for additional manpower to be mobilized
List trade/name, work area
N/A
Weather Report: MUST INCLUDE ANY IMPACT TO SCHEDULE, STANDOWNS, ETC. |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Date |  | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16
Hi |  | 65 | 72
Low |  | 45 | 46
Rain Inches
Weather: |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Date | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
| Hi | [5 empty] | NA | NA
| Lo | [5 empty] | NA | NA
| Rain | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
Engineering:
Engineering Issues/RFI's/NCR's
Piperack Pile Locations
Field Change Orders (FCO): |  | Period | To Date
| Transmitted | 0 | 0
| Approved | 0 | 0
| Rejected | 0 | 0
| Outstanding | 0 | 0
| Change Order Number | Description | Status | Date to Client | Hours | Labor $ | Material $ | Subcontract $ | Per Diem | Approved Totals
| 1 | added 19 piles | Approved | 2025-10-30 |  |  | 61742 |  |  | 61742
| 2 | added 8 piles | Approved | 2025-11-18 | - | - | 42752 | - | - | 42752
| 3 | changing rebar size in Turbine area | Approved | 2025-12-09 |  |  | 2849
| 4 | Adding 2 piles in the Bent | Approved | 2025-12-09 |  |  | 11219
| 5 | Procedure Change to Turbine Piles | Approved | 2025-12-10 |  |  | 19683
| Total |  |  |  | 0 | 0 | 118562 | 0 | 0 | 104494
Current Procurement and Receiving:
Deliveries:
Next Day Procurement and Receiving:
Deliveries:
Schedule:
Project Completion:
|  | BASELINE SCHEDULE | CURRENT SCHEDULE | VAR FROM SCHD (DAYS +/-) | Status
| Award Contract | 2025-10-25 | 2025-10-25 | 0
| Mobilization | 2025-11-06 | 2025-10-01 | 36
| Site Work | 2025-11-07 | 2025-11-11 | -4
| Laydown Yard Prep | 2025-11-07 | 2025-11-07 | 0
| Piles Start | 2025-11-10 | 2025-11-11 | -1
| Piles Finish | 2025-12-03 | 2025-12-11 | -8
|  | TO DATE SCHEDULED | TO DATE ACTUAL | VAR FROM TO DATE SCHD PCT | PERCENT GAIN FOR WEEK SCHD | PERCENT GAIN FOR WEEK ACTUAL
| UG Piping |  |  | 0% | 0% | 0%
Duct Banks |  |  |  | 0% | 0% | 0%
| Civil |  |  | 0% | 0% | 0%
| Piping / Equipment |  |  | 0% | 0% | 0%
| E&I |  |  | 0% | 0% | 0%
| Percent Complete Overall |  |  | 0% | 0% | 0%
|  | #REF! | #REF! | #REF! | #REF! | #REF!
| Performance (PF = E / A ) | #REF! | #REF! | #REF! | #REF! | #REF!
Work Schedule: |  | SCHEDULED DAYS LAST WEEK | ACTUAL LAST WEEK | VAR FROM SCHD (LAST WEEK) | VAR FROM SCHD (TO DATE)
| Number of Work Days | 7 | 6 | 0 | 0
| Total Work Hours | 68 | 68 | 0 | 0
Impacts to Schedule:
No. HOURS AFFECTED
|  | TODAY | TO DATE
| Construction | 0 | 0
| Evacuations/Exclusions | 0 | 0
| Permits | 0 | 0
| Equip/Material | 0 | 0
| Site Conditions/Obstruction | 0 | 0
| Safety Stoppage | 0 | 0
| Weather/Wind Delay | 1 | 0
Construction Equipment
| Rental Equipment |  | RPS / Contractor | Qty | On Rent Date | On Rent Finish
Forklift
12k (55'r each) - laydown
12k (55'r each) - field grub
185CFM Air Compressor
2000 Gallon Water Truck
Concrete Mixer
Gas Rammer
Plate Comp
Light Plants
Pallet Jack
Manlift
45' Articulating Boom
60' Articulating Boom
85' Articulating Boom
80' Straight Boom
85' Articulating Boom
SKID STEER
Skid Steer Pallet Forks
Mini Ex (10-11k)
10k Track Excavator
20k Track Excavator (Cab & Air)
3 yard loader
84" roller
3K W/B Padfoot Roller
2500lb Track Loader
1900lb Track Loader
850P Dozer
750L Dozer
260E ADT
824L Wheel Loader
135P Excavator
Bomag BW211 Pad Compactor
Bomag BW211 Smooth Compactor
850P Dozer
850P Dozer
310E ADT
QA/QC:
Highlights and Activities:
Civil
This should list QC activities/inspections. This content should be on "Completed Activities"
Welding:
| Total Field Welds |  | Welds Progressed to Date | Welds Remaining | % Complete
Field Weld Count |  |  |  | 0 | 0%
| Field Weld VT Count | Field Weld RT Count | Total Rejected / Repairs | Reject Rate (Last Week) | Reject Rate (Current)
N.D.E. |  |  | 0 | 0% | 0%
Non-Conformance Report Status:
| NCR's to Date | NCR's Open | NCR's Pending | NCR's Closed
| 0 | 0 | 0 | 0
Completed and Planned Actvities
Formed the remaining pedestals to complete entirety of Scope.
Planned Tomorrow:
Completing the forming of the Pedestals.
Materials Required:
Issues/Areas of Concerns
LIST ANY POTENTIAL IMPACT TO SCHEDULE:
Photos
Attach pictures to the report
Formulas:
Indirect = [Direct]+1
Indirect = +[Direct]+1
Subcontractors = [Indirect]+1
Hrs = [Subcontractors]+1

## RPS - Daily Report
|  | FRAME 6B POWER GROUP DAILY REPORT GENERAL CONSTRUCTION | [5 empty] | Document No.:
[8 empty] | Revision No.: |  | 0
Revision Date:
[9 empty] | DATE: | 2025-12-08
Safety and Personnel
Safety Topic: | MUSTER POINTS
Safety Statistics: |  | Direct | Indirect | Subcontractors |  |  |  | Total Direct | Total Indirect | TOTAL
(Cumm.) Work Hours |  | 4042 | 2594 | 888 |  |  |  | 4042 | 3482 | 7524
(Period) Safe Work Hours |  | 190 | 40 | 280 |  |  |  | 190 | 320 | 510
Total Safe Work Hours To-Date |  | 4232 | 2634 | 1168 | 0 | 0 | 0 | 4232 | 3802 | 8034
Incidents: |  | Period | To Date | Description
First Aids |  | 0 | 0
Incidents |  | 0 | 0
Recordable |  | 0 | 0
| Lost Time | 0 | 0
| Property Damage | 0 | 0
Near Misses |  | 0 | 0
Head Count: |  | Craft Type | Count | Subcontrator | Hrs |  | Per Diem (Y/N)
Total |  | Indirects | 4 |  | 10
Total |  | Directs | 19 |  | 10
Request for additional manpower to be mobilized
List trade/name, work area
N/A
Weather Report: MUST INCLUDE ANY IMPACT TO SCHEDULE, STANDOWNS, ETC. |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Date |  | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16
Hi |  | 65 | 72
Low |  | 45 | 46
Rain Inches
Weather: |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Date | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18
| Hi | [5 empty] | NA | NA
| Lo | [5 empty] | NA | NA
| Rain | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals
Engineering:
Engineering Issues/RFI's/NCR's
Field Change Orders (FCO): |  | Period | To Date
| Transmitted | 0 | 0
| Approved | 0 | 0
| Rejected | 0 | 0
| Outstanding | 0 | 0
| Change Order Number | Description | Status | Date to Client | Hours | Labor $ | Material $ | Subcontract $ | Per Diem | Approved Totals
| Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Current Procurement and Receiving:
Deliveries: | 1 CONEX AND 1 REBAR, 2 structures, 1 rebar
Next Day Procurement and Receiving:
Deliveries: | NOTHING SCHEDULED
Schedule:
Project Completion:
|  | BASELINE SCHEDULE | CURRENT SCHEDULE | VAR FROM SCHD (DAYS +/-) | Status
| Award Contract |  |  | 0
| Mobilization |  |  | 0
| Site Work |  |  | 0
| Laydown Yard Prep |  |  | 0
| Piles Start |  |  | 0
| Piles Finish |  |  | 0
|  | TO DATE SCHEDULED | TO DATE ACTUAL | VAR FROM TO DATE SCHD PCT | PERCENT GAIN FOR WEEK SCHD | PERCENT GAIN FOR WEEK ACTUAL
| UG Piping |  |  | 0% | 0% | 0%
Duct Banks |  |  |  | 0% | 0% | 0%
| Civil |  |  | 0% | 0% | 0%
| Piping / Equipment |  |  | 0% | 0% | 0%
| E&I |  |  | 0% | 0% | 0%
| Percent Complete Overall |  |  | 0% | 0% | 0%
|  | #REF! | #REF! | #REF! | #REF! | #REF!
| Performance (PF = E / A ) | #REF! | #REF! | #REF! | #REF! | #REF!
Work Schedule: |  | SCHEDULED DAYS LAST WEEK | ACTUAL LAST WEEK | VAR FROM SCHD (LAST WEEK) | VAR FROM SCHD (TO DATE)
Number of Work Days
Total Work Hours
Impacts to Schedule:
No. HOURS AFFECTED
|  | TODAY | TO DATE
| Construction | 0 | 0
| Evacuations/Exclusions | 0 | 0
| Permits | 0 | 0
| Equip/Material | 0 | 0
| Site Conditions/Obstruction | 0 | 0
| Safety Stoppage | 0 | 0
| Weather/Wind Delay | 0 | 0
Construction Equipment
| Rental Equipment |  | RPS / Contractor | Qty | On Rent Date | On Rent Finish
Forklift
12k (55'r each) - laydown
12k (55'r each) - field grub
185CFM Air Compressor
2000 Gallon Water Truck
Concrete Mixer
Gas Rammer
Plate Comp
Light Plants
Pallet Jack
Manlift
45' Articulating Boom
60' Articulating Boom
85' Articulating Boom
80' Straight Boom
85' Articulating Boom
SKID STEER
Skid Steer Pallet Forks
Mini Ex (10-11k)
10k Track Excavator
20k Track Excavator (Cab & Air)
3 yard loader
84" roller
3K W/B Padfoot Roller
2500lb Track Loader
1900lb Track Loader
850P Dozer
750L Dozer
260E ADT
824L Wheel Loader
135P Excavator
Bomag BW211 Pad Compactor
Bomag BW211 Smooth Compactor
850P Dozer
850P Dozer
310E ADT
QA/QC:
Highlights and Activities:
Civil
This should list QC activities/inspections. This content should be on "Completed Activities"
Welding:
| Total Field Welds |  | Welds Progressed to Date | Welds Remaining | % Complete
Field Weld Count |  |  |  | 0 | 0%
| Field Weld VT Count | Field Weld RT Count | Total Rejected / Repairs | Reject Rate (Last Week) | Reject Rate (Current)
N.D.E. |  |  | 0 | 0% | 0%
Non-Conformance Report Status:
| NCR's to Date | NCR's Open | NCR's Pending | NCR's Closed
| 0 | 0 | 0 | 0
Completed and Planned Actvities
Completed Today:
COSMETICS ON SITE GROUNDS, CONTINUED WITH THE EXCAVATION ON THE RETENTION POND
Planned Tomorrow:
• Continue Supporting Site Work and Receiving Deliveries • Still working on retention ponds, PREP TOOL ROOM
Materials Required:
None
Issues/Areas of Concerns
LIST ANY POTENTIAL IMPACT TO SCHEDULE:
None
Photos
Attach pictures to the report
Formulas:
Indirect = [Direct]+1
Indirect = +[Direct]+1