## Pipe Audit
RECORD # | DRAWING | Rev | SCHED_ID | Cost Area | Cost Code | SYS | Line Area | SPOOL / FR | SIZE | FLD QTY Ftg | IFC WHRS | UOM | Pipe Spec | Earned Qtys Footage | Earned IFC WHRS | Rec' 2% | M1 Desc | Stage 3% | M2 Desc | Erect/ Install 20% | M3 Desc | Conn 30% | M4 Desc | Support/ Jeep Trace 10% | M5 Desc | Punch 10% | M6 Desc | Test 15% | M7 Desc | Post 10% | M8 Desc | TEST PKG 1 | CWP | IWP_ No | SPOOLS | FOREMAN | GF | WHRS_ UNIT | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | VAR Area | paint_ spec | Insul Spec | Heat Trace Spec | TA_ BANK | TA_ BAY | TA_ LEVEL | INT | TOTAL CONSTRUCTION WHRS | EARNED CONSTRUCTION WHRS | REMAINING CONSTRUCTION HRS | EARNED PUNCH WHRS | EARNED TEST WHRS | EARNED POST WHRS | TEST & POST WHRS | EARNED PUNCH, TEST, POST HRS | Earned Erected A/G Footage | Construction HRS % Complete | TOTAL CONSTRUCTION QTYS | EARNED CONSTRUCTION QTYS | REMAINING CONSTRUCTION QTYS
[14 empty] | #DIV/0! | 0 | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
1 | 120-DR-590-SHT01 | 1 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-590-SHT01-1 | 02 | 131 | 5.06 | LF | 01HDPE | #DIV/0! | 10.12 | 100 | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | 120-DR-590-SHT02 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-590-SHT02-1 | 02 | 208 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | 120-DR-591-SHT01 | 1 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-591-SHT01-1 | 02 | 137 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | 120-DR-591-SHT02 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-591-SHT02-1 | 02 | 218 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | 120-GTD-501-SHT01 | 0 | CN-2880 |  | 08331 | GTD | GAS TURBINE DRAINS | 120-GTD-501-SHT01-1 | 02 | 8 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | 120-GTD-501-SHT01 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-501-SHT01-2 | 06 | 44 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 120-GTD-501-SHT02 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-501-SHT02-1 | 06 | 33 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | 120-GTD-501-SHT03 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-501-SHT03-1 | 06 | 120 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | 120-GTD-519-SHT01 | 0 | CN-2880 |  | 08331 | GTD | GAS TURBINE DRAINS | 120-GTD-519-SHT01-1 | 02 | 9 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | 120-GTD-519-SHT01 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-519-SHT01-2 | 06 | 24 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | 120-GTD-519-SHT02 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-519-SHT02-1 | 06 | 47 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | 120-GTD-519-SHT03 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-519-SHT03-1 | 06 | 105 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | 120-GTD-537-SHT01 | 0 | CN-2880 |  | 08331 | GTD | GAS TURBINE DRAINS | 120-GTD-537-SHT01-1 | 02 | 8 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | 120-GTD-537-SHT01 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-537-SHT01-2 | 06 | 44 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | 120-GTD-537-SHT02 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-537-SHT02-1 | 06 | 29 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | 120-GTD-537-SHT03 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-537-SHT03-1 | 06 | 97 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | 120-GTD-537-SHT04 | 0 | CN-2880 |  | 08332 | GTD | GAS TURBINE DRAINS | 120-GTD-537-SHT04-1 | 06 | 32 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 120-IA-1210-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1210-SHT01-1 | 02 | 32 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 120-IA-1210-SHT02 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1210-SHT02-1 | 02 | 63 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | 120-IA-1210-SHT03 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1210-SHT03-1 | 02 | 53 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | 120-IA-1210-SHT04 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1210-SHT04-1 | 02 | 80 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | 120-IA-1210-SHT05 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1210-SHT05-1 | 02 | 54 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | 120-IA-1230-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1230-SHT01-1 | 02 | 43 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | 120-IA-1230-SHT02 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1230-SHT02-1 | 02 | 53 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | 120-IA-1230-SHT03 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1230-SHT03-1 | 02 | 82 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 | 120-IA-1230-SHT04 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1230-SHT04-1 | 02 | 50 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | 120-IA-1230-SHT05 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1230-SHT05-1 | 02 | 31 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | 120-GCW-802-SHT01 | 0 | CN-2850 |  | 08331 | GCW | GLYCOL COOLING WATER | 120-GCW-802-SHT01-1 | 02 | 146 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | 120-GCW-802-SHT02 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-802-SHT02-1 | 08 | 21 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | 120-IA-1227-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1227-SHT01-1 | 02 | 63 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-004 | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | 120-IA-1227-SHT02 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1227-SHT02-1 | 02 | 38 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | 120-IA-1227-SHT03 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1227-SHT03-1 | 02 | 81 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | 120-IA-1227-SHT04 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1227-SHT04-1 | 02 | 38 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | 120-DR-587-SHT01 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-587-SHT01-1 | 02 | 139 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | 120-DR-587-SHT02 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-587-SHT02-1 | 02 | 210 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | 120-NH3-2103-SHT01 | 0 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2103-SHT01-1 | 03 | 107 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | 120-NH3-2103-SHT02 | 0 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2103-SHT02-1 | 03 | 400 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | 120-NH3-2103-SHT03 | 0 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2103-SHT03-1 | 03 | 71 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | 120-PW-1920-SHT01 | 0 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1920-SHT01-1 | 01.5 | 282 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 | 120-PW-1920-SHT02 | 1 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1920-SHT02-1 | 01.5 | 144 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 | 120-PW-1920-SHT03 | 0 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1920-SHT03-1 | 01.5 | 218 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 | 120-DR-565-SHT01 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-565-SHT01-1 | 02 | 82 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 | 120-DR-588-SHT01 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-588-SHT01-1 | 02 | 63 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 | 120-DR-594-SHT01 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-594-SHT01-1 | 02 | 51 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 | 120-DR-595-SHT01 | 0 | CN-2760 |  | 08331 | DR | DRAINS DRR DRIPS RETURN | 120-DR-595-SHT01-1 | 02 | 46 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 | 120-DW-1727-SHT01 | 0 | CN-2790 |  | 08332 | DW | DEMIN WATER | 120-DW-1727-SHT01-1 | 06 | 30 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 | 120-FG-200-SHT02 | 0 | CN-2820 |  | 08212 | FG | FUEL GAS | 120-FG-200-SHT02-1 | 10 | 52 |  | LF | 01CS300 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-004 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | 120-FG-203-SHT3 | 0 | CN-2820 |  | 08212 | FG | FUEL GAS | 120-FG-203-SHT3-1 | 06 | 85 |  | LF | 01CS300 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | 120-FG-211-SHT02 | 0 | CN-2820 |  | 08212 | FG | FUEL GAS | 120-FG-211-SHT02-1 | 06 | 103 |  | LF | 01CS300 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | 120-FG-219-SHT01 | 0 | CN-2820 |  | 08212 | FG | FUEL GAS | 120-FG-219-SHT01-1 | 06 | 78 |  | LF | 01CS300 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 | 120-FG-227-SHT01 | 0 | CN-2820 |  | 08212 | FG | FUEL GAS | 120-FG-227-SHT01-1 | 10 | 1477 |  | LF | 01CS600 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 | 120-GCW-805-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-805-SHT01-1 | 08 | 51 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 | 120-GCW-808-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-808-SHT01-1 | 08 | 132 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | 120-GCW-810-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-810-SHT01-1 | 08 | 159 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | 120-GCW-813-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-813-SHT01-1 | 08 | 168 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 | 120-GCW-816-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-816-SHT01-1 | 08 | 126 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | 120-GCW-818-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-818-SHT01-1 | 08 | 165 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 | 120-GCW-821-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-821-SHT01-1 | 08 | 51 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | 120-GCW-824-SHT01 | 0 | CN-2850 |  | 08332 | GCW | GLYCOL COOLING WATER | 120-GCW-824-SHT01-1 | 08 | 130 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 | 120-IA-1212-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1212-SHT01-1 | 02 | 26 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 | 120-IA-1213-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1213-SHT01-1 | 02 | 14 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 | 120-IA-1229-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1229-SHT01-1 | 02 | 15 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 | 120-IA-1421-SHT01 | 1 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1421-SHT01-1 | 01 | 328 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 | 120-IA-1422-SHT01 | 1 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1422-SHT01-1 | 01 | 355 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 | 120-IA-1423-SHT01 | 1 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1423-SHT01-1 | 01 | 326 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 | 120-NH3-2105-SHT01 | 1 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2105-SHT01-1 | 03 | 70 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 | 120-NH3-2107-SHT01 | 1 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2107-SHT01-1 | 03 | 70 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 | 120-PW-1909-SHT01 | 0 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1909-SHT01-1 | 01.5 | 44 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 | 120-PW-1911-SHT01 | 0 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1911-SHT01-1 | 01.5 | 44 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 | 120-PW-1913-SHT01 | 0 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1913-SHT01-1 | 01.5 | 42 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 | 120-PW-1915-SHT01 | 1 | CN-2970 |  | 08331 | PW | POTABLE WATER | 120-PW-1915-SHT01-1 | 01.5 | 56 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 | 120-SW-1002-SHT01 | 0 | CN-3000 |  | 08332 | SW | SERVICE WATER | 120-SW-1002-SHT01-1 | 08 | 20 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-002 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 | P02.03-PP-120-ISO-00057-01 | 1 | CN-3030 |  | 08332 | FIREWATER | FIREWATER | P02.03-PP-120-ISO-00057-01-1 | 06 | 28 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 | P02.03-PP-120-ISO-00057-01 | 1 | CN-3030 |  | 08332 | FIREWATER | FIREWATER | P02.03-PP-120-ISO-00057-01-2 | 08 | 620 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 | P02.03-PP-120-ISO-00058-01 | 1 | CN-3030 |  | 08332 | FIREWATER | FIREWATER | P02.03-PP-120-ISO-00058-01-1 | 06 | 28 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Sandra |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 | P02.03-PP-120-ISO-00058-01 | 1 | CN-3030 |  | 08332 | FIREWATER | FIREWATER | P02.03-PP-120-ISO-00058-01-2 | 10 | 635 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  |  | 1 | Bob |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 120 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 | 120-IA-1219-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1219-SHT01-1 | 02 | 35 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Jose |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 | 120-IA-1220-SHT01 | 0 | CN-2910 |  | 08211 | IA | INSTRUMENT AIR | 120-IA-1220-SHT01-1 | 02 | 25 |  | LF | 01CS150 | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Supts |  | Punch |  | Test |  | Post |  |  | PI-401-003 | 1 | Juan |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | CTCE1000-D014 | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 | 120-NH3-2100-SHT02 | 0 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2100-SHT02-1 | 03 | 111 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 | 120-NH3-2100-SHT01 | 0 | CN-2970 |  | 08332 | NH3 | AMMONIA | 120-NH3-2100-SHT01-1 | 03 | 26 |  | LF | 01HDPE | #DIV/0! | 0 |  | Receive |  | Stage |  | Erect |  | Connect |  | Jeep/Trace |  | Mech. Sell Off |  | Test |  | Post |  |  | PI-401-001 | 1 | Jerry |  |  | 0.02 | 0.03 | 0.2 | 0.3 | 0.1 | 0.1 | 0.15 | 0.1 | 401 | N/A | N/A | N/A |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## By Cost Code
ISO SIGN OFFS WITH TEST PACKAGES
Week Ending |  |  | UNIT | TOTAL | TOTAL HOURS | EARNED FOOTAGE | JOB SUBTOTAL | TOTAL | DAILY TOTAL | Weekly Total Hours Earned
|  |  | RATES | FOOTAGE |  |  |  | TOTAL | DAILY TOTAL
SPOOL - Carbon Steel Pipe 2.5" and Under | 8111 | 08111P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8111
SPOOL - Carbon Steel Pipe 3" to 10" | 8112 | 08112P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8112
SPOOL - Carbon Steel Pipe 12" and Over | 8113 | 08113P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8113
SPOOL - Alloy Pipe 2.5" and Under | 8121 | 08121P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8121
SPOOL - Alloy Pipe 3" to 10" | 8122 | 08122P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8122
SPOOL - Alloy Pipe Pipe 12" and Over | 8123 | 08123P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8123
Field Run - C/S Pipe 2.5" and Under | 8211 | 08211P | 0 | 1885 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 8211
Field Run - C/S Pipe 3" to 10" | 8212 | 08212P | 0 | 1795 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 8212
Field Run - C/S Pipe 12" and Over | 8213 | 08213P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8213
Field Run - Alloy Pipe 2.5" and Under | 8221 | 08221P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8221
Field Run - Alloy Pipe 3" to 10" | 8222 | 08222P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8222
Field Run - Alloy Pipe 12" and Over | 8223 | 08223P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8223
Field Run - Special Mill 2.5 and Under | 8231 | 08231P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8231
Underground - Carbon Steel Pipe 2.5" and Under | 8310 | 08310P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8310
Underground - Carbon Steel Pipe 3" to 10" | 8312 | 08312P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8312
Underground - Carbon Steel Pipe 12" and Over | 8313 | 08313P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8313
FLARE VENDOR PIPING | 8500 | 08500P | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500
FCO Work | 8000 | 8000 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0
TOTAL PIPE HOURS | Total |  | 0 | 3680 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | GOAL | REMAINDER TO EARN FOR THE WEEK
0
| Job Total Actual |  |  | #DIV/0! | #DIV/0! | #DIV/0! | Copy | Paste Special / as a Value | Daily Earned | Paste as a Value Special Total Week Ending | Total Weekly Hours
|  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
`
`

## Model Area
|  |  | FOOTAGE |  |  |  | IFC HOURS |  |  |  | Field Construction hours |  |  |  | PIPE SPOOL INFORMATION | [6 empty] | ISO SIGN-OFFS |  |  |  |  | 2022-05-07 | 2022-05-14 | 2022-05-07 | 2022-05-14
MODEL AREA | 'Average' UNIT RATE | TOTAL FOOTAGE ERECTED | TOTAL QTY'S | EARNED ERECTED AG QTY'S | LEFT QTY'S | % COMP QTY'S | TOTAL HRS | EARNED HRS. | HRS. LEFT | % COMP Hrs | Total Construction Hours | Earned Construction Hours | Construction Hours Left | % Construction Hours | Total Spools in audit | Spools Rec'v | SPOOLS NOT ON SITE | % RECIVED | Spools Erected | Spools Not Erected | SPOOL % ERECTED | ISO COUNT | ISO's at QC | ISO's SIGNED-OFF | ISOS REMAINING | MODEL AREA COMPLETE | Week -Ending Spools Erected | Weekly Spools Erected | Week Ending ERECTED AG QTY'S | Weekly ERECTED AG QTY'S
100 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 49 | -49 | 1647 | -1647
101 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 152 | -152 | 3233 | -3233
102 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 500 | -500 | 8237.9 | -8237.9
103 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 716 | -716 | 12741.65 | -12741.65
104 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 245 | -245 | 3910 | -3910
105 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 1014 | -1014 | 15441.95 | -15441.95
106 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 712 | -712 | 13166.75 | -13166.75
107 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 243 | -243 | 4279.3 | -4279.3
108 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 1074 | -1074 | 25394.95 | -25394.95
110 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 276 | -276 | 15005.2 | -15005.2
110-1 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 36 | -36 | 643.1 | -643.1
110-2 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 25 | -25 | 1744.1 | -1744.1
110-3 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60 | -60 | 866 | -866
110-4 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 24 | -24 | 318 | -318
110-5 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 56 | -56 | 1398 | -1398
110-6.1 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 7 | -7 | 490 | -490
110-6.2 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2 | -2 | 212 | -212
110-6.3 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 6 | -6 | 396 | -396
110-6.4 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 60 | -60 | 3120 | -3120
110-6.5 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 11 | -11 | 1034 | -1034
110-6.6 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 15 | -15 | 1208 | -1208
110-6.7 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 72 | -72 | 2655.2 | -2655.2
110-6.8 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 27 |  | 917
110-6.9 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 57 |  | 2962
110-6.10 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 16 |  | 395
110-6.12 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 6 |  | 210
110-6.13 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 0 |  | 0
110-7 | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | [5 empty] | 83 |  | 3974
TOTALS | #DIV/0! | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3588 | -5355 | 95802.2 | -117142.1
[27 empty] | copy paste special |  | copy paste special

## Weekly Gains
Current | time axis 2020-10-03 to 2023-04-01
Hours | 2021-10-23: Reforcasted |  | Budget
Weekly Pipe Hours Needed | 0 | 0 | 465.6867 | 580.1787 | 580.1787 | 509.4252 | 509.4252 | 509.4252 | 320.3204 | 509.4252 | 509.4252 | 509.4252 | 0 | 0 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 509.4252 | 792.4392 | 792.4392 | 905.6448 | 1018.8505 | 1584.8785 | 2150.9065 | 2716.9345 | 2830.1401 | 2830.1401 | 3962.1962 | 4638.857 | 7278.298 | 7278.298 | 7278.298 | 5830.5508 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 5830.5508 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | 7278.298 | -202748.7698 | 7547.0812 | 8260.2243 | 8726.6072 | 8787.9994 | 5273.7898 | 8787.9994 | 9235.5685 | 9783.1475 | 7899.7926 | 7988.9103 | 10309.9324 | 10309.9324 | 10939.6977 | 11223.8843 | 11339.7374 | 10893.1585 | 10820.8741 | 11056.541 | 11402.1198 | 12385.3855 | 12270.5226 | 13455.7886 | 13499.3573 | 14224.1816 | 11152.5901 | 14307.3581 | 14347.9562 | 14425.1916 | 14551.9368 | 14682.6428 | 14435.0935 | 11913.0615 | 15236.163 | 14524.2113 | 14608.378 | 15946.1343 | 12604.2191 | 15625.3105 | 15342.1141 | 15060.8981 | 14604.4172 | 14555.8976 | 14932.1725 | 14972.7706 | 14942.0745 | 12716.1113 | 13735.0242 | 12638.876 | 13934.0538 | 11671.4534 | 10900.0898 | 11528.865 | 11830.8751 | 12686.4054 | 12756.7094 | 12902.2684 | 6493.7127 | 11163.4823 | 11217.9431 | 10967.4232 | 6983.8602 | 6441.2322 | 6430.3401 | 6433.3107 | 4944.0542 | 4965.8385 | 4956.9268 | 4078.6219 | 4078.6219 | 2953.758 | 2953.758 | 1974.453 | 1980.3942 | 1980.3942 | 990.1971 | 990.1971 | 993037
Weekly % Gains Needed | 0% | 0% | 0.0469% | 0.05842% | 0.05842% | 0.0513% | 0.0513% | 0.0513% | 0.03226% | 0.0513% | 0.0513% | 0.0513% | 0% | 0% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0513% | 0.0798% | 0.0798% | 0.0912% | 0.1026% | 0.1596% | 0.2166% | 0.2736% | 0.285% | 0.285% | 0.399% | 0.4671% | 0.7329% | 0.7329% | 0.7329% | 0.5871% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.5871% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | 0.7329% | -20.42% | 0.76% | 0.8318% | 0.8788% | 0.885% | 0.5311% | 0.885% | 0.93% | 0.9852% | 0.7955% | 0.8045% | 1.038% | 1.038% | 1.102% | 1.13% | 1.142% | 1.097% | 1.09% | 1.113% | 1.148% | 1.247% | 1.236% | 1.355% | 1.359% | 1.432% | 1.123% | 1.441% | 1.445% | 1.453% | 1.465% | 1.479% | 1.454% | 1.2% | 1.534% | 1.463% | 1.471% | 1.606% | 1.269% | 1.573% | 1.545% | 1.517% | 1.471% | 1.466% | 1.504% | 1.508% | 1.505% | 1.281% | 1.383% | 1.273% | 1.403% | 1.175% | 1.098% | 1.161% | 1.191% | 1.278% | 1.285% | 1.299% | 0.6539% | 1.124% | 1.13% | 1.104% | 0.7033% | 0.6486% | 0.6475% | 0.6478% | 0.4979% | 0.5001% | 0.4992% | 0.4107% | 0.4107% | 0.2974% | 0.2974% | 0.1988% | 0.1994% | 0.1994% | 0.09971% | 0.09971%
Actual Weekly Hours Earned | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 44678 | 3625 | 2311 | 5108 | 2538 | 11479.4307 | 11995.4495 | 3751.4092 | 3602.0421 | 6468.6133 | 6141.4748 | 5871.354 | 4890.1 | 5975.1264 | -474 | 7883 | 8018 | 7910.5954 | 7467.7327 | 7180.0228 | 9422.4174 | 2247.6217 | 10201.8698 | 10390.6244 | 16320.1158 | 9774.9291 | 9670.7606 | 11785.1805 | 13712.1199 | 8276.2792 | 12273.7307 | 11320 | 12583 | 5958 | 7130 | 10762 | 11481 | 10539 | 11962 | 5526 | 13857 | 8948 | 8862 | 11097 | 5860 | 10605 | 6835 | 11126 | 10964 | 8899 | 13007 | 12757 | 11285 | -491859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Weekly % Gains |  |  |  | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.365% | 0.2327% | 0.5144% | 0.2556% | 1.156% | 1.208% | 0.3778% | 0.3627% | 0.6514% | 0.6185% | 0.5913% | 0.4924% | 0.6017% | -0.04773% | 0.7938% | 0.8074% | 0.7966% | 0.752% | 0.723% | 0.9488% | 0.2263% |  |  |  |  | 0.9739% | 1.187% | 1.381% | 0.8334% | 1.236% | 1.14% | 1.267% | 0.6% | 0.718% | 1.084% | 1.156% | 1.061% | 1.205% | 0.5565% | 1.395% | 0.9011% | 0.8924% | 1.117% | 0.5901% | 1.068% | 0.6883% | 1.12% | 1.104% | 0.8961% | 1.31% | 1.285% | 1.136% | -49.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Planned Total Hours Earned | 0 | 0 | 465.6867 | 1045.8654 | 1626.0442 | 2135.4694 | 2644.8946 | 3154.3198 | 3474.6402 | 3984.0655 | 4493.4907 | 5002.9159 | 5002.9159 | 5002.9159 | 5512.3411 | 6021.7664 | 6531.1916 | 7040.6168 | 7550.042 | 8059.4673 | 8568.8925 | 9078.3177 | 9587.7429 | 10097.1682 | 10606.5934 | 11116.0186 | 11908.4579 | 12700.8971 | 13606.5419 | 14625.3924 | 16210.2709 | 18361.1774 | 21078.1119 | 23908.2521 | 26738.3922 | 30700.5884 | 74634.8994 | 81913.1975 | 89191.4955 | 96469.7936 | 102300.3444 | 109578.6424 | 116856.9404 | 124135.2385 | 131413.5365 | 138691.8346 | 145970.1326 | 153248.4307 | 160526.7287 | 166357.2795 | 173635.5776 | 180913.8756 | 188192.1737 | 195470.4717 | 202748.7698 | 0 | 211112.0052 | 219372.2296 | 228098.8367 | 236886.8361 | 242160.626 | 250948.6254 | 260184.1939 | 269967.3413 | 277867.1339 | 285856.0442 | 296165.9766 | 306475.909 | 317415.6067 | 328639.491 | 339979.2283 | 350872.3868 | 361693.2609 | 372749.8018 | 384151.9216 | 396537.3071 | 408807.8298 | 422263.6184 | 435762.9756 | 449987.1572 | 461139.7473 | 475447.1054 | 489795.0616 | 504220.2532 | 518772.19 | 533454.8328 | 547889.9263 | 559802.9878 | 575039.1508 | 589563.3621 | 604171.7401 | 620117.8744 | 632722.0935 | 648347.404 | 663689.5181 | 678750.4162 | 693354.8334 | 707910.731 | 722842.9035 | 737815.6741 | 752757.7485 | 765473.8599 | 779208.8841 | 791847.76 | 805781.8138 | 817453.2672 | 828353.3571 | 839882.2221 | 851713.0972 | 864399.5026 | 877156.2121 | 890058.4805 | 896552.1931 | 907715.6754 | 918933.6185 | 929901.0418 | 936884.902 | 943326.1343 | 949756.4743 | 956189.785 | 961133.8392 | 966099.6777 | 971056.6044 | 975135.2264 | 979213.8483 | 982167.6063 | 985121.3643 | 987095.8173 | 989076.2115 | 991056.6058 | 992046.8029 | 993037
Planned Total % Complete | 0% | 0% | 0.0469% | 0.1053% | 0.1637% | 0.215% | 0.2663% | 0.3176% | 0.3499% | 0.4012% | 0.4525% | 0.5038% | 0.5038% | 0.5038% | 0.5551% | 0.6064% | 0.6577% | 0.709% | 0.7603% | 0.8116% | 0.8629% | 0.9142% | 0.9655% | 1.017% | 1.068% | 1.119% | 1.199% | 1.279% | 1.37% | 1.473% | 1.632% | 1.849% | 2.123% | 2.408% | 2.693% | 3.092% | 7.516% | 8.249% | 8.982% | 9.715% | 10.3% | 11.03% | 11.77% | 12.5% | 13.23% | 13.97% | 14.7% | 15.43% | 16.17% | 16.75% | 17.49% | 18.22% | 18.95% | 19.68% | 20.42% |  | 21.26% | 22.09% | 22.97% | 23.85% | 24.39% | 25.27% | 26.2% | 27.19% | 27.98% | 28.79% | 29.82% | 30.86% | 31.96% | 33.09% | 34.24% | 35.33% | 36.42% | 37.54% | 38.68% | 39.93% | 41.17% | 42.52% | 43.88% | 45.31% | 46.44% | 47.88% | 49.32% | 50.78% | 52.24% | 53.72% | 55.17% | 56.37% | 57.91% | 59.37% | 60.84% | 62.45% | 63.72% | 65.29% | 66.83% | 68.35% | 69.82% | 71.29% | 72.79% | 74.3% | 75.8% | 77.08% | 78.47% | 79.74% | 81.14% | 82.32% | 83.42% | 84.58% | 85.77% | 87.05% | 88.33% | 89.63% | 90.28% | 91.41% | 92.54% | 93.64% | 94.35% | 94.99% | 95.64% | 96.29% | 96.79% | 97.29% | 97.79% | 98.2% | 98.61% | 98.91% | 99.2% | 99.4% | 99.6% | 99.8% | 99.9% | 100%
Actual Total Hours Earned | 2021-05-08: 44678; 2021-05-15: 48303; 2021-05-22: 50614; 2021-05-29: 55722; 2021-06-05: 58260; 2021-06-12: 69739.4307; 2021-06-19: 81734.8802; 2021-06-26: 85486.2895; 2021-07-03: 89088.3316; 2021-07-10: 95556.9449; 2021-07-17: 101698.4197; 2021-07-24: 107569.7736; 2021-07-31: 112459.8736; 2021-08-07: 118435; 2021-08-14: 117961; 2021-08-21: 125844; 2021-08-28: 133862; 2021-09-04: 141772.5954; 2021-09-11: 149240.3281; 2021-09-18: 156420.3509; 2021-09-25: 165842.7683; 2021-10-02: 168090.39; 2021-10-09: 178292.2598; 2021-10-16: 188682.8842; 2021-10-23: 205003; 2021-10-30: 214777.9291; 2021-11-06: 224448.6897; 2021-11-13: 236233.8702; 2021-11-20: 249945.9901; 2021-11-27: 258222.2693; 2021-12-04: 270496; 2021-12-11: 281816; 2021-12-18: 294399; 2021-12-25: 300357; 2022-01-01: 307487; 2022-01-08: 318249; 2022-01-15: 329730; 2022-01-22: 340269; 2022-01-29: 352231; 2022-02-05: 357757; 2022-02-12: 371614; 2022-02-19: 380562; 2022-02-26: 389424; 2022-03-05: 400521; 2022-03-12: 406381; 2022-03-19: 416986; 2022-03-26: 423821; 2022-04-02: 434947; 2022-04-09: 445911; 2022-04-16: 454810; 2022-04-23: 467817; 2022-04-30: 480574; 2022-05-07: 491859
Actual Total % Complete |  |  |  | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 4.499% | 4.864% | 5.097% | 5.611% | 5.867% | 7.023% | 8.231% | 8.609% | 8.971% | 9.623% | 10.24% | 10.83% | 11.32% | 11.93% | 11.88% | 12.67% | 13.48% | 14.28% | 15.03% | 15.75% | 16.7% | 16.93% | 17.95% | 19% | 21.9% | 21.63% | 22.6% | 23.79% | 25.17% | 26% | 27.24% | 28.38% | 29.65% | 30.25% | 30.96% | 32.05% | 33.2% | 34.27% | 35.47% | 36.03% | 37.42% | 38.32% | 39.22% | 40.33% | 40.92% | 41.99% | 42.68% | 43.8% | 44.9% | 45.8% | 47.11% | 48.39% | 49.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
DELTA % COMPLETE | 2021-10-30: 0.3692%; 2021-11-06: 0.5112%; 2021-11-13: 0.8192%; 2021-11-20: 1.315%; 2021-11-27: 1.617%; 2021-12-04: 1.968%; 2021-12-11: 2.178%; 2021-12-18: 2.46%; 2021-12-25: 2.265%; 2022-01-01: 2.178%; 2022-01-08: 2.224%; 2022-01-15: 2.342%; 2022-01-22: 2.301%; 2022-01-29: 2.376%; 2022-02-05: 1.79%; 2022-02-12: 2.089%; 2022-02-19: 1.9%; 2022-02-26: 1.679%; 2022-03-05: 1.648%; 2022-03-12: 0.9913%; 2022-03-19: 0.8236%; 2022-03-26: 0.1568%; 2022-04-02: -0.08217%; 2022-04-09: -0.4105%; 2022-04-16: -0.6374%; 2022-04-23: -0.7684%; 2022-04-30: -0.9286%; 2022-05-07: -1.245%; 2022-05-14: -52.24%; 2022-05-21: -53.72%; 2022-05-28: -55.17%; 2022-06-04: -56.37%; 2022-06-11: -57.91%; 2022-06-18: -59.37%; 2022-06-25: -60.84%; 2022-07-02: -62.45%; 2022-07-09: -63.72%; 2022-07-16: -65.29%; 2022-07-23: -66.83%; 2022-07-30: -68.35%; 2022-08-06: -69.82%; 2022-08-13: -71.29%; 2022-08-20: -72.79%; 2022-08-27: -74.3%; 2022-09-03: -75.8%; 2022-09-10: -77.08%; 2022-09-17: -78.47%; 2022-09-24: -79.74%; 2022-10-01: -81.14%; 2022-10-08: -82.32%; 2022-10-15: -83.42%; 2022-10-22: -84.58%; 2022-10-29: -85.77%; 2022-11-05: -87.05%; 2022-11-12: -88.33%; 2022-11-19: -89.63%; 2022-11-26: -90.28%; 2022-12-03: -91.41%; 2022-12-10: -92.54%; 2022-12-17: -93.64%; 2022-12-24: -94.35%; 2022-12-31: -94.99%; 2023-01-07: -95.64%; 2023-01-14: -96.29%; 2023-01-21: -96.79%; 2023-01-28: -97.29%; 2023-02-04: -97.79%; 2023-02-11: -98.2%; 2023-02-18: -98.61%; 2023-02-25: -98.91%; 2023-03-04: -99.2%; 2023-03-11: -99.4%; 2023-03-18: -99.6%; 2023-03-25: -99.8%; 2023-04-01: -99.9% | -100%
OVER-ALL DELTA | [32 empty] | 908.0655 | -519.1401 | 2277.8599 | -1424.1962 | 6840.5738 | 4717.1514 | -3526.8888 | -3676.2559 | 638.0625 | -1136.8233 | -1406.9441 | -2388.1981 | -1303.1716 | -7752.298 | 604.702 | 739.702 | 632.2973 | 1637.1819 | -98.2752 | 2144.1193 | -5030.6763 | 2923.5718 | 3112.3264 | 205003 | 3665.9239 | 5076.4601 | 8135.0335 | 13059.154 | 16061.6433 | 19547.3746 | 21631.8061 | 24431.6587 | 22489.8661 | 21630.9558 | 22083.0234 | 23254.091 | 22853.3933 | 23591.509 | 17777.7717 | 20741.6132 | 18868.7391 | 16674.1982 | 16369.0784 | 9843.6929 | 8178.1702 | 1557.3816 | -815.9756 | -4076.1572 | -6329.7473 | -7630.1054 | -9221.0616 | -12361.2532 | -518772.19 | -533454.8328 | -547889.9263 | -559802.9878 | -575039.1508 | -589563.3621 | -604171.7401 | -620117.8744 | -632722.0935 | -648347.404 | -663689.5181 | -678750.4162 | -693354.8334 | -707910.731 | -722842.9035 | -737815.6741 | -752757.7485 | -765473.8599 | -779208.8841 | -791847.76 | -805781.8138 | -817453.2672 | -828353.3571 | -839882.2221 | -851713.0972 | -864399.5026 | -877156.2121 | -890058.4805 | -896552.1931 | -907715.6754 | -918933.6185 | -929901.0418 | -936884.902 | -943326.1343 | -949756.4743 | -956189.785 | -961133.8392 | -966099.6777 | -971056.6044 | -975135.2264 | -979213.8483 | -982167.6063 | -985121.3643 | -987095.8173 | -989076.2115 | -991056.6058 | -992046.8029 | -993037
WEEKLY EI | 2020-11-28: -3474.6402; 2020-12-05: -3984.0655; 2020-12-12: -4493.4907; 2020-12-19: -5002.9159; 2020-12-26: -5002.9159; 2021-01-02: -5002.9159; 2021-01-09: -5512.3411; 2021-01-16: -6021.7664; 2021-01-23: -6531.1916; 2021-01-30: -7040.6168; 2021-02-06: -7550.042; 2021-02-13: -8059.4673; 2021-02-20: -8568.8925; 2021-02-27: -9078.3177; 2021-03-06: -9587.7429; 2021-03-13: -10097.1682; 2021-03-20: -10606.5934; 2021-03-27: -11116.0186; 2021-04-03: -11908.4579; 2021-04-10: -12700.8971; 2021-04-17: -13606.5419; 2021-04-24: -14625.3924; 2021-05-01: -16210.2709; 2021-05-08: 26316.8226; 2021-05-15: 27224.8881; 2021-05-22: 26705.7479; 2021-05-29: 28983.6078; 2021-06-05: 27559.4116; 2021-06-12: -4895.4687; 2021-06-19: -178.3172; 2021-06-26: -3705.2061; 2021-07-03: -7381.462; 2021-07-10: -6743.3995; 2021-07-17: -7880.2227; 2021-07-24: -9287.1668; 2021-07-31: -11675.3649; 2021-08-07: -12978.5365; 2021-08-14: -20730.8346; 2021-08-21: -20126.1326; 2021-08-28: -19386.4307; 2021-09-04: -18754.1333; 2021-09-11: -17116.9514; 2021-09-18: -17215.2267; 2021-09-25: -15071.1074; 2021-10-02: -20101.7837; 2021-10-09: 1.02; 2021-10-16: 0.89; 2021-10-23: 0.98; 2021-10-30: 1.05; 2021-11-06: 1.09; 2021-11-13: 0.94; 2021-11-20: 0.99; 2021-11-27: 0.96; 2021-12-04: 1.05; 2021-12-11: 1.02; 2021-12-18: 0.91; 2021-12-25: 1.02; 2022-01-01: 0.96; 2022-01-08: 1.08; 2022-01-15: 1.1; 2022-01-22: 1.17; 2022-01-29: 0.92; 2022-02-05: 1.13; 2022-02-12: 1.06; 2022-02-19: 1.09; 2022-02-26: 1.28; 2022-03-05: 0.98; 2022-03-12: 1.42; 2022-03-19: 1.08; 2022-03-26: 1.46; 2022-04-02: 1.22; 2022-04-09: 1.42; 2022-04-16: 1.3; 2022-04-23: 1.21; 2022-04-30: 1.2; 2022-05-07: 1.19
MANPOWER 50 HR |  |  | 9.3137 | 11.6036 | 11.6036 | 10.1885 | 10.1885 | 10.1885 | 6.4064 | 10.1885 | 10.1885 | 10.1885 | 0 | 0 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 10.1885 | 15.8488 | 15.8488 | 18.1129 | 20.377 | 31.6976 | 43.0181 | 54.3387 | 56.6028 | 56.6028 | 79.2439 | 92.7771 | 145.566 | 145.566 | 145.566 | 116.611 | 145.566 | 145.566 | 145.566 | 145.566 | 145.566 | 145.566 | 145.566 | 145.566 | 116.611 | 145.566 | 145.566 | 145.566 | 145.566 | 145.566 | -4054.9754 | 150.9416 | 165.2045 | 174.5321 | 175.76 | 105.4758 | 175.76 | 184.7114 | 195.6629 | 157.9959 | 159.7782 | 206.1986 | 206.1986 | 218.794 | 224.4777 | 226.7947 | 217.8632 | 216.4175 | 221.1308 | 228.0424 | 247.7077 | 245.4105 | 269.1158 | 269.9871 | 284.4836 | 225 | 289 | 290 | 288.5038 | 291.0387 | 293.6529 | 288.7019 | 238.2612 | 304.7233 | 290.4842 | 292.1676 | 318.9227 | 252.0844 | 312.5062 | 306.8423 | 301.218 | 292.0883 | 291.118 | 298.6434 | 299.4554 | 298.8415 | 254.3222 | 274.7005 | 252.7775 | 278.6811 | 233.4291 | 218.0018 | 230.5773 | 236.6175 | 253.7281 | 255.1342 | 258.0454 | 129.8743 | 223.2696 | 224.3589 | 219.3485 | 139.6772 | 128.8246 | 128.6068 | 128.6662 | 98.8811 | 99.3168 | 99.1385 | 81.5724 | 81.5724 | 59.0752 | 59.0752 | 39.4891 | 39.6079 | 39.6079 | 19.8039 | 19.8039
ACTUAL MANPOWER 50 HR | 2021-10-09: 208; 2021-10-16: 186; 2021-10-23: 202; 2021-10-30: 205; 2021-11-06: 218; 2021-11-13: 225; 2021-11-20: 280; 2021-11-27: 165; 2021-12-04: 228; 2021-12-11: 231; 2021-12-18: 228; 2021-12-25: 121; 2022-01-01: 136; 2022-01-08: 232; 2022-01-15: 253; 2022-01-22: 245; 2022-01-29: 215; 2022-02-05: 123; 2022-02-12: 294; 2022-02-19: 195; 2022-02-26: 225; 2022-03-05: 217; 2022-03-12: 165; 2022-03-19: 228; 2022-03-26: 198; 2022-04-02: 271; 2022-04-09: 311; 2022-04-16: 230; 2022-04-23: 315; 2022-04-30: 305; 2022-05-07: 268
DELTA | [36 empty] | reforcasted | [16 empty] | 62.434 | 40.434 | 4256.9754 | 54.0584 | 52.7955 | 50.4679 | 104.24 | 59.5242 | 52.24 | 46.2886 | 32.3371 | -36.9959 | -23.7782 | 25.8014 | 46.8014 | 26.206 | -9.4777 | -103.7947 | 76.1368 | -21.4175 | 3.8692 | -11.0424 | -82.7077 | -17.4105 | -71.1158 | 1.0129 | 26.5164 | 5 | 26 | 15 | -20.5038 | -291.0387 | -293.6529 | -288.7019 | -238.2612 | -304.7233 | -290.4842 | -292.1676 | -318.9227 | -252.0844 | -312.5062 | -306.8423 | -301.218 | -292.0883 | -291.118 | -298.6434 | -299.4554 | -298.8415 | -254.3222 | -274.7005 | -252.7775 | -278.6811 | -233.4291 | -218.0018 | -230.5773 | -236.6175 | -253.7281 | -255.1342 | -258.0454 | -129.8743 | -223.2696 | -224.3589 | -219.3485 | -139.6772 | -128.8246 | -128.6068 | -128.6662 | -98.8811 | -99.3168 | -99.1385 | -81.5724 | -81.5724 | -59.0752 | -59.0752 | -39.4891 | -39.6079 | -39.6079 | -19.8039 | -19.8039
TOTAL PIPE DEPT MANPOWER | 2021-12-04: 274; 2021-12-11: 271; 2021-12-18: 274; 2021-12-25: 276; 2022-01-01: 277; 2022-01-08: 286; 2022-01-15: 288; 2022-01-22: 285; 2022-01-29: 279; 2022-02-05: 273; 2022-02-12: 273; 2022-02-19: 261; 2022-02-26: 258; 2022-03-05: 251; 2022-03-12: 254; 2022-03-19: 267; 2022-03-26: 283; 2022-04-02: 291; 2022-04-09: 306; 2022-04-16: 317; 2022-04-23: 327; 2022-04-30: 330; 2022-05-07: 348
Date | time axis 2021-10-23 to 2023-04-08
ISBL Period | [56 empty] | 0.7642% | 0.8053% | 0.855% | 0.855% | 0.5129% | 0.855% | 0.8625% | 0.9005% | 0.7329% | 0.7489% | 1.05% | 1.05% | 1.127% | 1.166% | 1.172% | 1.104% | 1.083% | 1.212% | 1.175% | 1.253% | 1.253% | 1.253% | 1.23% | 1.194% | 0.9199% | 1.169% | 1.223% | 1.254% | 1.26% | 1.262% | 1.267% | 1.018% | 1.29% | 1.162% | 1.189% | 1.349% | 1.14% | 1.419% | 1.442% | 1.453% | 1.416% | 1.331% | 1.375% | 1.38% | 1.526% | 1.245% | 1.37% | 1.354% | 1.287% | 1.21% | 1.018% | 1.106% | 1.06% | 1.14% | 1.32% | 1.36% | 0.7975% | 1.386% | 1.452% | 1.42% | 1.13% | 1.145% | 1.157% | 1.24% | 1.128% | 0.8568% | 0.7196% | 0.3767% | 0.3767% | 0.3486% | 0.277% | 0.2326% | 0.2326% | 0.2326% | 0.1981% | 0.1008%
ISBL To-Date | [56 empty] | 21.43% | 22.23% | 23.09% | 23.94% | 24.46% | 25.31% | 26.17% | 27.07% | 27.81% | 28.56% | 29.61% | 30.66% | 31.78% | 32.95% | 34.12% | 35.22% | 36.31% | 37.52% | 38.69% | 39.95% | 41.2% | 42.45% | 43.68% | 44.88% | 45.8% | 46.97% | 48.19% | 49.44% | 50.7% | 51.96% | 53.23% | 54.25% | 55.54% | 56.7% | 57.89% | 59.24% | 60.38% | 61.8% | 63.24% | 64.69% | 66.11% | 67.44% | 68.81% | 70.2% | 71.72% | 72.97% | 74.34% | 75.69% | 76.98% | 78.19% | 79.2% | 80.31% | 81.37% | 82.51% | 83.83% | 85.19% | 85.99% | 87.37% | 88.83% | 90.25% | 91.38% | 92.52% | 93.68% | 94.92% | 96.05% | 96.9% | 97.62% | 98% | 98.38% | 98.73% | 99% | 99.24% | 99.47% | 99.7% | 99.9% | 100%
ISBL To-Date Hrs | [55 empty] | 167716 | 173918 | 180454 | 187393 | 194332 | 198495 | 205434 | 212434 | 219743 | 225691 | 231769 | 240289 | 248809 | 257954 | 267415 | 276925 | 285889 | 294679 | 304513 | 314048 | 324221 | 334394 | 344567 | 354547 | 364237 | 371703 | 381191 | 391114 | 401288 | 411515 | 421756 | 432039 | 440303 | 450770 | 460197 | 469849 | 480795 | 490050 | 501564 | 513266 | 525056 | 536549 | 547351 | 558510 | 569714 | 582098 | 592204 | 603320 | 614313 | 624756 | 634575 | 642839 | 651812 | 660415 | 669666 | 680382 | 691418 | 697891 | 709142 | 720930 | 732457 | 741630 | 750923 | 760316 | 770381 | 779537 | 786491 | 792331 | 795388 | 798445 | 801274 | 803522 | 805410 | 807298 | 809186 | 810794 | 811612
FTE | [56 empty] | 124.04 | 130.72 | 138.78 | 138.78 | 83.26 | 138.78 | 140 | 146.18 | 118.96 | 121.56 | 170.4 | 170.4 | 182.9 | 189.22 | 190.2 | 179.28 | 175.8 | 196.68 | 190.7 | 203.46 | 203.46 | 203.46 | 199.6 | 193.8 | 149.32 | 189.76 | 198.46 | 203.48 | 204.54 | 204.82 | 205.66 | 165.28 | 209.34 | 188.54 | 193.04 | 218.92 | 185.1 | 230.28 | 234.04 | 235.8 | 229.86 | 216.04 | 223.18 | 224.08 | 247.68 | 202.12 | 222.32 | 219.86 | 208.86 | 196.38 | 165.28 | 179.46 | 172.06 | 185.02 | 214.32 | 220.72 | 129.46 | 225.02 | 235.76 | 230.54 | 183.46 | 185.86 | 187.86 | 201.3 | 183.12 | 139.08 | 116.8 | 61.14 | 61.14 | 56.58 | 44.96 | 37.76 | 37.76 | 37.76 | 32.16 | 16.36
OSBL Period | [56 empty] | 0.8287% | 0.8418% | 0.9579% | 0.9579% | 0.5772% | 0.9642% | 0.9642% | 0.9694% | 0.8219% | 0.8617% | 1.248% | 1.248% | 1.248% | 1.321% | 1.432% | 1.442% | 1.46% | 1.374% | 1.374% | 1.421% | 1.432% | 1.572% | 1.663% | 1.749% | 1.405% | 1.884% | 1.646% | 1.668% | 1.729% | 1.699% | 1.677% | 1.462% | 1.894% | 1.535% | 1.58% | 1.649% | 1.449% | 1.774% | 1.689% | 1.689% | 1.606% | 1.64% | 1.654% | 1.654% | 1.592% | 1.111% | 1.068% | 1.197% | 1.197% | 1.107% | 1.021% | 0.9521% | 0.9809% | 1.121% | 1.033% | 1.05% | 0.4627% | 0.7712% | 0.7712% | 0.7712% | 0.617% | 0.4293% | 0.1689% | 0.102% | 0.102% | 0.1025% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.1082% | 0.0868%
OSBL To-Date | [56 empty] | 20.32% | 21.16% | 22.12% | 23.08% | 23.66% | 24.62% | 25.59% | 26.56% | 27.38% | 28.24% | 29.49% | 30.74% | 31.98% | 33.3% | 34.74% | 36.18% | 37.64% | 39.01% | 40.39% | 41.81% | 43.24% | 44.81% | 46.47% | 48.22% | 49.63% | 51.51% | 53.16% | 54.83% | 56.56% | 58.26% | 59.93% | 61.39% | 63.29% | 64.82% | 66.4% | 68.05% | 69.5% | 71.28% | 72.97% | 74.66% | 76.26% | 77.9% | 79.56% | 81.21% | 82.8% | 83.91% | 84.98% | 86.18% | 87.37% | 88.48% | 89.5% | 90.46% | 91.44% | 92.56% | 93.59% | 94.64% | 95.1% | 95.87% | 96.65% | 97.42% | 98.03% | 98.46% | 98.63% | 98.73% | 98.84% | 98.94% | 99.05% | 99.16% | 99.26% | 99.37% | 99.48% | 99.59% | 99.7% | 99.8% | 99.91% | 100%
OSBL To-Date Hrs | [55 empty] | 37284 | 38869 | 40479 | 42311 | 44143 | 45247 | 47091 | 48935 | 50789 | 52361 | 54009 | 56396 | 58783 | 61170 | 63697 | 66436 | 69194 | 71986 | 74614 | 77242 | 79959 | 82698 | 85704 | 88884 | 92230 | 94917 | 98521 | 101670 | 104860 | 108167 | 111416 | 114624 | 117421 | 121043 | 123979 | 127001 | 130155 | 132927 | 136320 | 139551 | 142782 | 145853 | 148990 | 152153 | 155316 | 158361 | 160486 | 162529 | 164819 | 167109 | 169227 | 171180 | 173001 | 174877 | 177021 | 178997 | 181005 | 181890 | 183365 | 184840 | 186315 | 187495 | 188316 | 188639 | 188834 | 189029 | 189225 | 189432 | 189639 | 189846 | 190053 | 190260 | 190467 | 190674 | 190881 | 191088 | 191254
FTE | [56 empty] | 31.7 | 32.2 | 36.64 | 36.64 | 22.08 | 36.88 | 36.88 | 37.08 | 31.44 | 32.96 | 47.74 | 47.74 | 47.74 | 50.54 | 54.78 | 55.16 | 55.84 | 52.56 | 52.56 | 54.34 | 54.78 | 60.12 | 63.6 | 66.92 | 53.74 | 72.08 | 62.98 | 63.8 | 66.14 | 64.98 | 64.16 | 55.94 | 72.44 | 58.72 | 60.44 | 63.08 | 55.44 | 67.86 | 64.62 | 64.62 | 61.42 | 62.74 | 63.26 | 63.26 | 60.9 | 42.5 | 40.86 | 45.8 | 45.8 | 42.36 | 39.06 | 36.42 | 37.52 | 42.88 | 39.52 | 40.16 | 17.7 | 29.5 | 29.5 | 29.5 | 23.6 | 16.42 | 6.46 | 3.9 | 3.9 | 3.92 | 4.14 | 4.14 | 4.14 | 4.14 | 4.14 | 4.14 | 4.14 | 4.14 | 4.14 | 3.32
Total Period | [56 empty] | 0.7765% | 0.8123% | 0.8746% | 0.8746% | 0.5253% | 0.8758% | 0.8819% | 0.9137% | 0.7498% | 0.7704% | 1.087% | 1.087% | 1.15% | 1.195% | 1.221% | 1.169% | 1.155% | 1.243% | 1.213% | 1.285% | 1.288% | 1.314% | 1.312% | 1.3% | 1.012% | 1.305% | 1.303% | 1.333% | 1.35% | 1.345% | 1.345% | 1.103% | 1.405% | 1.233% | 1.264% | 1.406% | 1.199% | 1.486% | 1.489% | 1.498% | 1.452% | 1.39% | 1.428% | 1.433% | 1.538% | 1.22% | 1.312% | 1.324% | 1.27% | 1.19% | 1.019% | 1.076% | 1.045% | 1.136% | 1.266% | 1.301% | 0.7337% | 1.269% | 1.323% | 1.296% | 1.032% | 1.009% | 0.9688% | 1.023% | 0.9324% | 0.713% | 0.603% | 0.3255% | 0.3255% | 0.3027% | 0.2448% | 0.2089% | 0.2089% | 0.2089% | 0.181% | 0.09802%
Total To-Date | [55 empty] | 205000 | 21.22% | 22.03% | 22.9% | 23.78% | 24.3% | 25.18% | 26.06% | 26.98% | 27.73% | 28.5% | 29.58% | 30.67% | 31.82% | 33.02% | 34.24% | 35.41% | 36.56% | 37.8% | 39.02% | 40.3% | 41.59% | 42.9% | 44.22% | 45.52% | 46.53% | 47.83% | 49.14% | 50.47% | 51.82% | 53.16% | 54.51% | 55.61% | 57.02% | 58.25% | 59.51% | 60.92% | 62.12% | 63.61% | 65.1% | 66.59% | 68.05% | 69.44% | 70.86% | 72.3% | 73.83% | 75.05% | 76.37% | 77.69% | 78.96% | 80.15% | 81.17% | 82.25% | 83.29% | 84.43% | 85.69% | 86.99% | 87.73% | 89% | 90.32% | 91.61% | 92.65% | 93.66% | 94.62% | 95.65% | 96.58% | 97.29% | 97.9% | 98.22% | 98.55% | 98.85% | 99.09% | 99.3% | 99.51% | 99.72% | 99.9% | 100%
FTE | [56 empty] | 155.74 | 162.92 | 175.42 | 175.42 | 105.36 | 175.66 | 176.88 | 183.26 | 150.4 | 154.52 | 218.12 | 218.12 | 230.64 | 239.78 | 244.98 | 234.44 | 231.64 | 249.24 | 243.28 | 257.82 | 258.26 | 263.58 | 263.2 | 260.72 | 203.06 | 261.84 | 261.44 | 267.28 | 270.7 | 269.78 | 269.84 | 221.22 | 281.8 | 247.26 | 253.48 | 282 | 240.54 | 298.14 | 298.66 | 300.42 | 291.3 | 278.76 | 286.44 | 287.34 | 308.58 | 244.64 | 263.18 | 265.66 | 254.64 | 238.76 | 204.36 | 215.86 | 209.6 | 227.9 | 253.84 | 260.88 | 147.16 | 254.52 | 265.26 | 260.04 | 207.08 | 202.3 | 194.32 | 205.22 | 187.02 | 143 | 120.94 | 65.28 | 65.28 | 60.72 | 49.1 | 41.9 | 41.9 | 41.9 | 36.3 | 19.66
Total To-Date Hrs | [56 empty] | 212787 | 220933 | 229704 | 238475 | 243743 | 252526 | 261370 | 270533 | 278053 | 285779 | 296685 | 307591 | 319123 | 331112 | 343361 | 355083 | 366665 | 379127 | 391291 | 404182 | 417095 | 430274 | 443434 | 456470 | 466623 | 479715 | 492787 | 506151 | 519686 | 533175 | 546667 | 557728 | 571818 | 584181 | 596855 | 610955 | 622982 | 637889 | 652822 | 667843 | 682408 | 696346 | 710668 | 725035 | 740464 | 752696 | 765855 | 779138 | 791870 | 803808 | 814026 | 824819 | 835299 | 846694 | 859386 | 872430 | 879788 | 892514 | 905777 | 918779 | 929133 | 939248 | 948964 | 959225 | 968576 | 975726 | 981773 | 985037 | 988301 | 991337 | 993792 | 995887 | 997982 | 1000077 | 1001892 | 1002875

## By Schedule ID (hidden)
ACTIVITY ID | MODEL AREA | DESCRIPTION | ACTUAL START DATE | TOTAL FOOTAGE | EARNED FOOTAGE | FOOTAGE REMAINING | % COMP FTG | TOTAL Const IFC HRS. | Const. IFC EARNED HRS. | Const. IFC HRS. LEFT | % COMP Hrs | Total Spools in audit | Spools Rec'v | Spools Not On-Site | % Spools Rec'v | Spool footage | Spool footage Rec'v | Spools Erected | Spool footage Erected | Spools NOT Erected | Percentage of Spools Eected
CN-FW-2420 | 200 | Area 200 - Install U/G Firewater |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-PW-1010 | 200 | Area 200 - Install Revised Potable Water Reroute Spools |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-FW-3670 | 200 | Area 200 - Install Firewater Monitors, Valves, Etc... |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-201-1350 | 201 | Area 201A - Piperack - Field Fit-up / Weld-Out Rack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-201-1290 | 201 | Area 201 - Piperack - Field Fit-up / Weld-Out Rack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2890 | 202 | Area 202 - Pipe Install - Area 202 Deethanizer Stripper West Side Area Racks & Tower 208 / HT16.215 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2900 | 202 | Area 202 - Pipe Install - Area 202 Refrigeration System Equipment Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2860 | 202 | Area 202 - PV17.207 Deethanizer Rectifier - Pre-Fab Downcomer Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3060 | 202 | Area 202 - PV17.207 Deethanizer Rectifier - Dress-out Downcomer Pipe after Set |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2810 | 202 | Area 202 - PV17.207 Deethanizer Rectifier - Install Remaining Piping / Valves |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3630 | 202 | Area 202 - Install / Dress-out Piping - PV17.206 Deethanizer Stripper |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3670 | 202 | Area 202 - Install / Dress-out Piping - PV17.209 Splitter Tower (Section 1) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3910 | 202 | Area 202 - Install / Dress-out Piping - PV17.209 Splitter Tower (Section 2) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2880 | 202 | Area 202 - Pipe Install - Area 202 Deethanizer Stripper Tower Area (205 Valve Platform to Tower) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-2990 | 202 | Area 202 - Pipe Install - Area 202 Pipe rack / HT16.651 A-F Refrigerant Condenser |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3900 | 202 | Area 202 - Install Remaining after setting PV17.206 Piping / Valves - Deethanizer Stripper |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-4440 | 202 | Area 202 - Complete Installation of Piping / Valves on PV17.209 Splitter Tower |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-202-3320 | 202 | Area 202 - Install Piping / Valves- Area 202 Splitter Area Base ( HT16.216A/B/C/D) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-2770 | 203 | Area 203 - Pipe Install - Area 203 Feed Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-3120 | 203 | Area 203 - Pipe Install - Area 203 Structure D |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-3330 | 203 | Area 203 - Pipe Install - Area 203 Vessel Reactor & Exchangers |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-3320 | 203 | Area 203 - Install Large Bore Pipe Below CM12.201 Table Top |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-2980 | 203 | Area 203 - Pipe Install - Area 203 Solvent Recovery Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-3130 | 203 | Area 203 - Pipe Install - Area 203 Heat Pump Compressor Area West |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-3940 | 203 | Area 203 - CM12.201 Install Remaining Compressor Area Piping - CM12.201 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-203-9220 | 203 | Area 203 - CM12.201 Install Lube Oil Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-3070 | 204 | Area 204 - Pipe Install - Area 204 Pipe Rack (West) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-3450 | 204 | Area 204 - Pipe Install - Area 204 Caustic Storage Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-3090 | 204 | Area 204 - Pipe Install - Area 204 Raw Water Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-3120 | 204 | Area 204 - Pipe Install - Area 204 Process Water |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-1400 | 204 | Area 204 - Install UG Pipe for WS24.831 - Raw Water Clarifier |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-3080 | 204 | Area 204 - Pipe Install - Area 204 Instrument Air Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-4280 | 204 | Area 204 - Pipe Install - Area 204 Clarified Water Tank & Pumps |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-204-5470 | 204 | Area 204 - Pipe Install - Area 204 Sludge Thickener Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-205-2210 | 205 | Area 205 - Field Fit-up / Weld-Out Rack Piping West (Column Lines 1-28) (Install) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-205-1530 | 205 | Area 205 - Install / Field Fit-up & Weld-Out Air Cooler Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-6190 | 206 | Area 206 - Pipe Install - Area 206 KO Drum Area & Finger Racks |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-2800 | 206 | Area 206 - Pipe Install - Area 206 KO Drum Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-2790 | 206 | Area 206 - Field Fit-up / Weld-Out Rack Piping - Area 206 Flare Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-2770 | 206 | Area 206 - Connect / Install Lube Oil spools on Skid(Cooler to Compressor) - Ethane Compressor Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-2810 | 206 | Area 206 - Pipe Install - Ethane Compressor Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-206-3020 | 206 | Area 206 - Pipe Install Bridge Area - Area 206 Flare Pipe Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-3670 | 207 | Area 207 - Pipe Rack - Install Pipe / Valves in Rack and Weld out |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5680 | 207 | Area 207 - Install Piping / Valves and Weld out Ground Level & 115' Elev. under Structure |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5651 | 207 | Area 207 - Pipe Installation for 132' elev. to Reactor Set Level 197' & 224' #4 Prior to Reactor Setting Summary |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-3532 | 207 | Area 207 - HCFE - Install Piping Prior to HCFE Set overall Summary |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5650 | 207 | Area 207 - Elev. 132' Install Piping / Valves and Weld out at Lock Hopper Level |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5631 | 207 | Area 207 - Install Horseshoe Large Bore Pipe Prior to Setting Reactors Summary |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5660 | 207 | Area 207 - 3rd Level Install Piping / Valves and Weld at Catalyst Collectors Level |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5670 | 207 | Area 207 - Elev. 204' Install Piping / Valves and Weld at Catalyst Collectors Level |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-6660 | 207 | Area 207 - Reactors #1 & #2 - Install Remaining Piping / Valves and Weld out in Structure |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-3531 | 207 | Area 207 - HCFE - Install Piping After to HCFE Set overall Summary |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1890 | 207 | Area 207 - Install Vendor Supplied Pipe on Cold Box |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5630 | 207 | Area 207 - Overall Large Bore Pipe Task (Installation Post Reactor Set) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1910 | 207 | Area 207 - Install PV17.121 Structure Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1900 | 207 | Area 207 - Install Cold Box Pipe to Struture / Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-6841 | 207 | Area 207 - Overall Install Piping above Reactor Head Summary |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-6670 | 207 | Area 207 - Reactors #3 & #4 - Install Remaining Piping / Valves and Weld out in Structure |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5430 | 207 | Area 207 - CCR - Install Ground Level Equipment Piping / Valves and Weldout |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1920 | 207 | Area 207 - Install Turboexpanders Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-4040 | 207 | Area 207 - CCR - Install External Piping / Valves and Weld Lower Levels |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1930 | 207 | Area 207 - Install Piping Pumps / Feed Filter / AH-004 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CP-207-1921 | 207 | Area 207 - Turboexpanders Com. - Install Lube Oil Piping Turboexpanders |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5460 | 207 | Area 207 - CCR - Install External Piping / Valves and Weld Upper Levels |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-6730 | 207 | Area 207 - Pipe Rack - Install East Loop Pipe / Valves in Rack and Weld out |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-6820 | 207 | Area 207 - Pipe Rack - Install West Loop Pipe / Valves in Rack and Weld out |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-207-5180 | 207 | Area 207 - Reactor / HCFE - Install Remaining Piping / Valves and Weld out |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-6570 | 208 | Area 208 - Install Area 207 N2 Pipe at Grade |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-2083 | 208 | Area 208 - HR15.103 Vendor Pipe - Burner Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-2081 | 208 | Area 208 - HR15.101 Vendor Pipe - Burner Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-2084 | 208 | Area 208 - HR15.104 Vendor Pipe - Burner Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-8560 | 208 | Area 208 - HR15.102 Vendor Pipe - Burner Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7060 | 208 | Area 208 - Vendor Pipe HR15.103 - Install Crossover Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-8190 | 208 | Area 208 - Vendor Pipe HR15.104 - Install Crossover Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-6810 | 208 | Area 208 - Vendor Pipe HR15.101 - Install Crossover Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-8340 | 208 | Area 208 - Vendor Pipe HR15.102 - Install Crossover Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7880 | 208 | Area 208 - Vendor Pipe HR15.101 - Install Ammonia Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-8350 | 208 | Area 208 - Vendor Pipe HR15.102 - Install Ammonia Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-6660 | 208 | Area 208 - Pipe HR15.104 - Install Utility Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7050 | 208 | Area 208 - Pipe HR15.103 - Install Utility Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7090 | 208 | Area 208 - HR15.102 - Install Utility Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7800 | 208 | Area 208 - Vendor Pipe 208 HR15.103 - Install Ammonia Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-8180 | 208 | Area 208 - Vendor Pipe 208 HR15.104 - Install Ammonia Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-1450 | 208 | Area 208 - Install Rack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-208-7110 | 208 | Area 208 - HR15.101 - Install Utility Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2650 | 209 | Area 209 - Install Pipe - Load Pipe in Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2600 | 209 | Area 209 - Pipe Install - Area 209 Cooler Structure |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-3190 | 209 | Area 209 - Pipe Install - Area 209 Hot Oil Storage Area / Ammonia Pump / Unloading Skid Area - Finger Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2610 | 209 | Area 209 - Pipe Install - Area 209 Hot Oil Heater Area (Blower / Fans / Heater) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2480 | 209 | Area 209 - HR15.601 - Install, Weld and NDE Inlet & Outlet pipes (Vendor Supply) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2640 | 209 | Area 209 - HR15.601 - Install Crossover piping`(Vendor Supply) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2470 | 209 | Area 209 - Install Piping - Install Burner Piping & Supports`(Vendor Supply) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-3140 | 209 | Area 209 - Pipe Install - Area 209 Hot Oil Drum Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2550 | 209 | Area 209 - Install Piping - HR15.601 Area (Heater Burner Pipimg) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-5660 | 209 | Area 209 - Pipe Install - Hot Oil Pump Alignment (60102-02 / 60102-02 / 60103-04 / 60104-01 / 60105-01 / 60113-03) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-209-2830 | 209 | Area 209 - Pipe Install - Area 209 Chlorine Storage Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-210-2050 | 210 | Area 210 - Pipe Install - Area 210 Process Waste Water / Propane Feed Filter Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-210-2080 | 210 | Area 210 - Pipe Install - Area 210 Fuel Gas Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-210-2060 | 210 | Area 210 - Pipe Install - Area 210 Solvent Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-210-2070 | 210 | Area 210 - Pipe Install - Area 210 Sulfur Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2560 | 211 | Area 211 - Load East Piperack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-3970 | 211 | Area 211 - Pipe Dress Out PV17.212- Area 211 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2680 | 211 | Area 211 - Pipe Install - Area 211 Coalescer Area (South) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2580 | 211 | Area 211 - Pipe Install - Area 211 Caustic Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2880 | 211 | Area 211 - Pipe Install - Area 211 Debutanizer (North) Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-3740 | 211 | Area 211 - Pipe Install - Area 211 Wash Water Pumps / Caustic Circulation Pumps Area (North) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2700 | 211 | Area 211 - Pipe Install - Area 211 Heater / Regen KO Drum Area (South) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-3780 | 211 | Area 211 - Field Fit-up / Weld-Out Rack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-211-2930 | 211 | Area 211 - Install / Dress-out PV17.112 - Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-2810 | 212 | Area 212 - Install DU22.101 A Piping / Valves - Reactor Effluent Dryers |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-2820 | 212 | Area 212 - Install DU22.101 B Piping / Valves - Reactor Effluent Dryers |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-2830 | 212 | Area 212 - Install PV17.109 - Piping / Valves - Chloride Treater |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-2840 | 212 | Area 212 - PV17.107 - Reactor Effluent Compressor Interstage Contact Cooler - Install Piping / Valves |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3720 | 212 | Area 212 - CM12 102 Erect Large Bore Below Table Top (212-12001 & 120021) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-4070 | 212 | Area 212 - CM12 102 Install Large Bore Spools(2) to Compressor (212-12001 & 120021) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3230 | 212 | Area 212 - Install Piping - CM12.101 - Piping / Valves - Containment / LO / Sump Pump Piping Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3740 | 212 | Area 212 - CM12.101 Reactor Effluent Compressor 1st Stage - Install Large Bore Pipe Below Table Top (11810) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3850 | 212 | Area 212 - Field Fit-up / Weld-Out Rack Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3300 | 212 | Area 212 - Install Piping - CM12.102 - Piping / Valves - Containment / LO / Sump Pump Piping Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3350 | 212 | Area 212 - Pipe Install - Area 212 Circulation Pump PM18.103 Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3360 | 212 | Area 212 - Pipe Install - Area 212 Solvent Circulation Pumps Area PM18.102A/B/C |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-4080 | 212 | Area 212 - CM12.101 Reactor Effluent Compressor 1st Stage - Install Large Bore Spools(3) to Compressor (11810 / 11810) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-4300 | 212 | Area 212 - Install Pipe for PV17.106 & 212 Compr. 1 RV Platform Structure (Compressor Piping and Grade Level) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3110 | 212 | Area 212 - Install Piping - PV17.106 Reactor Effluent Contact Cooler - Piping / Valves |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3730 | 212 | Area 212 - CM12 102 Install Compressor Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-4280 | 212 | Area 212 - Cooler Tie-In and Piping above Cable Tray |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3140 | 212 | Pipe Install / Alignment for - Area 212 Solvent Circulation Pumps Area PM18.102A/B/C (11501 / 11502 / 11503 / 11504) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3920 | 212 | Area 212 - CM12 102 Install Lube Oil Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-4310 | 212 | Area 212 - Install PV17.109 - Piping / Valves on Pipe Rack 201 Valve Platform - Chloride Treater |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-212-3910 | 212 | Area 212 - CM12.101 Reactor Effluent Compressor 1st Stage - Install Lube Oil Piping ********** |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-213-1760 | 213 | Area 213 - Pipe Install - Area 213 Depropanizer (South) Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-213-1880 | 213 | Area 213 - Pipe Install - Area 213 Depropanizer (North) Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-213-2320 | 213 | Area 213 - PV17.204 Depropanizer - Install / Dress-out Piping |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4110 | 214 | Area 214 - Pipe Install / Load in rack - Area 214 Piperack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-2650 | 214 | Area 214 - Pipe Install - Area 214 HT16.211 WSAC 8-Cell Spray Water Pumps Area (West Side) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4230 | 214 | Area 214 - Pipe Install - Area 214 Reactor Effluent Compressor Discharge Area (PV17.108) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-2130 | 214 | Area 214 - Pipe Install - Area 214 Modular Cooling Tower Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4460 | 214 | Area 214 - Pipe Install - Area 214 WSAC 4-Cell South Finger Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4320 | 214 | Area 214 - Pipe Install - Area 214 HT16.102 WSAC 4-Cell Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4470 | 214 | Area 214 - Pipe Install - Area 214 WSAC 4-Cell West Finger Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4670 | 214 | Area 214 - Pipe Install - Area 214 Modular Cooling Tower Chem Treat Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-5130 | 214 | Area 214 - Install PSV's on valve structure |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4660 | 214 | Area 214 - Pipe Install - Area 214 WSAC 4-Cell Chem Treat Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4100 | 214 | Area 214 - Pipe Install - Area 214 - HT16.211WSAC 8-Cell Area * |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-214-4650 | 214 | Area 214 - Pipe Install - Area 214 WSAC 8-Cell Chem Treat Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-215-1620 | 215 | 215 - Pipe Install - Area 215 Meter Skid Area |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-216-1240 | 216 | Area 216 - Field Fit-up / Weld-Out Rack Piping Battery Limit Pipe Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-217-2610 | 217 | Area 217 - Install Piping / Valves and Weld out from Building to Rack PCR#1 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-217-2640 | 217 | Area 217 - Install Piping Area 217 Electrical Pipe Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-217-2940 | 217 | Area 217 - Install Piping / Valves and Weld Out from Building to Rack PCR#2 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-217-2960 | 217 | Area 217 - Install Piping / Valves and Weld Out from Building to Rack PCR#3 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-217-2620 | 217 | Area 217 - Install Piping / Valves and Weld Out from PKG-SE29.911 - Chlorine Scavenger Skid to Rack |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-218-1750 | 218 | Area 218 - Pipe Install - Area 218 |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-219-1510 | 219 | Area 219 - Pipe Install - Area 219 South Pond Area (Potable Water) **************** |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
CN-219-1230 | 219 | Area 219 - Pipe Install - Area 219 South Pond Area (Pipe Rack and Equipment) |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!
|  | TOTALS |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | #DIV/0!

## Supervisor Assingments
SUPERVISOR | AREA DESCRIPTION | TOTAL HOUR'S | EARNED HOUR'S | TOTAL QTY'S | EARNED ERECTED AG QTY'S | LEFT QTY'S | TOTAL SPOOLS IN AUDIT | SPOOLS REC'V | % SPOOLS REC'V | SPOOLS ERECTED | SPOOLS NOT ON SITE | SPOOLS LEFT TO ERECT | TOTAL CONST. WHRS | EARNED CONST. WHRS | REMAINING CONST. WHRS | ISO COUNT | ISOs AT "F" | ISOs AT "QC" | ISOs AT "RF" | ISO'S AT "O" | ISO's SIGNED-OFF | REMAINING ISOs | FITTERS | HELPERS | WELDERS | STR- WELDERS | Comments | REMAINING CONST. QTYS | REMAINING CONST. UNIT RATE
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | ON HOLD COLD BOX SET | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | ADDED THIS ROW JUST TO COUNT THE FITTER ON P.P.
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | ADDED THIS ROW JUST TO COUNT THE FITTER ON P.P. | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | ADDED THIS ROW JUST TO COUNT THE FITTER ON P.P. | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0 | #DIV/0!
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | 0
TOTALS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | #DIV/0!

## By Pipe Size (hidden)
Pipe Size | TOTAL FOOTAGE | EARNED FOOTAGE | FOOTAGE REMAINING | % COMP FTG | TOTAL IFC HRS. | IFC EARNED HRS. | IFC HRS. LEFT | % COMP Hrs | TOTAL Const IFC HRS. | Const. IFC EARNED HRS. | Const. IFC HRS. LEFT | % COMP Hrs | Total Spools in audit | Spools Rec'v | Spools Not On-Site | % Spools Rec'v | Spool footage | Spool footage Rec'v | Spools Erected | Spool footage Erected | Spools NOT Erected | Percentage of Spools Eected | ISO SIGN-OFFS
[23 empty] | ISO COUNT | ISO's at QC | ISO's SIGNED-OFF | ISOS REMAINING | MODEL AREA COMPLETE
0.5 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
0.75 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
1 | 1009 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
1.5 | 830 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
2 | 2332 | #REF! | #REF! | #REF! | 5.06 | 100 | -94.94 | 1976% | 3.542 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
3 | 855 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
4 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
6 | 927 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
8 | 1643 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
9 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
10 | 2164 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
12 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
14 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
16 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
18 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
20 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
24 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
26 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
30 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
36 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
42 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
48 | 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 0 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!
| 9760 | #REF! | #REF! | #REF! | 5.06 | 100 | -94.94 | 1976% | 3.542 | #REF! | #REF! | #REF! | 0 | 0 | 0 | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF! | #REF! | #VALUE! | #REF!