## Shipment Log
Shipment # | PROJECT | PO# | RTS Date | ETA | Status | Supplier | Category | Part Description | # Pcs | # Loads | Truck Type | Storage Loc | Ship from | Ship to | Shipper | Shipment By (RPS/Supplier) | NCR/OSD (X) | Rcvng Pics | det pk list | Delivery Date | Delivery Time | Progress Notes | Special Receiving Instructions
0255-F6B-001 | F6B | 14723 |  | 2026-01-28 | Not RTS | Braden Americas, Inc. | Major Equipment - SCR | Simple Cycle System - SCR
0255-F6B-001A | F6B | 14723 |  |  | Delivered | Braden Americas, Inc. | Major Equipment - SCR | Anchor Bolt Template |  |  |  |  | Mexico | Fermi Site |  |  |  | PENDING | PENDING
0255-F6B-001B | F6B | 14723 | 2026-01-20 | 2026-01-28 | Not RTS |  |  | Unit 1 - Stack, Breach, Units 1, 2: CO AIG Duct, SCR Duct, Units 1-3 Field Crates (Shiploose)
0255-F6B-001B | F6B | 14723 | 2026-02-06 |  | Not RTS
0255-F6B-001B | F6B | 14723 | 2026-02-27 |  | Not RTS
0255-F6B-001C | F6B | 14723 |  |  | Not RTS | Braden Americas, Inc. | Major Equipment - SCR | Spare Parts
0255-F6B-001C | F6B | 14723 |  |  | Not RTS | Braden Americas, Inc. | Major Equipment - SCR | Ammonia Storage/Transfer System
0255-F6B-001D | F6B | 14723 |  |  | Not RTS | Braden Americas, Inc. | Major Equipment - SCR | CEMS System
0255-F6B-002A | F6B | 14795 | 2026-01-05 |  | Delivered | Equisales Associates | Major Equipment - Transformers, Electrical Panels | 3000A MLO Nema 3r Switchboard |  |  |  |  | Equisales - Houston | Lynn Eng - Houston
0255-F6B-002B | F6B | 14795 | 2026-01-05 |  | Not RTS | Equisales Associates | Major Equipment - Transformers, Electrical Panels | 13.8kv-480V, 3750 KVA, 3P Padmount Xfmr
0255-F6B-002C | F6B | 14795 |  |  | Not RTS | Equisales Associates | Major Equipment - Transformers, Electrical Panels | 7500/9375 kVA 3P Substation Xfmr
0255-F6B-002D | F6B | 14795 |  |  | Not RTS | Equisales Associates | Major Equipment - Transformers, Electrical Panels | 3000 kVA 3P Substation Xfmr
0255-F6B-002E | F6B | 14795 |  |  | Not RTS | Equisales Associates | Major Equipment - Transformers, Electrical Panels | 1500 kVA 3P Substation Xfmr
0255-F6B-002F | F6B | 14795 |  |  | Delivered | Equisales Associates | Major Equipment - Transformers, Electrical Panels | Nema 3R Switchboard, 2000A Main |  |  |  |  | Equisales - Houston | Lynn Eng - Houston
0255-F6B-002G | F6B | 14795 |  |  | Delivered | Equisales Associates | Major Equipment - Transformers, Electrical Panels | Nema 1 2000A -Transfer Switch (ASCO) |  |  |  |  | Equisales - Houston | Lynn Eng - Houston
0255-F6B-002H | F6B | 14795 | 2026-04-10 |  | Not RTS | Equisales Associates | Major Equipment - Transformers, Electrical Panels | Vaults |  |  |  |  | Equisales - Houston | Fermo Site
0255-F6B-003A | F6B | - | 2025-12-01 |  | In Transit | RPS | Major Equipment - GSUs | GSU Transformer |  |  |  |  | Eltas - Turkey | RPS - Houston | Eltas | RPS
0255-F6B-003B | F6B | - | 2025-12-01 |  | Not RTS | RPS | Major Equipment - GSUs | GSU Transformer |  |  |  |  | RPS - Houston | Fermi Site | RPS | RPS
0255-F6B-004 | F6B | 14986 |  |  | Not RTS | Alfa Laval | Major Equipment - WSAC | Wet Surface Air Cooler (WSAC)
0255-F6B-005 | F6B | 14992 |  |  | Not RTS | Equisales Associates | Major Equipment - GSU Relay Panel Bldg | GSU Relay Protection Panel Bldg | 1 | 1
0255-F6B-006 | F6B | 15057 |  |  | Not RTS | Equisales Associates | Major Equipment - LV MCC | Rockwell MCC (Top feed,1600A,8 sections) |  |  |  |  | Equisales - Houston | Lynn Eng - Houston
0255-F6B-007 | F6B | 15060 |  |  | Not RTS | AG Power Systems, Inc. | Major Equipment - GSU Oil | Shell Diala Oil
0255-SITE-008A | F6B | 15156 |  |  | Delivered | Groves | Site - Consumables, Tooling, Supplies | Consumables, Tooling, Site Supplies | [9 empty] | PENDING | PENDING
0255-SITE-008B | F6B | 15156 |  |  | Not RTS | Groves | Site - Consumables, Tooling, Supplies | Consumables, Tooling, Site Supplies
0255-SITE-008C | F6B | 15156 |  |  | Not RTS | Groves | Site - Consumables, Tooling, Supplies | Consumables, Tooling, Site Supplies
0255-SITE-008D | F6B | 15156 | 2026-01-06 | 2026-01-07 | Not RTS | Groves | Site - Consumables, Tooling, Supplies | Rigging Gear | [14 empty] | Alert Jason Sullivan
0255-SITE-009 | F6B | 15157 |  |  | Not RTS | Grainger | Site - Consumables, Tooling, Supplies | Consumables, Tooling, Site Supplies
0255-F6B-010 | F6B | 15167 | 2026-01-25 |  | Not RTS | Lynn Energy | Major Equipment - MCC E-Houses | Electrical Buildings (2) | 2 | 2
0255-F6B-011A | F6B | 15171 |  |  | Delivered | USA Weld Express | Bulks - Structural - Pipe Rack | Bridges | [9 empty] | PENDING | PENDING |  |  | Mark the pieces per drawing
0255-F6B-011B | F6B | 15171 |  |  | Delivered | USA Weld Express | Bulks - Structural - Pipe Rack | [10 empty] | PENDING | PENDING |  |  | Mark the pieces per drawing
0255-F6B-011C | F6B | 15171 | 2025-12-20 | 2026-01-05 | Not RTS | USA Weld Express | Bulks - Structural - Pipe Rack |  |  | 3 | [10 empty] | 2026-01-07 | Schedule with Claudio
0255-F6B-011D | F6B | 15171 | 2025-12-20 | 2026-01-06 | Not RTS | USA Weld Express | Bulks - Structural - Pipe Rack |  |  | 4 | [10 empty] | 2026-01-07 | Schedule with Claudio
0255-F6B-012A | F6B | 15174 |  |  | Delivered | Katy Steel | Bulks - Civil - Rebar | Reinforcing Steel (Rebar & Cages) | [9 empty] | PENDING | PENDING
0255-F6B-012B | F6B | 15174 |  |  | Delivered | Katy Steel | Bulks - Civil - Rebar | Reinforcing Steel (Rebar & Cages) | [9 empty] | PENDING | PENDING
0255-F6B-012C | F6B | 15174 |  |  | Delivered | Katy Steel | Bulks - Civil - Rebar | Reinforcing Steel (Rebar & Cages) | [9 empty] | PENDING | PENDING
0255-F6B-012D | F6B | 15174 |  |  | Delivered | Katy Steel | Bulks - Civil - Rebar | Reinforcing Steel (Rebar & Cages) | [9 empty] | PENDING | PENDING
0255-F6B-012E | F6B | 15174 |  |  |  | Katy Steel | Bulks - Civil - Rebar | Reinforcing Steel (Rebar & Cages)
0255-F6B-013A | F6B | 15216 |  |  | Delivered | Madden Bolt | Bulks - Civil - Anchor Bolts/Embeds | 1 1/2" x 11 x 24" Embed Plt A36 Galv | [9 empty] | PENDING | PENDING
0255-F6B-013B | F6B | 15216 | 2025-12-26 | 2026-01-06 | Not RTS | Madden Bolt | Bulks - Civil - Anchor Bolts/Embeds | 1 1/2" x 14 x 32" Embed Plt A36 Galv | [12 empty] | 2026-01-07
0255-F6B-014 | F6B | 15330 |  |  | Not RTS | Petrotech | Major Equipment - CT Control Modules | (3 Controls Modules
0255-SITE-015 | F6B | 15360 |  |  | Not RTS | White Cap | Site - Consumables, Tooling, Supplies | Civil Supplies
0255-F6B-016 | F6B | 15374 |  |  | Not RTS | Gaumer | Major Equipment - Last Chance Filters | Last Chance Gas Fuel Filter
0255-F6B-017 | F6B | 15399 |  |  | Not RTS | CST Industries | Major Equipment - Tanks | Demin Water Tank (135,447 Gal) TK-400
0255-TM-018 | F6B | 15402 |  |  | Not RTS | Equisales Associates | Major Equipment - Blackstart Gen | Black Start System
0255-F6B-019 | F6B | 15423 |  |  | Not RTS | Camfil Power Systems | Major Equipment - Inlet Air Filters | Swgr & MCC Refurbishment
0255-F6B-020 | F6B | 15441 |  |  | Not RTS | Shermco | Major Equipment - CT MCC/Swgr | Procurement-Specialist
0255-F6B-021 | F6B | 15450 |  |  | Not RTS | Atlas Copco | Major Equipment - Air Compressor | Atlas Copco Start-Up
0255-F6B-022 | F6B | 15460 |  |  | Not RTS | Corrpro | Major Equipment - Cathodic Protection | Cathodic Protection
0255-F6B-023A | F6B | 15461 |  |  | Delivered | Magnatex | Bulks - Piping - U/G Piping | U/G Piping (11/07/25)
0255-F6B-023B | F6B | 15461 |  |  | Delivered | Magnatex | Bulks - Piping - U/G Piping | U/G Piping (11/07/25)
0255-F6B-023C | F6B | 15461 |  | 2026-01-06 | On Site | Magnatex | Bulks - Piping - U/G Piping | U/G Piping (11/07/25)
0255-F6B-024A | F6B | 15462 |  | 2026-01-05 | Delivered | Magnatex | Tagged Equipment - Pumps | Pumps |  |  |  |  | Magnatex - Houston | Fermi site | [8 empty] | Tag the outer crate with pump tag #, check for any shiploose, pics of the pumps and nameplates
0255-F6B-024B | F6B | 15462 |  | 2026-01-06 | In Transit | Magnatex | Tagged Equipment - Pumps | Pumps |  |  |  |  | Fermi site | Cotton Warehouse | [8 empty] | Tag the outer crate with pump tag #, check for any shiploose, pics of the pumps and nameplates
0255-F6B-024C | F6B | 15462 |  |  | Not RTS | Magnatex | Tagged Equipment - Pumps | Pumps | [14 empty] | Tag the outer crate with pump tag #, check for any shiploose, pics of the pumps and nameplates
0255-F6B-025A | F6B | 15463 |  |  | Delivered | Momentum | Site - Consumables, Tooling, Supplies | Tools & Consumables
0255-F6B-025B | F6B | 15463 |  |  | Not RTS | Momentum | Site - Consumables, Tooling, Supplies | Tools & Consumables
0255-F6B-027A | F6B | 15510 |  |  | Not RTS | Fluid Flow/New Gen | IMTT - | IMTT Control Valves Inspection/Repair
0255-F6B-027B | F6B | 15510 |  |  |  | Fluid Flow/New Gen | IMTT | IMTT Control Valves Inspection/Repair
0255-F6B-027C | F6B | 15510 |  |  |  | Fluid Flow/New Gen | IMTT | IMTT Control Valves Inspection/Repair
0255-F6B-027D | F6B | 15510 |  |  |  | Fluid Flow/New Gen | IMTT | 3 Steam Valves from Site |  |  |  |  | Fermni Site | Dooling
0255-SITE-028A | F6B | 15575 |  |  | Delivered | WT Supply | Site - Consumables, Tooling, Supplies | Construction Supplies
0255-SITE-028B | F6B | 15575 |  |  | Delivered | WT Supply | Site - Consumables, Tooling, Supplies | Construction Supplies
0255-SITE-028C | F6B | 15575 |  |  | Delivered | WT Supply | Site - Consumables, Tooling, Supplies | Construction Supplies
0255-SITE-028D | F6B | 15575 |  |  | Not RTS | WT Supply | Site - Consumables, Tooling, Supplies | Construction Supplies
0255-F6B-029 | F6B | 15582 |  |  | Not RTS | Lynn Energy | Major Equipment - PLC Cabinets | BOP PLC Cabinets
0255-F6B-039A | F6B | 15783 |  | 2026-01-06 |  | Crawford | Bulks - Electrical - Conduit | Conduit
0255-F6B-039B | F6B | 15783 |  |  |  | Crawford | Bulks - Electrical - Conduit | Conduit
0255-CC-030 | F6B | 15639 |  |  | Not RTS | Sulzer Pump Services | IMTT | BFW Pumps Refurb
0255-F6B-031 | F6B | 15670 |  |  | Not RTS | The Reynolds Company | Major Equipment - Controls | PlantPAx control system server and server software
0255-F6B-032 | F6B | 15677 |  |  | Not RTS | Fluid Flow/New Gen | IMTT | Hot Well Pumps Refurb
0255-F6B-033 | F6B | 15702 |  |  | Not RTS | Sulzer Electro Machinery Services | IMTT | Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower)
0255-F6B-034 | F6B | 15704 |  |  | Not RTS | Puffer | Tagged Equipment - Valves (Auto) | Control Valves
0255-F6B-035 | F6B | 15705 |  |  | Not RTS | Emerson | Tagged Equipment - Instrumentation | Instrumentation (replacing 15605)
0255-F6B-036A | F6B | 15706 |  | 2026-01-06 | Not RTS | CED | Bulks - Electrical - Grounding | Plant Grounding
0255-F6B-036B | F6B | 15706 |  |  | Not RTS | CED | Bulks - Electrical - Grounding | Plant Grounding
0255-F6B-037A | F6B | 15782 |  | 2026-01-06 | Not RTS | CED | Bulks - Electrical - Cable Tray | Cable Tray
0255-F6B-037B | F6B | 15782 |  |  | Not RTS | CED | Bulks - Electrical - Cable Tray | Cable Tray
0255-F6B-038 | F6B | 15737 |  |  |  | Wiltew | Major Equipment - Glycol Tank | Glycol Expansion Tank
0255-F6B-039A | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039B | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039C | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039D | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039E | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039F | Site | 15464 |  |  | Delivered | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-039G | Site | 15464 | 1/7/2026; 1/8/2026 |  |  | West Gulf Containers | Site - Containers | 2 x 40' containers
0255-F6B-039H | Site | 15464 |  |  |  | West Gulf Containers | Site - Containers | 40' Containers
0255-F6B-040A | Site | 15208 |  |  | Delivered | Uline | Site - Office | Office Supplies/Furniture
0255-F6B-040B | Site | 15208 |  |  | Delivered | Uline | Site - Office | Office Supplies/Furniture
0255-F6B-040C | Site | 15208 |  |  | Delivered | Uline | Site - Office | Office Supplies/Furniture
0255-F6B-040D | Site | 15208 |  |  |  | Uline | Site - Office | Office Supplies/Furniture
0255-F6B-032A | F6B | 15815 | 2025-12-28 | 2026-01-06 |  | Zephyr | Bulks - Electrical - Vaults/Trenches | Duct Bank Vaults | 3
0255-F6B-032B | F6B | 15815 | 2025-12-28 | 2026-01-07 |  | Zephyr | Bulks - Electrical - Vaults/Trenches | Duct Bank Vaults | 4
0255-F6B-032D | F6B | 15815 |  |  |  | Zephyr | Bulks - Electrical - Vaults/Trenches | Trenches
0255-F6B-041 | Site | 15311 |  |  |  | Fastenal | Site - Consumables, Tooling, Supplies | Misc. Hardware
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-042 | Site | 15408 |  |  | Delivered | Home Depot | Site - Office | Appliances for trailers
0255-F6B-043 | Site | 15492 |  |  |  | Aqua One | Site - Office | Coffee Supplies
0255-F6B-044 | Site | 15608 |  |  | Delivered | Kohler | Site - Consumables, Tooling, Supplies | Hot Pressure Washer
0255-F6B-045 | Site | 15746 |  |  |  | Yard Mule Specialists | Site - Equipment | Yard Mule Rental
0255-TM-046 | TM2500 | 15810 |  |  |  | Lynn Energy | Major Equipment - PLC Cabinets | TURB PLC 100, RIO 100, RIO 101
0255-F6B-047 | F6B | 15813 |  |  |  | Fluid Flow | Tagged Equipment - Strainers | Strainers
0255-TM-048 | TM2500 | 15814 |  |  |  | Fluid Flow | Tagged Equipment - Strainers | Strainers
0255-TM-050A | TM2500 | 15818 | 2026-01-07 |  |  | Katy Steel | Bulks - Civil - Rebar | TM2500 Foundations | 1 | [12 empty] | 18 loads starting on the 6th,
0255-TM-050B | TM2500 | 15814 | 2026-01-08 | [5 empty] | 1
0255-TM-050C | TM2500 | 15818 | 2026-01-09 | [5 empty] | 1
0255-TM-050D | TM2500 | 15814 | 2026-01-10 | [5 empty] | 2
0255-TM-050E | TM2500 | 15818 | 2026-01-12 | [5 empty] | 1
0255-TM-050F | TM2500 | 15814 | 2026-01-13 | [5 empty] | 1
0255-TM-050G | TM2500 | 15818 | 2026-01-14 | [5 empty] | 1
0255-TM-050H | TM2500 | 15814 | 2026-01-15 | [5 empty] | 1
0255-TM-050I | TM2500 | 15818 | 2026-01-16 | [5 empty] | 1
0255-F6B-051 | F6B | 15818 |  |  |  | Madden Bolt | Bulks - Civil - Anchor Bolts/Embeds | Misc Foundations
0255-F6B-052 | F6B | 15843 |  |  |  | Fluid Flow | Tagged Equipment - Manual Valves
0255-RPS-054 | Facilities | RPS Asset |  | 2026-01-06 |  | RPS | Site - Containers | Office Trailer

## PO Parts Log
Purchase Order ID | PO Description | Created On | Status | Scope | Item UUID | PO LI | Shipment | Category | Sub Category | Item Status | Item Last Change Date Time | Supplier | Project Task | Item Description | Item Remark for Supplier | Supplier Part Number | Product | Product | Manufacturer | Manufacturer Part Number | Base UoM | Item Type | Delivery Date From | Delivery Status | Incoterms | Purchase Order Item | Base Net Price Base Quantity Unit | Ordered Quantity | Net Price | Net Value
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 1 | 14464 - 1 | - | Labor | Labor - Mechanical | Canceled | 10/11/2025 06:56:44 CST | HPI, LLC | CPSO-0255-1 | Construction Manager | Technical Advisor - Straight Time | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 1 | EA | 120 | 112.86 | 13543.2
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 2 | 14464 - 2 | - | Labor | Labor - Mechanical | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Senior Engineer 2 | Generator Specialist - Straight Time | # | ENG0015 | Senior Engineer 2 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 2 | EA | 64 | 344 | 22016
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 3 | 14464 - 3 | - | Labor | Labor - Mechanical | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Engineer 1 | Generator Technician - Straight Time | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 3 | XPK | 64 | 251 | 16064
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 4 | 14464 - 4 | - | Per Diem | Expenses | Canceled | 10/11/2025 06:56:44 CST | HPI, LLC | CPSO-0255-1 | Contractor Per Diem Service | HPI Field Personnel | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 08/19/2025 | Not Relevant | N/A | 4 | EA | 16 | 200 | 3200
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 5 | 14464 - 5 | - | Per Diem | Expenses | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Contractor Per Diem Service | MD&A Per Diem | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 08/19/2025 | Not Relevant | N/A | 5 | EA | 22 | 546.25 | 12017.5
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 6 | 14464 - 6 | - | T&E | Expenses | Follow-Up Document Created | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 6 | EA | 0 | 0 | 40473
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 7 | 14464 - 7 | - | Labor | Labor - Mechanical | Canceled | 10/11/2025 06:56:44 CST | HPI, LLC | CPSO-0255-1 | Construction Manager | Technical Advisory - Overtime | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 7 | EA | 72 | 169.29 | 12188.88
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 8 | 14464 - 8 | - | Labor | Labor - Mechanical | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Senior Engineer 2 | Generator Specialist - Overtime | # | ENG0015 | Senior Engineer 2 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 8 | EA | 26 | 516 | 13416
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 9 | 14464 - 9 | - | Labor | Labor - Mechanical | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Engineer 1 | Generator Technician - Overtime | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 9 | EA | 26 | 376.5 | 9789
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 10 | 14464 - 10 | - | T&E | Expenses | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Field Service T&E Expenses | Generator Specialist Mobe/Demobe | # | EXP0001 | Field Service T&E Expenses | # | # | Each | Expense | 08/19/2025 | Not Relevant | N/A | 10 | EA | 2 | 9280.5 | 18561
14464 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical) | 11 | 14464 - 11 | - | T&E | Expenses | Finished | 11/06/2025 12:14:28 CST | HPI, LLC | CPSO-0255-1 | Field Service T&E Expenses | Generator Technician Mobe/Demobe | # | EXP0001 | Field Service T&E Expenses | # | # | Each | Expense | 08/19/2025 | Not Relevant | N/A | 11 | EA | 2 | 7544 | 15088
14469 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly)) | 08/19/2025 | Finished | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly) | 1 | 14469 - 1 | - | Labor | Labor - Mechanical | Finished | 10/13/2025 09:30:25 CST | E&H Excavations LLC | CPSO-0255-1 | Senior Project Manager 1 | Project Manager (ST) | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 1 | EA | 40 | 136.08 | 5443.2
14469 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly)) | 08/19/2025 | Finished | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly) | 2 | 14469 - 2 | - | Labor | Labor - Mechanical | Finished | 10/13/2025 09:30:25 CST | E&H Excavations LLC | CPSO-0255-1 | Construction Manager | Site Superintendent (ST) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 2 | EA | 40 | 108.87 | 4354.8
14469 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly)) | 08/19/2025 | Finished | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly) | 3 | 14469 - 3 | - | T&E | Expenses | Finished | 10/13/2025 09:30:25 CST | E&H Excavations LLC | CPSO-0255-1 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 7335.3
14469 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly)) | 08/19/2025 | Finished | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Mechanical - Preparation for Disassembly) | 4 | 14469 - 4 | - | Labor | Labor - Mechanical | Finished | 10/13/2025 09:30:25 CST | E&H Excavations LLC | CPSO-0255-1 | Construction Manager | Site Superintendent (OT) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 4 | EA | 20 | 147.62 | 2952.4
14471 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 1 | 14471 - 1 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 11/07/2025 14:30:22 CST | MEITEC, Inc. | CPSO-0255-1 | Foreman | Electrical Lead (ST) | # | FLD0009 | Foreman | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 1 | EA | 460 | 86 | 39560
14471 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 2 | 14471 - 2 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 11/06/2025 10:25:24 CST | MEITEC, Inc. | CPSO-0255-1 | Field Service - Electrical | Electrical Technician (ST) | # | FLD0006 | Field Service - Electrical | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 2 | EA | 440 | 82 | 36080
14471 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 3 | 14471 - 3 | - | T&E | Expenses | Finished | 11/06/2025 10:25:24 CST | MEITEC, Inc. | CPSO-0255-1 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 3569.8
14471 | Fermi Matador PP - TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 08/19/2025 | Follow-Up Document Created | TO #1 Equipment Assessments & Data Gathering / Preliminary Engineering (Electrical - Preparation for Disassembly) | 4 | 14471 - 4 | - | T&E | Expenses | Follow-Up Document Created | 11/18/2025 16:15:47 CST | MEITEC, Inc. | CPSO-0255-1 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 4 | EA | 0 | 0 | 20000
14473 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment | 1 | 14473 - 1 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 12/23/2025 14:23:27 CST | E&H Excavations LLC | CPSO-0255-2 | Senior Project Manager 1 | Project Manager (ST) | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 1 | EA | 300 | 136.08 | 40824
14473 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment | 2 | 14473 - 2 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 12/23/2025 14:23:27 CST | E&H Excavations LLC | CPSO-0255-2 | Construction Manager | Site Superintendent (ST) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 2 | EA | 950 | 108.87 | 103426.5
14473 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment | 3 | 14473 - 3 | - | T&E | Expenses | Follow-Up Document Created | 12/31/2025 07:55:01 CST | E&H Excavations LLC | CPSO-0255-2 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 40000
14473 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment | 4 | 14473 - 4 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 12/31/2025 07:55:01 CST | E&H Excavations LLC | CPSO-0255-2 | Construction Manager | Site Superintendent (OT) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 4 | EA | 750 | 147.62 | 110715
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 1 | 14474 - 1 | - | Labor | Labor - Mechanical | Finished | 11/25/2025 13:28:20 CST | HPI, LLC | CPSO-0255-2 | Construction Manager | Technical Advisor (ST) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 1 | EA | 349 | 112.86 | 39388.14
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 2 | 14474 - 2 | - | Labor | Expenses | Finished | 11/25/2025 13:28:20 CST | HPI, LLC | CPSO-0255-2 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 08/19/2025 | Not Relevant | N/A | 2 | EA | 69 | 200 | 13800
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 3 | 14474 - 3 | - | T&E | Expenses | Follow-Up Document Created | 12/16/2025 14:43:46 CST | HPI, LLC | CPSO-0255-2 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 08/19/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 57684
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 4 | 14474 - 4 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 12/16/2025 14:43:46 CST | HPI, LLC | CPSO-0255-2 | Construction Manager | Technical Advisor (OT) | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 4 | EA | 380 | 169.29 | 64330.2
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 5 | 14474 - 5 | - | Labor | Labor - Mechanical | Follow-Up Document Created | 12/16/2025 14:43:46 CST | HPI, LLC | CPSO-0255-2 | Construction Manager | # | # | FLD0008 | Construction Manager | # | # | Hour(s) | Service | 08/19/2025 | Not Relevant | N/A | 5 | EA | 400 | 112.86 | 45144
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 6 | 14474 - 6 | - | Labor | Expenses | Follow-Up Document Created | 12/16/2025 14:43:46 CST | HPI, LLC | CPSO-0255-2 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 08/19/2025 | Not Relevant | N/A | 6 | EA | 70 | 200 | 14000
14474 | Fermi Matador PP - TO #2 - Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 08/19/2025 | Follow-Up Document Created | Supervision of the Disassembly of Equipment, Turbine Rotor Stands and Transport | 7 | 14474 - 7 | - | Material | Material | Follow-Up Document Created | 12/03/2025 08:42:22 CST | HPI, LLC | CPSO-0255-2 | Turbine Rotor Stands and Transport | Phase 1: Rotor stands accompanied with KIS transport tech to be taken to Bayonne,NJ and coordinate all aspects of transporting 1-(61 MW) Steam Turbine rotor in which weighs approx 35,000 lbs and has a diameter of approx 100 inches . KIS will perform the chaining of transport pedestals/stands to the trailer as well as properly securing the rotor down into the transport pedestals, preferably resting the rotor on its glands if possible as opposed to the journals. KIS will provide and perform the covering(tarp) for this turbine unit whether it be conestoga slide curtain or the conventional “total tarp wrap” done by hand. Phase 2: Pick up of GE (61MW) Steam Turbine at Ethos in Houston TX. Rotor transport stands can be used at delivery point in Panhandle TX for up to one week from delivery in Panhandle TX. Shipping of the stands, once rotor is removed is included in the pricing. | # | # | Not assigned | # | # | Not assigned | Material | 08/19/2025 | Not Delivered | N/A | 7 | EA | 1 | 33125 | 33125
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 1 | 14586 - 1 | - | Labor | Labor - Executive | Follow-Up Document Created | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | Project Manager 1 | Executive (ST) Preparation Planning for Disassembly (200 hrs) Prepare RFP for new HRSG (50 hrs) | # | PROJ0003 | Project Manager 1 | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 1 | EA | 250 | 210 | 52500
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 2 | 14586 - 2 | - | Labor | Labor - Executive | Follow-Up Document Created | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | Engineering-Project Manager | Project Engineer (ST) Preparation Planning for Disassembly (200 hrs) Prepare RFP for new HRSG (20 hrs) | # | ENG0004 | Engineering-Project Manager | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 2 | EA | 220 | 165 | 36300
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 3 | 14586 - 3 | - | Labor | Labor - Executive | Finished | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | Engineer 1 | Electrical Engineer (ST) Preparation Planning for Disassembly (8 hrs) | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 3 | XPK | 13 | 137 | 1781
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 4 | 14586 - 4 | - | Labor | Labor - Executive | Finished | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | CAD Designer 1 | Sr. Electrical Designer (ST) Preparation Planning for Disassembly (50 hrs) | # | CAD0001 | CAD Designer 1 | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 4 | EA | 50 | 116 | 5800
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 5 | 14586 - 5 | - | Labor | Labor - Executive | Finished | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | CAD Technician 1 | Equipment 3D scan | # | CAD0004 | CAD Technician 1 | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 5 | EA | 165 | 112 | 18480
14586 | Fermi Matador PP - TO #1 Preparation/Planning for Disassembly, 3D Scan, RFP for new HRSG | 08/29/2025 | Follow-Up Document Created | # | 6 | 14586 - 6 | - | T&E | Expenses | Follow-Up Document Created | 10/13/2025 12:39:50 CST | Bankhead Energy Solutions | CPSO-0255-1 | Travel Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 09/04/2025 | Not Relevant | N/A | 6 | EA | 0 | 0 | 12151.6
14587 | Fermi PP - TO# 2 - Supervision of the Disassembly of Equipment | 08/29/2025 | Follow-Up Document Created | # | 1 | 14587 - 1 | - | Labor | Labor - Executive | Follow-Up Document Created | 10/13/2025 12:47:10 CST | Bankhead Energy Solutions | CPSO-0255-2 | Executive | # | # | EXEC0001 | Executive | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 1 | EA | 432 | 210 | 90720
14587 | Fermi PP - TO# 2 - Supervision of the Disassembly of Equipment | 08/29/2025 | Follow-Up Document Created | # | 2 | 14587 - 2 | - | Labor | Labor - Executive | Follow-Up Document Created | 10/13/2025 12:47:10 CST | Bankhead Energy Solutions | CPSO-0255-2 | Senior Project Manager 1 | # | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 09/04/2025 | Not Relevant | N/A | 2 | EA | 432 | 164.64 | 71124.48
14587 | Fermi PP - TO# 2 - Supervision of the Disassembly of Equipment | 08/29/2025 | Follow-Up Document Created | # | 3 | 14587 - 3 | - | T&E | Expenses | Follow-Up Document Created | 08/29/2025 15:32:44 CST | Bankhead Energy Solutions | CPSO-0255-2 | Travel Expenses | # | # | # | Not assigned | # | # | Not assigned | Service | 09/05/2025 | Not Relevant | N/A | 3 | XPK | 1 | 10238 | 10238
14685 | Fermi PP - TO# 3 - Equipment Transportation from IMTT site to Amarillo via trucking and barge (Shipment S2500004308) | 09/09/2025 | Follow-Up Document Created | Equipment Transportation from IMTT site to Amarillo via trucking and barge | 1 | 14685 - 1 | - | Major Equipment | Logistics | Follow-Up Document Created | 12/16/2025 17:58:57 CST | UTC OVERSEAS, INC. | CPSO-0255-3 | Logistics | 1. Purchase of Containers for general cargo 2. 20 Truck Shipments from Bayonne Site to Requested Delivery Addresses 3. IMTT Site movement, loadout, securing and delivery to dock of 3 Turbine and 3 generator skids 4. Dockage, loadout to barge, securing on deck barge 5. Engineering Work for all scopes lifted above - This PO is an initial release of the logistics for the Fermi project. This covers engineering service, loading truck (Bayonne), delivery trucking (Amarillo), and Barge transport. Included in this amount is the first barge, trucking for all major skids for the first two GT's, initial barge transport, cargo loading, securing, engineering, and containers for spare/shiploose parts. - Once all weights and dimensions are confirmed by the customer, UTC will provide a firm estimate of cargo engineered plans, surveys, loading, securing, discharge, cargo insurance, and similar charges associated with this phase of the logistics plan. Until such time, all costs should be considered to be billed at cost plus | # | 20000006 | Logistics | # | # | Each | Service | 09/16/2025 | Not Relevant | Delivered at place | 1 | EA | 1 | 1265500.48 | 1265500.48
14685 | Fermi PP - TO# 3 - Equipment Transportation from IMTT site to Amarillo via trucking and barge (Shipment S2500004308) | 09/09/2025 | Follow-Up Document Created | Equipment Transportation from IMTT site to Amarillo via trucking and barge | 2 | 14685 - 2 | - | Major Equipment | Logistics | Finished | 12/28/2025 16:03:06 CST | UTC OVERSEAS, INC. | CPSO-0255-3 | Logistics | 2nd half of the GT Generator & Turbine deliveries to Houston which includes the barge transportation costs, the Houston terminal handling charges, and the trucking form the port to the elected rehab sites. | # | 20000006 | Logistics | # | # | Each | Service | 09/16/2025 | Not Relevant | Delivered at place | 2 | EA | 1 | 1489968.06 | 1489968.06
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 1 | 14723 - 1 | 0255-F6B-001 | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | Simple Cycle System - DRIVE Design | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 1 | EA | 3 | 4358100 | 13074300
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 2 | 14723 - 2 | 0255-F6B-001A | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | Anchor Bolt Template | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 2 | EA | 3 | 7400 | 22200
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 3 | 14723 - 3 | 0255-F6B-001B | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | Spare Parts | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 3 | XPK | 3 | 14100 | 42300
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 4 | 14723 - 4 | - | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | Change to 2x 100% TA Fans | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 4 | EA | 3 | 639700 | 1919100
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 5 | 14723 - 5 | 0255-F6B-001C | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | Ammonia Storage/Transfer System | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 5 | EA | 1 | 403400 | 403400
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 6 | 14723 - 6 | 0255-F6B-001D | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | CEMS System | # | # | # | Not assigned | # | # | Not assigned | Material | 09/19/2025 | Not Delivered | Ex works | 6 | EA | 3 | 534300 | 1602900
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 7 | 14723 - 7 | - | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | CEMS System - Field Services | # | # | # | Not assigned | # | # | Not assigned | Service | 09/19/2025 | Not Relevant | Ex works | 7 | EA | 3 | 36000 | 108000
14723 | Fermi Matador PP - TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 09/12/2025 | Not Yet Acknowledged | TO #4 - Three (3) Frame 6 SCR/CO Emission Control Systems | 8 | 14723 - 8 | - | Major Equipment | Major Equipment | Not Yet Acknowledged | 09/12/2025 15:55:54 CST | Braden Americas, Inc. | CPSO-0255-PO2 | System Only Site Training | # | # | # | Not assigned | # | # | Not assigned | Service | 09/19/2025 | Not Relevant | Ex works | 8 | EA | 1 | 25000 | 25000
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 1 | 14738 - 1 | - | Labor | Labor - Engineering | Finished | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Executive | Project Manager (ST) | # | EXEC0001 | Executive | # | # | Hour(s) | Service | 07/13/2025 | Not Relevant | N/A | 1 | EA | 2200 | 210 | 462000
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 2 | 14738 - 2 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Project Manager 1 | Project Engineer (ST) | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 2 | EA | 1760 | 190 | 334400
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 3 | 14738 - 3 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Project Administrator 1 | Admin (ST) | # | PROJ0010 | Senior Project Administrator 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 3 | XPK | 750 | 84.96 | 63720
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 4 | 14738 - 4 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 2 | Proc Engr (ST) | # | ENG0009 | Engineer 2 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 4 | EA | 563 | 186.91 | 105230.33
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 5 | 14738 - 5 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 1 | Mech Engr (ST) | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 5 | EA | 2000 | 175.23 | 350460
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 6 | 14738 - 6 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 2 | C/S Engr (ST) | # | ENG0009 | Engineer 2 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 6 | EA | 1850 | 184.97 | 342194.5
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 7 | 14738 - 7 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 1 | Elec Engr (ST) | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 7 | EA | 1750 | 165.5 | 289625
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 8 | 14738 - 8 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 1 | Instr Engr (ST) | # | ENG0008 | Engineer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 8 | EA | 1163 | 165.5 | 192476.5
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 9 | 14738 - 9 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 | Mech Design (ST) | # | CAD0001 | CAD Designer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 9 | EA | 2900 | 155.76 | 451704
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 10 | 14738 - 10 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 | C/S Design (ST) | # | CAD0001 | CAD Designer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 10 | EA | 1900 | 151.87 | 288553
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 11 | 14738 - 11 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior CAD Technician 1 | I&E Design (ST) | # | CAD0009 | Senior CAD Technician 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 11 | EA | 1200 | 136.29 | 163548
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 12 | 14738 - 12 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Project Controls | Proj. Controls (ST) | # | PROJ0002 | Project Controls | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 12 | EA | 930 | 116.82 | 108642.6
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 13 | 14738 - 13 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Project Administrator 1 | Doc Control | # | PROJ0010 | Senior Project Administrator 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 13 | EA | 813 | 93.46 | 75982.98
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 14 | 14738 - 14 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 | Mech Design (OT) | # | CAD0001 | CAD Designer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 14 | EA | 625 | 233.64 | 146025
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 15 | 14738 - 15 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 | C/S Design (OT) | # | CAD0001 | CAD Designer 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 15 | EA | 475 | 227.8 | 108205
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 16 | 14738 - 16 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior CAD Technician 1 | I&E Design (OT) | # | CAD0009 | Senior CAD Technician 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 16 | EA | 300 | 204.44 | 61332
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 17 | 14738 - 17 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Project Controls | Proj. Controls (OT) | # | PROJ0002 | Project Controls | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 17 | EA | 233 | 175.23 | 40828.59
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 18 | 14738 - 18 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Project Administrator 1 | Doc. Control (OT) | # | PROJ0010 | Senior Project Administrator 1 | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 18 | EA | 163 | 140.18 | 22849.34
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 19 | 14738 - 19 | - | Labor | Labor - Engineering | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | ENGR SOFTWARE | Aconex / P6 / CAD / 3D / MISC / Software | # | ENG0018 | ENGR SOFTWARE | # | # | Each | Service | 09/16/2025 | Not Relevant | N/A | 19 | EA | 5 | 26250 | 131250
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 20 | 14738 - 20 | - | T&E | Expenses | Follow-Up Document Created | 12/29/2025 10:08:56 CST | Bankhead Energy Solutions | CPSO-0255-3 | Expenses | Airfare, Hotel, Meals, Rental Car, Aconex / P6 / CAD / 3D / Misc Software | # | # | Not assigned | # | # | Not assigned | Service | 09/16/2025 | Not Relevant | N/A | 20 | EA | 1 | 120750 | 120750
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 21 | 14738 - 21 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineering Software | # | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Relevant | N/A | 21 | EA | 1 | 26250 | 26250
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 22 | 14738 - 22 | #N/A | #N/A | #N/A | Follow-Up Document Created | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Executive (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 22 | EA | 759 | 229.17 | 173940.03
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 23 | 14738 - 23 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Sr. Project Management (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 23 | EA | 403 | 186.83 | 75292.49
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 24 | 14738 - 24 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Project Management (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 24 | EA | 70 | 170.12 | 11908.4
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 25 | 14738 - 25 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Principal Engineer 2 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 25 | EA | 13 | 280.25 | 3643.25
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 26 | 14738 - 26 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Principal Engineer 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 26 | EA | 168 | 266.98 | 44852.64
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 27 | 14738 - 27 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Engineer 2 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 27 | EA | 309.5 | 227.64 | 70454.58
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 28 | 14738 - 28 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior Engineer 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 28 | EA | 1187.5 | 199.62 | 237048.75
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 29 | 14738 - 29 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Engineer 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 29 | EA | 639.75 | 172.08 | 110088.18
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 30 | 14738 - 30 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Principal CAD Designer (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 30 | EA | 338 | 227.64 | 76942.32
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 31 | 14738 - 31 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior CAD Designer 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 31 | EA | 2968 | 185.36 | 550148.48
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 32 | 14738 - 32 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior CAD Designer 1 (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 32 | EA | 426.5 | 278.04 | 118584.06
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 33 | 14738 - 33 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 33 | EA | 864.5 | 157.83 | 136444.04
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 34 | 14738 - 34 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Designer 1 (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 34 | EA | 79.83 | 236.74 | 18898.95
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 35 | 14738 - 35 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Senior CAD Technician 1 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 35 | EA | 17 | 130.78 | 2223.26
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 36 | 14738 - 36 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Technician 2 (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 36 | EA | 432.5 | 117.02 | 50611.15
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 37 | 14738 - 37 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | CAD Technician 2 (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 37 | EA | 40.5 | 175.53 | 7108.97
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 38 | 14738 - 38 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Sr. Planner (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 38 | EA | 945 | 130.78 | 123587.1
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 39 | 14738 - 39 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Sr. Planner (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 39 | EA | 307 | 196.18 | 60227.26
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 40 | 14738 - 40 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Project Administrator (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 40 | EA | 431 | 93.42 | 40264.02
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 41 | 14738 - 41 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Project Administrator (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 41 | EA | 22 | 140.13 | 3082.86
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 42 | 14738 - 42 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Per Diem | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 42 | EA | 1 | 32016.6 | 32016.6
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 43 | 14738 - 43 | #N/A | #N/A | #N/A | Follow-Up Document Created | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Expenses | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 43 | EA | 1 | 65237.89 | 65237.89
14738 | Fermi Matador PP - TO#3 - Engineering Services | 09/14/2025 | Follow-Up Document Created | Fermi Matador PP - TO#3: Engineering Services | 44 | 14738 - 44 | #N/A | #N/A | #N/A | Finished | 12/31/2025 16:53:40 CST | Bankhead Energy Solutions | CPSO-0255-3 | Mileage | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | N/A | 44 | EA | 1 | 1031.94 | 1031.94
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 1 | 14795 - 1 | 0255-F6B-002A | Major Equipment | Major Equipment | Finished | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | 3000A MLO Nema 3r Switchboard | AT-1, AT-2 Per Proposal # 2527 Rev3 - One to be modified to include a 1000A breaker | # | # | Not assigned | # | # | Not assigned | Material | 10/09/2025 | Not Relevant | Delivered at place | 1 | EA | 2 | 96107 | 192214
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 2 | 14795 - 2 | - | Major Equipment | Major Equipment | Canceled | 09/26/2025 03:56:16 CST | Equisales Associates | CPSO-0255-3 | 34.5kV 4000A 100kA GOAB with Stands | Per Proposal # 2527 Rev3 | # | # | Not assigned | # | # | Not assigned | Material | 10/09/2025 | Not Relevant | Delivered at place | 2 | EA | 2 | 51750 | 103500
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 3 | 14795 - 3 | 0255-F6B-002B | Major Equipment | Major Equipment | Finished | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | 13.8kv-480V, 3750 KVA, 3P Padmount Xfmr | Per Proposal # 2527 Rev3 | # | # | Not assigned | # | # | Not assigned | Material | 10/16/2025 | Not Relevant | Delivered at place | 3 | XPK | 1 | 184821 | 184821
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 4 | 14795 - 4 | 0255-F6B-002C | Major Equipment | Major Equipment | Finished | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | 7500/9375 kVA 3P Substation Xfmr | # | # | # | Not assigned | # | # | Not assigned | Material | 12/22/2025 | Not Relevant | Delivered at place | 4 | EA | 2 | 224520 | 449040
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 5 | 14795 - 5 | 0255-F6B-002D | Major Equipment | Major Equipment | Follow-Up Document Created | 12/02/2025 17:16:27 CST | Equisales Associates | CPSO-0255-3 | 3000 kVA 3P Substation Xfmr | AT-11, AT-21 | # | # | Not assigned | # | # | Not assigned | Material | 12/22/2025 | Not Relevant | Delivered at place | 5 | EA | 2 | 146231 | 292462
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 6 | 14795 - 6 | 0255-F6B-002E | Major Equipment | Major Equipment | Follow-Up Document Created | 12/02/2025 17:16:27 CST | Equisales Associates | CPSO-0255-3 | 1500 kVA 3P Substation Xfmr | AT-22 | # | # | Not assigned | # | # | Not assigned | Material | 12/22/2025 | Not Relevant | Delivered at place | 6 | EA | 1 | 68388 | 68388
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 7 | 14795 - 7 | 0255-F6B-002F | Major Equipment | Major Equipment | Finished | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | Nema 3R Switchboard, 2000A Main | # | # | # | Not assigned | # | # | Not assigned | Material | 11/30/2025 | Not Relevant | Delivered at place | 7 | EA | 2 | 88714 | 177428
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 8 | 14795 - 8 | 0255-F6B-002G | Major Equipment | Major Equipment | Finished | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | Nema 1 2000A -Transfer Switch (ASCO) | # | # | # | Not assigned | # | # | Not assigned | Material | 12/22/2025 | Not Relevant | Delivered at place | 8 | EA | 2 | 71509 | 143018
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 9 | 14795 - 9 | 0255-F6B-002G | Major Equipment | Major Equipment | Follow-Up Document Created | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | Replace transformers with FR3 Fluid | Modification of the Frame 6 Aux transformers to the FR3 Fluid. | # | # | Not assigned | # | # | Not assigned | Service | 12/22/2025 | Not Delivered | Delivered at place | 9 | EA | 1 | 67692 | 67692
14795 | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 09/19/2025 | Follow-Up Document Created | Fermi Matador PP - TO #3 - Transformer, Switchboard, Air Breaker, FR3 Fluid, Trench Box Switch | 10 | 14795 - 10 | 0255-F6B-002G | Major Equipment | Major Equipment | Follow-Up Document Created | 12/28/2025 16:26:41 CST | Equisales Associates | CPSO-0255-3 | Trench for Instr. Run on Frame 6B Design | Trench Required for Instrumentation Run on Frame 6B Design | # | # | Not assigned | # | # | Not assigned | Service | 01/28/2026 | Not Delivered | Delivered at place | 10 | EA | 1 | 77418 | 77418
14955 | Fermi Matador PP - TO #3: Supply Chain Services (Procurement & Logistics) | 10/07/2025 | Follow-Up Document Created | TO #3: Supply Chain Services (Procurement & Logistics) | 1 | 14955 - 1 | - | Labor | Labor - Admin | Follow-Up Document Created | 11/13/2025 11:07:01 CST | Sigma Oilfield USA Inc | CPSO-0255-3 | Procurement-Specialist | # | # | PROC0001 | Procurement-Specialist | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 1 | EA | 1625 | 75 | 121875
14955 | Fermi Matador PP - TO #3: Supply Chain Services (Procurement & Logistics) | 10/07/2025 | Follow-Up Document Created | TO #3: Supply Chain Services (Procurement & Logistics) | 2 | 14955 - 2 | - | Labor | Labor - Admin | Follow-Up Document Created | 11/13/2025 11:07:01 CST | Sigma Oilfield USA Inc | CPSO-0255-3 | Procurement-Specialist | # | # | PROC0001 | Procurement-Specialist | # | # | Hour(s) | Service | 09/16/2025 | Not Relevant | N/A | 2 | EA | 400 | 112.5 | 45000
14955 | Fermi Matador PP - TO #3: Supply Chain Services (Procurement & Logistics) | 10/07/2025 | Follow-Up Document Created | TO #3: Supply Chain Services (Procurement & Logistics) | 3 | 14955 - 3 | - | Per Diem | Expenses | Follow-Up Document Created | 11/13/2025 11:07:01 CST | Sigma Oilfield USA Inc | CPSO-0255-3 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 09/16/2025 | Not Relevant | N/A | 3 | XPK | 210 | 178 | 37380
14955 | Fermi Matador PP - TO #3: Supply Chain Services (Procurement & Logistics) | 10/07/2025 | Follow-Up Document Created | TO #3: Supply Chain Services (Procurement & Logistics) | 4 | 14955 - 4 | - | T&E | Expenses | Follow-Up Document Created | 11/13/2025 11:07:01 CST | Sigma Oilfield USA Inc | CPSO-0255-3 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 09/16/2025 | Not Relevant | N/A | 4 | EA | 0 | 0 | 20000
14955 | Fermi Matador PP - TO #3: Supply Chain Services (Procurement & Logistics) | 10/07/2025 | Follow-Up Document Created | TO #3: Supply Chain Services (Procurement & Logistics) | 5 | 14955 - 5 | - | T&E | Labor - Admin | Follow-Up Document Created | 11/13/2025 09:10:48 CST | Sigma Oilfield USA Inc | CPSO-0255-3 | Mileage | # | # | # | Not assigned | # | # | Not assigned | Limit | 09/16/2025 | Not Relevant | N/A | 5 | EA | 0 | 0 | 4000
14986 | Fermi Matador PP - TO #4 - Major Equipment: Wet Surface Air Cooler (WSAC) | 10/10/2025 | Follow-Up Document Created | Major Equipment: Wet Surface Air Cooler (WSAC) | 1 | 14986 - 1 | 0255-F6B-004 | Major Equipment | Major Equipment | Follow-Up Document Created | 12/03/2025 07:39:45 CST | Alfa laval Inc | CPSO-0255-4-1 | Wet Surface Air Cooler (WSAC) | Niagara Model #A4411XL Includes: - Cleanable Tube Bundles - Fan System & Fan Plenum - Catch Basin - Spray Water Distribution System | # | # | Not assigned | # | # | Not assigned | Material | 02/13/2026 | Not Relevant | Free carrier | 1 | EA | 1 | 2347221 | 2347221
14992 | Fermi Matador Power Group Project - TO #4 - GSU Relay Protection Panel | 10/10/2025 | Follow-Up Document Created | TO #4 - GSU Relay Protection Panel | 1 | 14992 - 1 | 0255-F6B-005 | Major Equipment | Major Equipment | Follow-Up Document Created | 12/02/2025 16:59:25 CST | Equisales Associates | CPSO-0255-4-1 | GSU Protection Panel (in 20' E-House) | Includes: Building/AC/DC system, HVAC, 3 Panels for protection + 6 remote CT to fiber conversion Boxes in NEMA 3R/ Stairs and Platforms for the building, Relay settings Excludes: Piers for the building/Foundation/ Fiber for CT conversion box interconnections/ Commissioning and Testing Conceptual drawings - 3-4 weeks ARO | # | # | Not assigned | # | # | Not assigned | Material | 02/27/2026 | Not Relevant | Free carrier | 1 | EA | 1 | 903827 | 903827
14993 | Fermi Frame 6B PGP - TO #4 - Logistics for (3) GSU's and accessories | 10/10/2025 | Follow-Up Document Created | TO #4 - Logistics for (3) GSU's and accessories | 1 | 14993 - 1 | - | Freight | Freight | Follow-Up Document Created | 12/28/2025 13:19:00 CST | UTC OVERSEAS, INC. | CPSO-0255-4-5 | Logistics for (3) GSU's & Accessories | - (3) GSU's + (6) 40' HC with Accessories - Izmir, Turkey - Norfolk, VA - 4-5 days to Amarillo site | # | # | Not assigned | # | # | Not assigned | Service | 10/17/2025 | Not Relevant | N/A | 1 | EA | 1 | 814358.89 | 814358.89
14993 | Fermi Frame 6B PGP - TO #4 - Logistics for (3) GSU's and accessories | 10/10/2025 | Follow-Up Document Created | TO #4 - Logistics for (3) GSU's and accessories | 2 | 14993 - 2 | - | Freight | Freight | Follow-Up Document Created | 12/28/2025 13:19:00 CST | UTC OVERSEAS, INC. | CPSO-0255-4-5 | Markup on bare cost - GSU freight (15%) | # | # | # | Not assigned | # | # | Not assigned | Service | 10/17/2025 | Not Relevant | N/A | 2 | EA | 1 | 122153.83 | 122153.83
14993 | Fermi Frame 6B PGP - TO #4 - Logistics for (3) GSU's and accessories | 10/10/2025 | Follow-Up Document Created | TO #4 - Logistics for (3) GSU's and accessories | 3 | 14993 - 3 | - | Freight | Freight | Finished | 12/22/2025 08:47:09 CST | UTC OVERSEAS, INC. | CPSO-0255-4-5 | Duties & Markup | # | # | # | Not assigned | # | # | Not assigned | Service | 10/17/2025 | Not Relevant | N/A | 3 | XPK | 1 | 936512.72 | 936512.72
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 1 | 15007 - 1 | - | 0 | Equipment Rental - Facilities | Follow-Up Document Created | 01/02/2026 21:08:04 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | 60x24 Modular (56x24) 4 Units-Rental | # | # | # | Not assigned | # | # | Not assigned | Service | 10/18/2025 | Not Relevant | Free carrier | 1 | EA | 16 | 3191 | 51056
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 2 | 15007 - 2 | - | 0 | Equipment Rental - Facilities | Follow-Up Document Created | 01/02/2026 21:08:04 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | 60x24 Modular (56x24) 4 Units-Inst | # | # | # | Not assigned | # | # | Not assigned | Service | 10/18/2025 | Not Relevant | Free carrier | 2 | EA | 4 | 21903 | 87612
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 3 | 15007 - 3 | - | 0 | Equipment Rental - Facilities | Follow-Up Document Created | 12/16/2025 17:51:56 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | 60x36 Modular (56x36) 2 Units-Rental | # | # | # | Not assigned | # | # | Not assigned | Service | 10/18/2025 | Not Relevant | Free carrier | 3 | XPK | 16 | 4724 | 75584
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 4 | 15007 - 4 | - | 0 | Equipment Rental - Facilities | Follow-Up Document Created | 01/02/2026 16:07:31 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | 60x36 Modular (56x36) 2 Units-Inst | # | # | # | Not assigned | # | # | Not assigned | Service | 10/18/2025 | Not Relevant | Free carrier | 4 | EA | 4 | 35459.5 | 141838
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 5 | 15007 - 5 | - | 0 | Equipment Rental - Facilities | Follow-Up Document Created | 01/02/2026 21:08:04 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | Misc Charges/Fees | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/21/2025 | Not Relevant | Free carrier | 5 | EA | 0 | 0 | 50000
15007 | Fermi Matador PGP - TO #4 - Office Trailers (Rental) | 10/14/2025 | Follow-Up Document Created | TO #4 - Office Trailers (Rental) | 6 | 15007 - 6 | - | 0 | 0 | Sent | 12/16/2025 17:51:56 CST | Williams Scotsman, Inc. | CPSO-0255-4-9 | Bathroom Trailer | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/21/2025 | Not Relevant | Free carrier | 6 | EA | 0 | 0 | 0.01
15057 | Fermi Frame 6B PGP - TO#4: LV MCC | 10/17/2025 | Finished | TO#4: LV MCC | 1 | 15057 - 1 | 0255-F6B-006 | Major Equipment | Major Equipment | Finished | 12/08/2025 09:34:29 CST | Equisales Associates | CPSO-0255-4-1 | Rockwell MCC (Top feed,1600A,8 sections) | # | # | # | Not assigned | # | # | Not assigned | Material | 12/19/2025 | Delivered | Free on board | 1 | EA | 1 | 235450 | 235450
15060 | Fermi Frame 6B PGP - TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 10/17/2025 | Follow-Up Document Created | TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 1 | 15060 - 1 | - | Major Equipment | Freight | Finished | 12/18/2025 20:33:09 CST | AG Power Systems Inc. | CPSO-0255-4-1 | Ocean Freight Export Packing | # | # | # | Not assigned | # | # | Not assigned | Service | 10/24/2025 | Not Relevant | Delivered duty paid | 1 | EA | 3 | 9100 | 27300
15060 | Fermi Frame 6B PGP - TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 10/17/2025 | Follow-Up Document Created | TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 2 | 15060 - 2 | - | Major Equipment | Major Equipment | Finished | 12/18/2025 20:33:09 CST | AG Power Systems Inc. | CPSO-0255-4-1 | Additional FAT | Measurement of SFRA according to IEC 60076-18 on Tap=5 that is 117kV tap position. Measurement of magnetizing current at HV side (Tap=5 / 117kV) | # | # | Not assigned | # | # | Not assigned | Service | 10/24/2025 | Not Relevant | Delivered duty paid | 2 | EA | 3 | 6760 | 20280
15060 | Fermi Frame 6B PGP - TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 10/17/2025 | Follow-Up Document Created | TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 3 | 15060 - 3 | - | Major Equipment | Major Equipment | Finished | 12/18/2025 20:33:09 CST | AG Power Systems Inc. | CPSO-0255-4-1 | Prep and handling after LT Storage | # | # | # | Not assigned | # | # | Not assigned | Service | 10/24/2025 | Not Relevant | Delivered duty paid | 3 | XPK | 3 | 2530 | 7590
15060 | Fermi Frame 6B PGP - TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 10/17/2025 | Follow-Up Document Created | TO#4: GSU's Oil, Export Packing, Additional FAT, Preparation and Handling after LT Storage | 4 | 15060 - 4 | 0255-F6B-007 | Major Equipment | Major Equipment | Not Yet Acknowledged | 10/17/2025 10:13:27 CST | AG Power Systems Inc. | CPSO-0255-4-1 | Shell Diala Oil | Total gallons to be delivered 17,850 (5,950 gallons per unit). Delivery to site in oil tankers included. | # | # | Not assigned | # | # | Not assigned | Material | 10/24/2025 | Not Delivered | Delivered duty paid | 4 | EA | 3570 | 5.75 | 20527.5
15070 | Fermi Frame 6B PGP - TO#4: Aggregates (Concrete Base, Crushed Rock) | 10/17/2025 | Follow-Up Document Created | TO#4: Aggregates (Concrete Base, Crushed Rock) | 1 | 15070 - 1 | - | Construction | Civil - Aggregates | Follow-Up Document Created | 12/12/2025 11:23:33 CST | Howell Sand Company, Inc. | CPSO-0255-4-9 | #57 Crushed Grey Rock ($77.30/Ton) | Initial Request 10/15/25: 12,150.00 Tons | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 1000000
15070 | Fermi Frame 6B PGP - TO#4: Aggregates (Concrete Base, Crushed Rock) | 10/17/2025 | Follow-Up Document Created | TO#4: Aggregates (Concrete Base, Crushed Rock) | 2 | 15070 - 2 | - | Construction | Civil - Aggregates | Follow-Up Document Created | 12/08/2025 10:32:14 CST | Howell Sand Company, Inc. | CPSO-0255-4-9 | Crushed Concrete Base ($50.00/Ton) | Initial Request 10/15/25: 64,184 Tons | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 740000
15070 | Fermi Frame 6B PGP - TO#4: Aggregates (Concrete Base, Crushed Rock) | 10/17/2025 | Follow-Up Document Created | TO#4: Aggregates (Concrete Base, Crushed Rock) | 3 | 15070 - 3 | - | Construction | Civil - Aggregates | Follow-Up Document Created | 12/17/2025 13:26:04 CST | Howell Sand Company, Inc. | CPSO-0255-4-9 | Crushed Concrete Base ($50.00/Ton) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 800000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 1 | 15077 - 1 | - | Equipment Rental | Equipment Rental - Crane | Follow-Up Document Created | 12/22/2025 11:18:51 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | 300T Crawler Manitowoc 2250 (4mos) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 450000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 2 | 15077 - 2 | - | Equipment Rental | Equipment Rental - Crane | Follow-Up Document Created | 12/22/2025 11:26:30 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | 100T - Tadano GR-1000XL (6mos) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 260000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 3 | 15077 - 3 | - | Equipment Rental | Equipment Rental - Crane | Not Yet Acknowledged | 10/22/2025 21:43:08 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | 50T - Tadano GR-500XL (6mos) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 136000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 4 | 15077 - 4 | - | Equipment Rental | Equipment Rental - Crane | Not Yet Acknowledged | 10/22/2025 21:43:08 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | 80T - Tadano GR-800XL (6mos) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 4 | EA | 0 | 0 | 190000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 5 | 15077 - 5 | - | Equipment Rental | Equipment Rental - Crane | Not Yet Acknowledged | 10/22/2025 21:43:08 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | (2) Carry Decks IC200 (15T) (6mos) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 5 | EA | 0 | 0 | 135000
15077 | Fermi Frame 6B PGP - TO#4: Crane Rental (M&O) | 10/17/2025 | Follow-Up Document Created | TO#4: Crane Rental & Maintenance | 6 | 15077 - 6 | - | Equipment Rental | Equipment Rental - Crane | Follow-Up Document Created | 12/22/2025 11:18:51 CST | Deep South Crane and Rigging LLC | CPSO-0255-4-9 | Misc Fees, Charges | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/24/2025 | Not Relevant | Free carrier | 6 | EA | 0 | 0 | 150000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 1 | 15118 - 1 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/16/2025 15:10:42 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Light Plants (30) 7 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 270000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 2 | 15118 - 2 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/30/2025 10:02:08 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Plate Compactor (4) 3 mos RTO | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 7500
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 3 | 15118 - 3 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/16/2025 15:41:17 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Gas Rammer (1) 4 mos RTO | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 3200
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 4 | 15118 - 4 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Mortar Mixer-10/12 CU/FT (1) 1 mo RTO | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 4 | EA | 0 | 0 | 1500
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 5 | 15118 - 5 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Concrete Vibrator 2HP (3) 3 mos RTO | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 5 | EA | 0 | 0 | 8000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 6 | 15118 - 6 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Concrete Mixer (2) 3 mos RTO | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 6 | EA | 0 | 0 | 6000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 7 | 15118 - 7 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/03/2026 08:16:12 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Full Maint/Service Tech On Site | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 7 | EA | 0 | 0 | 300000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 8 | 15118 - 8 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 1900lb Track Loader (1) 4mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 8 | EA | 0 | 0 | 16000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 9 | 15118 - 9 | - | Equipment Rental | Equipment Rental - Machinery | Finished | 12/23/2025 19:33:20 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 2500lb Track Loader (1) 4mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 9 | EA | 0 | 0 | 12000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 10 | 15118 - 10 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 3K W/B Padfoot Roller (3) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 10 | EA | 0 | 0 | 52000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 11 | 15118 - 11 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/30/2025 17:05:35 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 84" roller (2) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 11 | EA | 0 | 0 | 58000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 12 | 15118 - 12 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/03/2026 13:16:56 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Forklift 12k (55' reach) (3) 7 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 12 | EA | 0 | 0 | 110000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 13 | 15118 - 13 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/26/2025 12:25:37 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 3 Yard loader (2) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 13 | EA | 0 | 0 | 78000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 14 | 15118 - 14 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 20K Track Excavator (Cab & Air) (1) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 14 | EA | 0 | 0 | 33000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 15 | 15118 - 15 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 10K Track Excavator (1) 5mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 15 | EA | 0 | 0 | 26000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 16 | 15118 - 16 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/03/2026 07:50:52 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Mini Excavator (10-11K) (4) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 16 | EA | 0 | 0 | 128000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 17 | 15118 - 17 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/03/2026 13:24:29 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 2000 Gallon Water Truck (2) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 17 | EA | 0 | 0 | 60000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 18 | 15118 - 18 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/24/2025 15:34:16 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Skid Steer Pallet Forks (1) 6 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 18 | EA | 0 | 0 | 7200
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 19 | 15118 - 19 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Skid Steer (5) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 19 | EA | 0 | 0 | 80000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 20 | 15118 - 20 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/15/2025 08:22:41 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 150KW Prime Generator (1) 7mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 20 | EA | 0 | 0 | 135000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 21 | 15118 - 21 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/13/2025 21:18:50 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 350KW Prime Generator (1) 7mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 21 | EA | 0 | 0 | 190000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 22 | 15118 - 22 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Manlift - 85' Straight Boom (3) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 22 | EA | 0 | 0 | 96000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 23 | 15118 - 23 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Manlift - 85' Articulating Boom (4) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 23 | EA | 0 | 0 | 130000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 24 | 15118 - 24 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Manlift - 60' Articulating Boom (4) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 24 | EA | 0 | 0 | 100000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 25 | 15118 - 25 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/02/2026 08:01:51 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Manlift - 45' Articulating Boom (6) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 25 | EA | 0 | 0 | 140000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 26 | 15118 - 26 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/30/2025 10:03:32 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 4x4 Utility Carts (4) 6 mos (RTO) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 26 | EA | 0 | 0 | 120000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 27 | 15118 - 27 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | High Lifter Lift Truck (2) 7mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 27 | EA | 0 | 0 | 70000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 28 | 15118 - 28 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 185CFM Air Compressor (2) 2mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 28 | EA | 0 | 0 | 5000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 29 | 15118 - 29 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Pallet Jack (2) 6mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 29 | EA | 0 | 0 | 1200
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 30 | 15118 - 30 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 535 Pipe Threader 1/2-2" | w/ 3/4 x 50' red air hose) | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 30 | EA | 0 | 0 | 5500
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 31 | 15118 - 31 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 400A Welder (10) 6 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 31 | EA | 0 | 0 | 70000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 32 | 15118 - 32 | - | Equipment Rental | Equipment Rental - Machinery | Not Yet Acknowledged | 12/12/2025 14:58:45 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 300A Welder (10) 4 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 32 | EA | 0 | 0 | 46000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 33 | 15118 - 33 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 12/30/2025 10:13:17 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Sweeper (1) 6 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 33 | EA | 0 | 0 | 24000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 34 | 15118 - 34 | - | Equipment Rental | Equipment Rental - Machinery | Follow-Up Document Created | 01/03/2026 08:07:01 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Generator (lunch tent) 6 mos | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | Free carrier | 34 | EA | 0 | 0 | 50000
15118 | Fermi Frame 6B PGP - Equipment Rental & Maintenance | 10/22/2025 | Follow-Up Document Created | Equipment Rental & Maintenance | 35 | 15118 - 35 | - | Equipment Rental | Equipment Rental - Machinery | Finished | 12/13/2025 20:41:56 CST | Momentum Rental and Sales | CPSO-0255-4-9 | 40' Gooseneck Trailer (Purchase) | # | # | # | Not assigned | # | # | Not assigned | Material | 10/29/2025 | Not Relevant | Free carrier | 35 | EA | 1 | 17750 | 17750
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 1 | 15119 - 1 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Site Manager | ST (George Morongell) - Nov 2025 - May 2026 Billable Title: Construction Manager/Site Manager | # | FLD0003 | Site Manager | # | # | Hour(s) | Service | 10/29/2025 | Not Relevant | N/A | 1 | EA | 1120 | 155 | 173600
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 2 | 15119 - 2 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Site Manager | OT (George Morongell) - Nov 2025 - May 2026 Construction Manager/Site Manager | # | FLD0003 | Site Manager | # | # | Hour(s) | Service | 10/29/2025 | Not Relevant | N/A | 2 | EA | 1050 | 216 | 226800
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 3 | 15119 - 3 | - | Labor - Construction | Expenses | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 10/29/2025 | Not Relevant | N/A | 3 | XPK | 420 | 178 | 74760
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 4 | 15119 - 4 | - | Labor - Construction | Expenses | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Expenses - Mileage (All) | Mileage $0.70/mile | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | N/A | 4 | EA | 0 | 0 | 9000
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 5 | 15119 - 5 | - | Labor - Construction | Expenses | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Expenses - Fuel (All) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | N/A | 5 | EA | 0 | 0 | 10000
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 6 | 15119 - 6 | - | Labor - Construction | Expenses | Finished | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Reimbursable Expenses (All) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/29/2025 | Not Relevant | N/A | 6 | EA | 0 | 0 | 10000
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 7 | 15119 - 7 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Site Safety Representative ST | ST (Noe Vasquez) Billable Title: HSE Coordinator | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 7 | EA | 1340 | 64 | 85760
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 8 | 15119 - 8 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 21:31:52 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Site Safety Representative OT | OT - Noe Vasquez Billable Title: HSE Coordinator | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 8 | EA | 1250 | 87 | 108750
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 9 | 15119 - 9 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/04/2026 14:41:39 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Subcontracts Coordinator - ST | Nate Barnhart Billable Title: Subcontracts Coordinator | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 9 | EA | 1340 | 90 | 120600
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 10 | 15119 - 10 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/04/2026 14:41:39 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Subcontracts Coordinator - OT | Nate Barnhart Billable Title: Subcontracts Coordinator | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 10 | EA | 125 | 130 | 16250
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 11 | 15119 - 11 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 17:38:53 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | HSE Coordinator II - ST | Grant McAfee Billable Title: HSE Coordinator II | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 11 | EA | 1340 | 50 | 67000
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 12 | 15119 - 12 | #N/A | #N/A | #N/A | Follow-Up Document Created | 01/03/2026 17:38:53 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | HSE Coordinator II - OT | Grant McAfee Billable Title: HSE Coordinator II | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 12 | EA | 1120 | 70 | 78400
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 13 | 15119 - 13 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/04/2026 14:41:39 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 10/29/2025 | Not Relevant | N/A | 13 | EA | 800 | 195.8 | 156640
15119 | Fermi Frame 6B PGP - TO#4 - Labor (Construction) | 10/22/2025 | Follow-Up Document Created | TO#4 - Labor (Construction) | 14 | 15119 - 14 | - | Labor - Construction | Labor - Management, EHS | Follow-Up Document Created | 01/03/2026 17:36:25 CST | AP FBO American Prof Staffing Sol. LLC | CPSO-0255-4-9 | Subcontracts Coordinator - OT | # | # | # | Not assigned | # | # | Not assigned | Service | 10/29/2025 | Not Relevant | N/A | 14 | EA | 1250 | 130 | 162500
15141 | Fermi Frame 6B PGP - TO#4 - 3/4" CR Rock (General Areas and Site Works) | 10/24/2025 | Follow-Up Document Created | TO#4 - 3/4" CR Rock (General Areas and Site Works) | 1 | 15141 - 1 | - | Construction | Civil - Aggregates | Follow-Up Document Created | 12/23/2025 14:13:40 CST | Zephyr 5001, LLC | CPSO-0255-4-9 | 3/4" CR Rock ($65.00/Ton) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/30/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 1750000
15141 | Fermi Frame 6B PGP - TO#4 - 3/4" CR Rock (General Areas and Site Works) | 10/24/2025 | Follow-Up Document Created | TO#4 - 3/4" CR Rock (General Areas and Site Works) | 2 | 15141 - 2 | 0 | 0 | Civil - Aggregates | Follow-Up Document Created | 12/23/2025 14:08:22 CST | Zephyr 5001, LLC | CPSO-0255-4-9 | Select Fill | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/30/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 1200000
15141 | Fermi Frame 6B PGP - TO#4 - 3/4" CR Rock (General Areas and Site Works) | 10/24/2025 | Follow-Up Document Created | TO#4 - 3/4" CR Rock (General Areas and Site Works) | 3 | 15141 - 3 | 0 | 0 | Civil - Aggregates | Follow-Up Document Created | 12/22/2025 07:22:57 CST | Zephyr 5001, LLC | CPSO-0255-4-9 | Lumber & Misc Supplies | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/30/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 100000
15142 | Fermi Frame 6B PGP - TO#4 - Fly Ash (General Areas & Site Works) | 10/24/2025 | Sent | TO#4 - Fly Ash (General Areas & Site Works) | 1 | 15142 - 1 | - | Construction | Civil - Aggregates | Sent | 10/24/2025 11:51:47 CST | Casca Belle LLC | CPSO-0255-4-9 | Fly Ash ($29.00/Ton) | # | # | # | Not assigned | # | # | Not assigned | Limit | 10/31/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 870000
15146 | Fermi Frame 6B PGP - TO#4 - Drilled Piers (CT's & SCR's) | 10/26/2025 | Finished | TO#4 - Drilled Piers (CT's & SCR's) | 1 | 15146 - 1 | - | Construction | Civil - Embeds | Finished | 12/03/2025 11:19:05 CST | Tejas Pier Drilling, LLC | CPSO-0255-4-9 | Drilled Piers (CT's & SCR's) | # | # | # | Not assigned | # | # | Not assigned | Service | 11/04/2025 | Not Relevant | N/A | 1 | EA | 75 | 300 | 22500
15146 | Fermi Frame 6B PGP - TO#4 - Drilled Piers (CT's & SCR's) | 10/26/2025 | Finished | TO#4 - Drilled Piers (CT's & SCR's) | 2 | 15146 - 2 | - | Construction | Civil - Embeds | Finished | 12/03/2025 11:19:05 CST | Tejas Pier Drilling, LLC | CPSO-0255-4-9 | Mobilization | # | # | # | Not assigned | # | # | Not assigned | Service | 11/04/2025 | Not Relevant | N/A | 2 | EA | 1 | 1500 | 1500
15147 | Fermi Frame 6B PGP - TO#4 - Pipe Rack Helical Piles | 10/26/2025 | Finished | TO#4 - Pipe Rack Helical Piles | 1 | 15147 - 1 | - | Construction | Civil - Embeds | Finished | 01/02/2026 12:33:37 CST | Audubon Companies, LLC. | CPSO-0255-4-9 | Pipe Rack Helical Piles (161) | Price per pile: $3,372.93 Predrilling, helical pile, and concrete pedestal. Design, supply and install One Hundred and Forty Two (142) piles and associated caps across the facility for support of pipe rack and other structures. ACS scope also includes concrete pedestals after the helicals have been installed. The pedestals are detailed in the provided drawings and as such, ACS will supply and installing rebar, bolts and concrete as per the drawing. | # | # | Not assigned | # | # | Not assigned | Service | 11/04/2025 | Not Relevant | Free carrier | 1 | EA | 1 | 543042 | 543042
15156 | Fermi Frame 6b PGP - TO#4 - Limit PO: Consumables, Tools, Site Supplies | 10/27/2025 | Follow-Up Document Created | TO#4 - Limit PO: Consumables, Tools, Site Supplies | 1 | 15156 - 1 | 0255-F6B-008 | 0 | Consumables, Tooling | Follow-Up Document Created | 01/04/2026 08:35:51 CST | Groves Industrial Supply Groves Supply Corporation | CPSO-0255-4-9 | Site Supplies, Consumables, Tooling, EHS | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/03/2025 | Not Relevant | Cost and freight | 1 | EA | 0 | 0 | 60000
15157 | Fermi Frame 6B PGP - TO#4 - Grainger Limit PO (Site Supplies, Tools, Consumables) | 10/28/2025 | Follow-Up Document Created | TO#4 - Grainger Limit PO (Site Supplies, Tools, Consumables) | 1 | 15157 - 1 | 0255-F6B-009 | 0 | Consumables, Tooling | Follow-Up Document Created | 12/02/2025 18:23:19 CST | Grainger | CPSO-0255-4-9 | Site Supplies, Tools, Consumables | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/04/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 20000
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 1 | 15167 - 1 | 0255-F6B-010A | 0 | Major Equipment | Follow-Up Document Created | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Electrical Buildings (60x18x14) | Each Building will have the following accessories: • Gland Plates in the building floors for bottom entry cabling • Gland Plates in Upper walls for top entry cabling • Qty of Three (3) HVAC Cutouts/Mounting flanges for ~ 7.5 Ton Units • Qty of One (1) HVAC Cutout/Mounting flange for ~ 2 Ton Unit • One set of double doors with removable transom above doors • One Personnel Door • Internal Wall for Control Room | # | # | Not assigned | # | # | Not assigned | Material | 12/26/2025 | Not Relevant | Free on board | 1 | EA | 2 | 264863.75 | 529727.5
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 2 | 15167 - 2 | 0255-F6B-010A | 0 | Major Equipment | Follow-Up Document Created | 12/02/2025 16:56:45 CST | Lynn Energy Services | CPSO-0255-4-1 | 10-Ton Wall Mount HVAC Units | Includes one lead lag controller per building | # | # | Not assigned | # | # | Not assigned | Material | 01/26/2026 | Not Relevant | Free on board | 2 | EA | 4 | 37052.5 | 148210
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 3 | 15167 - 3 | 0255-F6B-010A | 0 | Major Equipment | Sent | 12/09/2025 15:19:01 CST | Lynn Energy Services | CPSO-0255-4-1 | 80 kVA 480V-208Y/120V UPS (5hrs) | 80 kVA 480V-208Y/120V UPS with (5) Hours of Runtime at 45 kVA Load | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Relevant | Free on board | 3 | XPK | 1 | 177025 | 177025
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 4 | 15167 - 4 | 0255-F6B-010A | 0 | 0 | Canceled | 12/05/2025 22:11:47 CST | Lynn Energy Services | CPSO-0255-4-1 | 80 kVA 480V-208Y/120V UPS (175mins) | 80 kVA 480V-208Y/120V UPS with (175) Minutes of Runtime at 45 kVA Load | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Relevant | Free on board | 4 | EA | 1 | 143415 | 143415
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 5 | 15167 - 5 | 0255-F6B-010A | 0 | 0 | Canceled | 12/05/2025 22:11:47 CST | Lynn Energy Services | CPSO-0255-4-1 | 80 kVA 480V-208Y/120V UPS (90mins) | 80 kVA 480V-208Y/120V UPS with (90) Minutes of Runtime at 45 kVA Load | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Relevant | Free on board | 5 | EA | 1 | 114495 | 114495
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 6 | 15167 - 6 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Building (1) Integration | # | # | # | Not assigned | # | # | Not assigned | Service | 01/09/2026 | Not Relevant | Free on board | 6 | EA | 1 | 314755 | 314755
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 7 | 15167 - 7 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Building (2) Integration | # | # | # | Not assigned | # | # | Not assigned | Service | 01/09/2026 | Not Relevant | Free on board | 7 | EA | 1 | 574340 | 574340
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 8 | 15167 - 8 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Roll Up Access Door and Gland Plates | # | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Delivered | Free on board | 8 | EA | 1 | 70615 | 70615
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 9 | 15167 - 9 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Stairs and Landing for Buildings 1, 2 | # | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Delivered | Free on board | 9 | EA | 1 | 95265 | 95265
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 10 | 15167 - 10 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Personnel door reloc & H2 Ventilation | # | # | # | Not assigned | # | # | Not assigned | Service | 01/09/2026 | Not Relevant | Free on board | 10 | EA | 1 | 37375 | 37375
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 11 | 15167 - 11 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | Int Control Cabling & DIN Rail Relays | # | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Delivered | Free on board | 11 | EA | 1 | 27090 | 27090
15167 | Fermi Frame 6B PGP - TO#4 - Electrical Buildings, HVAC, UPS System | 10/29/2025 | In Approval | TO#4 - Electrical Buildings, HVAC, UPS System | 12 | 15167 - 12 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:28:37 CST | Lynn Energy Services | CPSO-0255-4-1 | 480V Lighting Contactor Panel | # | # | # | Not assigned | # | # | Not assigned | Material | 01/09/2026 | Not Delivered | Free on board | 12 | EA | 1 | 1700 | 1700
15171 | Fermi Frame 6B PGP - TO#4 - Pipe Rack | 10/29/2025 | Follow-Up Document Created | # | 1 | 15171 - 1 | 0255-F6B-011A, B, | 0 | Bulks - Structural | Follow-Up Document Created | 12/29/2025 15:37:43 CST | USA Weld Express, LLC | CPSO-0255-4-9 | Beams Stand | # | # | # | Not assigned | # | # | Not assigned | Material | 12/17/2025 | Not Relevant | Free carrier | 1 | EA | 55 | 11500 | 632500
15171 | Fermi Frame 6B PGP - TO#4 - Pipe Rack | 10/29/2025 | Follow-Up Document Created | # | 2 | 15171 - 2 | 0255-F6B-011A, B, | 0 | Bulks - Structural | Follow-Up Document Created | 12/29/2025 15:37:43 CST | USA Weld Express, LLC | CPSO-0255-4-9 | Middle Horizontal Pieces | # | # | # | Not assigned | # | # | Not assigned | Material | 12/17/2025 | Not Relevant | Free carrier | 2 | EA | 111 | 1950 | 216450
15171 | Fermi Frame 6B PGP - TO#4 - Pipe Rack | 10/29/2025 | Follow-Up Document Created | # | 3 | 15171 - 3 | 0255-F6B-011A, B, | 0 | Bulks - Structural | Follow-Up Document Created | 12/29/2025 15:37:43 CST | USA Weld Express, LLC | CPSO-0255-4-9 | Bridges | # | # | # | Not assigned | # | # | Not assigned | Material | 12/17/2025 | Not Relevant | Free carrier | 3 | XPK | 5 | 75000 | 375000
15171 | Fermi Frame 6B PGP - TO#4 - Pipe Rack | 10/29/2025 | Follow-Up Document Created | # | 4 | 15171 - 4 | 0255-F6B-011A, B, | 0 | Bulks - Structural | Follow-Up Document Created | 12/29/2025 15:37:43 CST | USA Weld Express, LLC | CPSO-0255-4-9 | Cross Members | # | # | # | Not assigned | # | # | Not assigned | Material | 12/17/2025 | Not Relevant | Free carrier | 4 | EA | 10 | 3800 | 38000
15174 | Fermi Frame 6B PGP - TO#4 - Rebar & Cages | 10/29/2025 | Finished | TO#4 - Rebar & Cages | 1 | 15174 - 1 | 0255-F6B-012 | 0 | Bulks - Civil (Embeds) | Finished | 12/29/2025 12:07:31 CST | Katy Steel Co. Inc. | CPSO-0255-4-9 | Reinforcing Steel (Rebar & Cages) | New Billet, Grade 60 Reinforcing Steel, cut to length, bent, bundled, and tagged including shop drawings Per drawings P02.03-CV-120-DWG-00006_1, 101_1, 103_1 54 cages (GT's), 21 cages (SCR's) | # | # | Not assigned | # | # | Not assigned | Material | 11/05/2025 | Delivered | Ex works | 1 | EA | 177091 | 58.75 | 104040.96
15174 | Fermi Frame 6B PGP - TO#4 - Rebar & Cages | 10/29/2025 | Finished | TO#4 - Rebar & Cages | 2 | 15174 - 2 | 0255-F6B-012 | 0 | Bulks - Civil (Embeds) | Finished | 12/09/2025 10:42:39 CST | Katy Steel Co. Inc. | CPSO-0255-4-9 | Tie Wire | # | # | # | Not assigned | # | # | Not assigned | Material | 11/05/2025 | Not Relevant | Ex works | 2 | EA | 5 | 75 | 375
15208 | Fermi Frame 6B PGP - TO#4 - Office Furniture/Trailers Setup/Office Supplies | 11/02/2025 | Follow-Up Document Created | TO#4 - Office Furniture/Trailers Setup/Office Supplies | 1 | 15208 - 1 | 0255-F6B-040 | 0 | Facilities | Follow-Up Document Created | 01/02/2026 19:18:09 CST | Uline | CPSO-0255-4-9 | Office Setup/Supplies | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/09/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 120000
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 1 | 15209 - 1 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Senior Project Manager 1 | Contractor Billable Title: Sr. Project Management - ST RPS Billable Title: Sr. Project Management | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 1 | EA | 200 | 136.08 | 27216
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 2 | 15209 - 2 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Senior Project Manager 1 | Contractor Billable Title: Sr. Project Management - OT RPS Billable Title: Sr. Project Management | # | PROJ0007 | Senior Project Manager 1 | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 2 | EA | 180 | 184.52 | 33213.6
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 3 | 15209 - 3 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Superintendent - Civil (ST) RPS Billable Title: Superintendent - Site/Civil | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 3 | XPK | 400 | 89.65 | 35860
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 4 | 15209 - 4 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Superintendent - Civil (OT) RPS Billable Title: Superintendent - Site/Civil | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 4 | EA | 308 | 121.57 | 37443.56
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 5 | 15209 - 5 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Project Services-Scheduling | Contractor Billable Title: Project Scheduler (ST) RPS Billable Title: Project Scheduler | # | PROJ0001 | Project Services-Scheduling | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 5 | EA | 280 | 104.06 | 29136.8
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 6 | 15209 - 6 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Project Services-Scheduling | Contractor Billable Title: Project Scheduler (OT) RPS Billable Title: Project Scheduler | # | PROJ0001 | Project Services-Scheduling | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 6 | EA | 308 | 141.1 | 43458.8
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 7 | 15209 - 7 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Quality Control Manager | Contractor Billable Title: Quality Manager (ST) RPS Billable Title: Quality Manager | # | QUAL0001 | Quality Control Manager | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 7 | EA | 280 | 88.05 | 24654
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 8 | 15209 - 8 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Quality Control Manager | Contractor Billable Title: Quality Manager (OT) RPS Billable Title: Quality Manager | # | QUAL0001 | Quality Control Manager | # | # | Hour(s) | Service | 11/07/2025 | Not Relevant | N/A | 8 | EA | 308 | 119.4 | 36775.2
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 9 | 15209 - 9 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 12:40:02 CST | E&H Excavations LLC | CPSO-0255-4-9 | HSE Supervisor | Contractor Billable Title: HSE Supervisor (ST) RPS Billable Title: HSE Supervisor | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 9 | EA | 280 | 83.25 | 23310
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 10 | 15209 - 10 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 12:40:02 CST | E&H Excavations LLC | CPSO-0255-4-9 | HSE Supervisor | Contractor Billable Title: HSE Supervisor (OT) RPS Billable Title: HSE Supervisor | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 10 | EA | 308 | 112.88 | 34767.04
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 11 | 15209 - 11 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Office Manager | Contractor Billable Title: Office Manager (ST) RPS Billable Title: Office Manager | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 11 | EA | 280 | 56.03 | 15688.4
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 12 | 15209 - 12 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Office Manager | Contractor Billable Title: Office Manager (OT) RPS Billable Title: Office Manager | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 12 | EA | 308 | 75.98 | 23401.84
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 13 | 15209 - 13 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Equipment Operator J1 (2) | Contractor Billable Title: Operators J1 (ST) RPS Billable Title: Forklift Operator | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 13 | EA | 960 | 83.25 | 79920
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 14 | 15209 - 14 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Equipment Operator J1 (2) | Contractor Billable Title: Operators J1 (OT) RPS Billable Title: Forklift Operator | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 14 | EA | 1056 | 112.88 | 119201.28
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 15 | 15209 - 15 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Tool Room Attendant | Contractor Billable Title: Tool Room Attendant (ST) RPS Billable Title: Warehouse Crew | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 15 | EA | 640 | 44.83 | 28691.2
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 16 | 15209 - 16 | - | 0 | Labor - Civil | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Tool Room Attendant | Contractor Billable Title: Tool Room Attendant (OT) RPS Billable Title: Warehouse Crew | # | # | Not assigned | # | # | Not assigned | Service | 11/07/2025 | Not Relevant | N/A | 16 | EA | 704 | 60.78 | 42789.12
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 17 | 15209 - 17 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 12:40:02 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Civil J1 (ST) - Qty 8 RPS Billable Title: Civil Journeyman I | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 17 | EA | 4496 | 64.04 | 287923.84
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 18 | 15209 - 18 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 12:40:02 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Civil J1 (OT) - Qty 8 RPS Billable Title: Civil Journeyman I | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 18 | EA | 4485 | 86.83 | 389432.55
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 19 | 15209 - 19 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Civil J2 (ST) - Qty 7 RPS Billable Title: Civil Journeyman II | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 19 | EA | 2800 | 60.84 | 170352
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 20 | 15209 - 20 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contract Labor, Civil | Contractor Billable Title: Civil J2 (OT) - Qty 7 RPS Billable Title: Civil Journeyman II | # | SVC000008 | Contract Labor, Civil | # | # | Each | Service | 11/07/2025 | Not Relevant | N/A | 20 | EA | 3080 | 82.49 | 254069.2
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 21 | 15209 - 21 | - | 0 | Expenses | Follow-Up Document Created | 12/31/2025 12:40:02 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 11/07/2025 | Not Relevant | N/A | 21 | EA | 1505 | 178 | 267890
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 22 | 15209 - 22 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Rental Equipment | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/08/2025 | Not Relevant | N/A | 22 | EA | 0 | 0 | 192000
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 23 | 15209 - 23 | - | 0 | Labor - Civil | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Safety & Consumables | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/08/2025 | Not Relevant | N/A | 23 | EA | 0 | 0 | 87360
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 24 | 15209 - 24 | - | 0 | Expenses | Follow-Up Document Created | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contractor Per Diem Expense | Truck allowance, Hotel, Flights | # | # | Not assigned | # | # | Not assigned | Limit | 11/08/2025 | Not Relevant | N/A | 24 | EA | 0 | 0 | 600000
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 25 | 15209 - 25 | #N/A | #N/A | #N/A | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Brundage - Pump Truck Rental | # | # | # | Not assigned | # | # | Not assigned | Service | 01/09/2026 | Not Relevant | N/A | 25 | EA | 8 | 3000 | 24000
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 26 | 15209 - 26 | #N/A | #N/A | #N/A | Finished | 12/31/2025 09:55:36 CST | E&H Excavations LLC | CPSO-0255-4-9 | Project Planner/Scheduler (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 12/31/2025 | Not Relevant | N/A | 26 | EA | 60 | 108.87 | 6532.2
15209 | Fermi Frame 6B PGP - Civil: Site Work & Grating for Pad Site & Laydown | 11/02/2025 | Follow-Up Document Created | Civil: Site Work & Grating for Pad Site & Laydown | 27 | 15209 - 27 | #N/A | #N/A | #N/A | Sent | 12/30/2025 15:34:28 CST | E&H Excavations LLC | CPSO-0255-4-9 | Project Planner/Scheduler (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 12/31/2025 | Not Relevant | N/A | 27 | EA | 80 | 147.62 | 11809.6
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 1 | 15216 - 1 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 11 x 24" Embed Plt A36 Galv | LI 1 1 1/2" x 11 x 24" Embed Plt A36 Galv w/ (6) Line 1A Ref: Detail 1/0101 Dwg: 00102 INCLUDES (54) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 1 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 1 | EA | 9 | 328.5 | 2956.5
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 2 | 15216 - 2 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 14 x 32" Embed Plt A36 Galv | LI 3 1 1/2" x 14 x 32" Embed Plt A36 Galv W/ (2) 1-3/4" Holes per DWG W/ (6) Line 3A REF: Detail 3 / 0101 DWG: 00102 INCLUDES 108 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 3 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 2 | EA | 18 | 446.5 | 8037
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 3 | 15216 - 3 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:49:47 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 24 x 24" Sq Embed Plt A36 Galv | LI 4 1 1/2" x 24 x 24" Sq Embed Plt A36 Galv W/ (9) Line 4A REF: Detail 4 /0101 DWG 00102 INCLUDES (81) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 4 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 3 | XPK | 9 | 596.8 | 5371.2
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 4 | 15216 - 4 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 14 x 22" Embed Plt A36 Galv | LI 5 1 1/2" x 14 x 22" Embed Plt A36 Galv W/ (2) 2-3/8" Holes per DWG W/ (6) Line 5A REF: Detail 5 /0101 DWG: 00102 INCLUDES (216) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 5 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 4 | EA | 36 | 357.3 | 12862.8
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 5 | 15216 - 5 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 8 x 12" Embed Plt A36 Galv | LI 6 1 1/2" x 8 x 12" Embed Plt A36 Galv W/ (2) Line 6A REF: Detail 6 /0101 DWG: 00102 INCLUDES (72) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 6 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 5 | EA | 36 | 119.6 | 4305.6
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 6 | 15216 - 6 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 12 x 48" Embed Plt A36 Galv | LI 8 1 1/2" x 12 x 48" Embed Plt A36 Galv W/ (2) 1-3/4" Holes per DWG W/ (12) Line 8A REF: Detail 8 /0101 DWG: 00103 INCLUDES (432) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 8 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 6 | EA | 36 | 681 | 24516
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 7 | 15216 - 7 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1/2" x 4" OD Jacking Plt A36 Galv | LI 9 1/2" x 4" OD Jacking Plt A36 Galv W/ (3) 3/8 x 4" Studs per DWG REF: Detail 9 /0101 DWG: 00103 | JACKING PLATES | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 7 | EA | 36 | 24.5 | 882
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 8 | 15216 - 8 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 36" ROD F1554 GR.36 Galv | LI 11 1 1/2" x 36" ROD F1554 GR.36 Galv 7 1/2" TOP 2" BOT W/(1) HHN Tack 3 Plcs W/ (2) HHN & (1) F436 F/W REF: Anchor Bolt Type 1 /0101 DWG 00104 | GT GENERATOR - AB-1 | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 8 | EA | 252 | 47.85 | 12058.2
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 9 | 15216 - 9 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 32" ROD F1554 GR.36 Galv | LI 12 1 1/2" x 32" ROD F1554 GR.36 Galv 3 1/2" TOP 2" BOT W/ (1) HHN Tack 3 Pcs W/ (2) HHN & (1) F436 F/W REF: Anchor Bolt Type 2 /0101 DWG: 00104 | GT GENERATOR - AB-2 | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 9 | EA | 72 | 47.85 | 3445.2
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 10 | 15216 - 10 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1" x 24" ROD F1554 GR.36 Galv | LI 13 1" x 24" ROD F1554 GR.36 Galv 5 1/2" TOP 1 1/2" BOT W/ (1) W/ (2) HHN & (1) F436 F/W REF: Anchor Bolt Type 3 /0101 DWG: 00104 | GT GENERATOR - AB-3 | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 10 | EA | 36 | 16.5 | 594
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 11 | 15216 - 11 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 8 x 12" Embed Plt A36 Galv | LI 2 l1-1/2 X 8 X 12" EMBED PLT A36 GALV W/ (1) 1-3/4" HOLE PER DWG W/ (2) LINE 2A REF: DETAIL 2 / 0101 DWG: 00102 INCLUDES (144) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 2 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 11 | EA | 72 | 120.6 | 8683.2
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 12 | 15216 - 12 | 0255-F6B-013A,B | 0 | Bulks - Civil (Embeds) | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 1/2" x 12 x 24" Embed Plt A36 Galv | LI 7 1-1/2 X 12 X 24" EMBED PLT A36 GALV W/ (6) LINE 7A REF: DETAIL 7 / 0101 DWG: 00103 INCLUDES (108) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 6 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 12 | EA | 18 | 343.3 | 6179.4
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 13 | 15216 - 13 | - | 0 | Bulks - Civil (Embeds) | Canceled | 01/04/2026 12:18:41 CST | Madden Bolt Corporation | CPSO-0255-4-9 | EXPEDITING FEE | # | # | # | Not assigned | # | # | Not assigned | Service | 11/04/2025 | Not Relevant | Ex works | 13 | EA | 1 | 5271.59 | 5271.59
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 14 | 15216 - 14 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1-1/2 X 8 X 17" PLT A36 GALV | LI 10 1-1/2 X 8 X 17" PLT A36 GALV W/ (6) LINE 10A REF: DETAIL 10 / 0101 DWG: 00103 INCLUDES (54) 1 X 10-1/2" HEADED SHEAR STUD A108 WELDED TO LINE 10 PER DWG | GT GENERATOR | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 14 | EA | 9 | 246.4 | 2217.6
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 15 | 15216 - 15 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1-1/2 X 36" ROD F1554 GR.36 GALV | LI 14 1-3/4 X 43" ROD F1554 GR 36 GALV 22"TOP 2-1/2"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (2) HHN 􀀦 (1) LINE 14A REF: ANCHOR BOLT TYPE 4 / 0101 DWG: 00104 INCLUDES (198) 5/8 X 4-1/2" S􀁑 PLT A36 GALV (1-13/16"I.D) FOR 1-3/4" BOLT | GT GENERATOR - AB-4 | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 15 | EA | 198 | 80.6 | 15958.8
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 16 | 15216 - 16 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 X 28" ROD F1554 GR 36 GALV | LI 15 1 X 28" ROD F1554 GR 36 GALV 8"TOP 1-1/2"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (2) HHN 􀀦 (1) LINE 15A REF: ANCHOR BOLT TYPE 5 / 0101 DWG: 00104 INCLUDES (792) 3/8 X 3" S􀁑 PLT A36 GALV (1-1/8"I.D) FOR 1" BOLT | GT GENERATOR - AB-5 | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 16 | EA | 792 | 20.2 | 15998.4
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 17 | 15216 - 17 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1/2 X 11" ROD F1554 GR 36 GALV | LI 16 1/2 X 11" ROD F1554 GR 36 GALV 2"TOP 1"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (1) HHN 􀀦 (1) F436 FW REF: ANCHOR BOLT DETAIL 1 DWG: 01301 | SCR Ammonia Injection Skid | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 17 | EA | 36 | 4.75 | 171
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 18 | 15216 - 18 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 X 11" ROD F1554 GR 36 GALV | LI 17 1 X 11" ROD F1554 GR 36 GALV 3-1/2"TOP 1"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (1) HHN 􀀦 (1) F436 FW REF: ANCHOR BOLT DETAIL 1 DWG: 01501 | Water Injection Skid | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 18 | EA | 36 | 10.3 | 370.8
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 19 | 15216 - 19 | 0255-F6B-013A,B | #N/A | #N/A | Finished | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 3/4 X 11" ROD F1554 GR 36 GALV | LI 18 3/4 X 11" ROD F1554 GR 36 GALV 2"TOP 1"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (1) HHN 􀀦 (1) F436 FW REF: ANCHOR BOLT DETAIL 1 DWG: 03001 | Water Wash Skid | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Relevant | Ex works | 19 | EA | 12 | 6.7 | 80.4
15216 | Fermi Frame 6B PGP - TO#4 - Embeds/Anchor Bolts (GT's/SCR's) | 11/03/2025 | Follow-Up Document Created | TO#4 - Embeds/Anchor Bolts | 20 | 15216 - 20 | 0255-F6B-013A,B | #N/A | #N/A | Follow-Up Document Created | 12/30/2025 15:37:28 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1/2 X 15" ROD F1554 GR 36 GALV | LI 19 1/2 X 15" ROD F1554 GR 36 GALV 7"TOP 1"BOT W/ (1) HHN TACK TYP BOT 3-PLCS W/ (1) HHN 􀀦 (1) F436 FW REF: ANCHOR BOLT DETAIL 1 DWG: 05001 | Meefog Pump Skid | # | Not assigned | # | # | Not assigned | Material | 11/04/2025 | Not Delivered | Ex works | 20 | EA | 36 | 5 | 180
15222 | Fermi Frame 6B PGP - TO#4 - Fuel for Site Equipment | 11/05/2025 | Follow-Up Document Created | TO#4 - Fuel for Site Equipment | 1 | 15222 - 1 | - | 0 | Facilities - Fuel | Follow-Up Document Created | 12/23/2025 16:07:12 CST | Davidson Oil Company | CPSO-0255-4-9 | DIESEL - CLEAR | Clear: Amarillo OPIS AM Gross ULS Contract Avg plus .30 per gallon | # | # | Not assigned | # | # | Not assigned | Limit | 11/12/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 50000
15222 | Fermi Frame 6B PGP - TO#4 - Fuel for Site Equipment | 11/05/2025 | Follow-Up Document Created | TO#4 - Fuel for Site Equipment | 2 | 15222 - 2 | - | 0 | Facilities - Fuel | Follow-Up Document Created | 12/23/2025 15:55:24 CST | Davidson Oil Company | CPSO-0255-4-9 | UNLEAD GASOLINE/ETHANOL | Unlead: Amarillo OPIS AM Gross CBOB Ethanol 10% Contract Average plus .30 per gallon | # | # | Not assigned | # | # | Not assigned | Limit | 11/12/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 40000
15222 | Fermi Frame 6B PGP - TO#4 - Fuel for Site Equipment | 11/05/2025 | Follow-Up Document Created | TO#4 - Fuel for Site Equipment | 3 | 15222 - 3 | - | 0 | Facilities - Fuel | Follow-Up Document Created | 12/27/2025 14:29:38 CST | Davidson Oil Company | CPSO-0255-4-9 | DIESEL - DYED | Dyed: Amarillo OPIS AM Gross ULS Red Dye Contract AVG plus .30 per gallon | # | # | Not assigned | # | # | Not assigned | Limit | 11/12/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 50000
15222 | Fermi Frame 6B PGP - TO#4 - Fuel for Site Equipment | 11/05/2025 | Follow-Up Document Created | TO#4 - Fuel for Site Equipment | 4 | 15222 - 4 | - | 0 | Facilities - Fuel | Follow-Up Document Created | 01/02/2026 15:08:24 CST | Davidson Oil Company | CPSO-0255-4-9 | MISC FEES - TANK DELIVERY, RENTAL, ETC | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/12/2025 | Not Relevant | Free carrier | 4 | EA | 0 | 0 | 15000
15238 | Fermi Frame 6B PGP - TO#4 - Main Laydown & Equipment Laydown Fencing | 11/06/2025 | Follow-Up Document Created | TO#4 - Main Laydown & Equipment Laydown Fencing | 1 | 15238 - 1 | - | 0 | Facilities - Fencing | Follow-Up Document Created | 12/21/2025 15:18:39 CST | TriWest Fence LLC | CPSO-0255-4-9 | Main - 6' Galv Chainlink Fence (2960LF) | Furnish & install approximately 2960LF of 6' galvanized chainlink & 2ea 20' cantilever slide gates according to the layout & the specs in the quote attached. Upgrade (2) gates and added (2) gates x $4500.00ea = $9000.00 | # | # | Not assigned | # | # | Not assigned | Material | 11/13/2025 | Delivered | Free carrier | 1 | EA | 1 | 101000 | 101000
15238 | Fermi Frame 6B PGP - TO#4 - Main Laydown & Equipment Laydown Fencing | 11/06/2025 | Follow-Up Document Created | TO#4 - Main Laydown & Equipment Laydown Fencing | 2 | 15238 - 2 | - | 0 | Facilities - Fencing | Finished | 12/21/2025 15:20:46 CST | TriWest Fence LLC | CPSO-0255-4-9 | Equip - 6' Galv Chainlink Fence (1980LF) | Furnish & install approximately 1980LF of 6' galvanized chainlink & 1ea 20' cantilever slide gates according to the layout & the specs in the quote attached. Upgrade (1) gate and added (3) gates | # | # | Not assigned | # | # | Not assigned | Material | 11/13/2025 | Delivered | Free carrier | 2 | EA | 1 | 74500 | 74500
15289 | Fermi Frame 6B PGP - TO#4 - Soil Testing | 11/09/2025 | Follow-Up Document Created | Soil Testing | 1 | 15289 - 1 | - | 0 | Quality - Testing | Follow-Up Document Created | 01/04/2026 14:58:41 CST | Terracon Consultants, Inc. | CPSO-0255-4-9 | Site Soil Testing | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/14/2025 | Not Relevant | N/A | 1 | EA | 0 | 0 | 80000
15310 | Fermi Frame 6B PGP - TO#4 - Temporary Power for Trailers/Laydown | 11/11/2025 | Follow-Up Document Created | Temporary Power for Trailers/Laydown | 1 | 15310 - 1 | - | 0 | Labor - Electrical (Facilities) | Follow-Up Document Created | 12/12/2025 15:01:13 CST | MEITEC, Inc. | CPSO-0255-4-9 | Material | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 1 | EA | 0 | 0 | 49105
15310 | Fermi Frame 6B PGP - TO#4 - Temporary Power for Trailers/Laydown | 11/11/2025 | Follow-Up Document Created | Temporary Power for Trailers/Laydown | 2 | 15310 - 2 | - | 0 | Labor - Electrical (Facilities) | Follow-Up Document Created | 12/17/2025 13:22:31 CST | MEITEC, Inc. | CPSO-0255-4-9 | Equipment and Site Cost | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 2 | EA | 0 | 0 | 2139
15310 | Fermi Frame 6B PGP - TO#4 - Temporary Power for Trailers/Laydown | 11/11/2025 | Follow-Up Document Created | Temporary Power for Trailers/Laydown | 3 | 15310 - 3 | - | 0 | Labor - Electrical (Facilities) | Finished | 12/17/2025 13:22:31 CST | MEITEC, Inc. | CPSO-0255-4-9 | Labor | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 55000
15311 | Fermi Frame 6B PGP - TO#4 - Misc. Hardware | 11/11/2025 | Not Yet Acknowledged | Fastenal Limit PO - Misc. Hardware | 1 | 15311 - 1 | 0255-F6B-041 | 0 | Consumables, Tooling | Not Yet Acknowledged | 11/11/2025 06:10:03 CST | Fastenal Company | CPSO-0255-4-9 | Misc Hardware | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 5000
15330 | Fermi Frame 6B PGP - TO#4 - (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 11/12/2025 | In Approval | (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 1 | 15330 - 1 | 0255-F6B-014 | 0 | Major Equipment | Follow-Up Document Created | 01/04/2026 14:39:30 CST | Petrotech Inc | CPSO-0255-4-1 | Material and Eng (3 Controls Refurb) | Per Proposal 25-0239 (rev.1) - To include new hardware and services to design and fabricate (3) GE Frame 6B Controls Systems. | # | # | Not assigned | # | # | Not assigned | Service | 11/19/2025 | Not Relevant | Ex works | 1 | EA | 3 | 481183 | 1443549
15330 | Fermi Frame 6B PGP - TO#4 - (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 11/12/2025 | In Approval | (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 2 | 15330 - 2 | 0255-F6B-014 | 0 | Major Equipment | Sent | 01/04/2026 14:39:30 CST | Petrotech Inc | CPSO-0255-4-1 | Control System Integration | Proposal: CO25-116001-001 (12/09/25) Three (3) GE Frame 6B Turbine Control System Control Cab Integration into the Control Cabs. Scope includes integration of the control subplates into the control buildings and refurbishment of all 3 buildings. | # | # | Not assigned | # | # | Not assigned | Service | 11/19/2025 | Not Relevant | Ex works | 2 | EA | 3 | 205769.67 | 617309.01
15330 | Fermi Frame 6B PGP - TO#4 - (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 11/12/2025 | In Approval | (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 3 | 15330 - 3 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:39:30 CST | Petrotech Inc | CPSO-0255-4-1 | Generator protection Relay Testing | Engineering and shop services to assist the Relay Test Engineers with the removal, testing setup, documentation of settings, and re-installation of the protection relays. Two (2) Relay Test Engineers to be on site for a period of two (2) days per control house working a 10-hour day, five (5) days (M-F) per week to complete the Generator protection relay testing. The Relay Test Engineers will perform relay testing and generate test reports per scope defined in attached proposal. | # | # | Not assigned | # | # | Not assigned | Service | 11/19/2025 | Not Relevant | Ex works | 3 | XPK | 3 | 21265 | 63795
15330 | Fermi Frame 6B PGP - TO#4 - (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 11/12/2025 | In Approval | (3) GE Frame 6B Mark IV Controls Upgrades, (3) Control System Integration into the Control Cabs | 4 | 15330 - 4 | #N/A | #N/A | #N/A | In Preparation | 01/04/2026 14:39:30 CST | Petrotech Inc | CPSO-0255-4-1 | 700G hardware and firmware upgrades | Generator Protection Relay Upgrade for Auto-Synchronization Functionality for Three (3) GE Frame 6B Turbine Control Houses Firmware Upgrade from 700G Basic protection to 700G1+ Basic protection plus 87, Gen 25, 21, 78, 78VS, Auto Synchronizer. | # | # | Not assigned | # | # | Not assigned | Material | 11/19/2025 | Not Relevant | Ex works | 4 | EA | 3 | 7470.33 | 22410.99
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 1 | 15350 - 1 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil QC (ST) | RPS Billable Rate - Quality Inspector (ST) Juan Rincon Rajesh Chalamagunta | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 1 | EA | 0 | 0 | 180000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 2 | 15350 - 2 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil QC (OT) | RPS Billable Rate - Quality Inspector (OT) Juan Rincon Rajesh Chalamagunta | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 2 | EA | 0 | 0 | 260000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 3 | 15350 - 3 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/12/2025 11:31:05 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Quantity Surveyor (ST) | RPS Billable Title - Quantity Surveyor (ST) Scott Faler | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 60000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 4 | 15350 - 4 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/12/2025 11:31:05 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Quantity Surveyor (OT) | RPS Billable Title - Quantity Surveyor (OT) Scott Faler | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 4 | EA | 0 | 0 | 92000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 5 | 15350 - 5 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (ST) | RPS Billable Title: Civil Journeyman II (ST) Brandon Soldivar Irvin Ozuna Jesus Soldivar Joel Soldivar | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 5 | EA | 0 | 0 | 200000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 6 | 15350 - 6 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (OT) | RPS Billable Title: Civil Journeyman II (OT) Brandon Soldivar Irvin Ozuna Jesus Soldivar Joel Soldivar | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 6 | EA | 0 | 0 | 320000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 7 | 15350 - 7 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (ST) | RPS Billable Title: Civil Journeyman III (ST) Gilbert Enrique Jose Hernandez Leodegario Trevino Ruben Cortez Oscar Rodriguez Ramon Cordero Samuel Rogelio Arroyo Jose Manuel Reynosa Torres Jose Martinez Jose Servin Vazquez Juan Gilberto Garza Palacios | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 7 | EA | 0 | 0 | 240000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 8 | 15350 - 8 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (OT) | RPS Billable Title: Civil Journeyman III (OT) Gilbert Enrique Jose Hernandez Leodegario Trevino Ruben Cortez Oscar Rodriguez Ramon Cordero Samuel Rogelio Arroyo Jose Manuel Reynosa Torres Jose Martinez Jose Servin Vazquez Juan Gilberto Garza Palacios | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 8 | EA | 0 | 0 | 370000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 9 | 15350 - 9 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Foreman (ST) | RPS Billable Title: General Foreman - Concrete (ST) Nemencio Ozuna | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 9 | EA | 0 | 0 | 70000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 10 | 15350 - 10 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Foreman (OT) | RPS Billable Title: General Foreman - Concrete (OT) Nemencio Ozuna | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 10 | EA | 0 | 0 | 120000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 11 | 15350 - 11 | - | 0 | Labor - Construction | Sent | 12/12/2025 11:31:05 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Tool room attendant (ST) | RPS Billable Title: Warehouse Crew (ST) Doreli Ozuna | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 11 | EA | 0 | 0 | 96000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 12 | 15350 - 12 | - | 0 | Labor - Construction | Sent | 12/12/2025 11:31:05 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Tool room attendant (OT) | RPS Billable Title: Warehouse Crew (OT) Doreli Ozuna | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 12 | EA | 0 | 0 | 150000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 13 | 15350 - 13 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Surveyor & Surveyor Helper (ST) | RPS Billable Title: Survey Crew (ST) Ricardo Madrial Jose Angel Mendez Micah Alba | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 13 | EA | 0 | 0 | 120000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 14 | 15350 - 14 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Surveyor & Surveyor Helper (OT) | RPS Billable Title: Survey Crew (OT) Ricardo Madrial Jose Angel Mendez Micah Alba | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 14 | EA | 0 | 0 | 170000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 15 | 15350 - 15 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Equip & Heavy Equip Op (ST) | RPS Billable Title - Forklift Operator (ST) Andrew Dunwood Arnoldo Galdean | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 15 | EA | 0 | 0 | 120000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 16 | 15350 - 16 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Equip & Heavy Equip Op (OT) | RPS Billable Title - Forklift Operator (OT) Andrew Dunwood Arnoldo Galdean | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 16 | EA | 0 | 0 | 180000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 17 | 15350 - 17 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (ST) | RPS Billable Title: Civil - Journeyman I (ST) Josefina Ocanas Juan Ozuna Santiago Ozuna Ulises Abrego | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 17 | EA | 0 | 0 | 250000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 18 | 15350 - 18 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Civil Worker (OT) | RPS Billable Title: Civil - Journeyman I (OT) Josefina Ocanas Juan Ozuna Santiago Ozuna Ulises Abrego | # | # | Not assigned | # | # | Not assigned | Limit | 11/18/2025 | Not Relevant | N/A | 18 | EA | 0 | 0 | 350000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 19 | 15350 - 19 | - | 0 | Expenses | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Per Diem | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 19 | EA | 0 | 0 | 260000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 20 | 15350 - 20 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Mileage (Mobe/Demobe) | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 20 | EA | 0 | 0 | 80000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 21 | 15350 - 21 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 14:44:33 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Flagger (ST) | RPS Billable Title: Civil - Flagger (ST) Ashley N Gurrero Brandy Diaz Briana Diaz Jakaylin Dewayne Terry Jaqueline Sanchez Jerone Davis Julissa Gaytan Luis Garcia Mauricio Silva | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 21 | EA | 0 | 0 | 300000
15350 | Fermi Frame 6B PGP - TO#4 - Labor - Construction, Warehousing, Quality | 11/13/2025 | Follow-Up Document Created | Labor - Construction, Warehousing, Quality | 22 | 15350 - 22 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/21/2025 23:15:44 CST | Automation Personnel Services, Inc | CPSO-0255-4-9 | Labor - Flagger (OT) | RPS Billable Title: Civil - Flagger (OT) Ashley N Gurrero Brandy Diaz Briana Diaz Jakaylin Dewayne Terry Jaqueline Sanchez Jerone Davis Julissa Gaytan Luis Garcia Mauricio Silva | # | # | Not assigned | # | # | Not assigned | Limit | 11/20/2025 | Not Relevant | N/A | 22 | EA | 0 | 0 | 400000
15352 | Fermi Frame 6B PGP - TO#4 - Receipt of (3) Control Buildings | 11/13/2025 | Finished | Receipt of (3) Control Buildings | 1 | 15352 - 1 | - | 0 | Refurb | Finished | 12/08/2025 08:20:02 CST | Petrotech Inc | CPSO-0255-4-1 | Receive 3 control buildings | Per proposal 25-0264 (rev.2) - Prepare and receive three (3) control buildings at Petrotech facility The pricing in this proposal is based on lifting the three (3) control buildings approximately 16’ L x 10’ W x 10’H weighing approximately 25,000 lbs from the transport company’s (hired by others) truck and lowering onto Petrotech’s lot. | # | # | Not assigned | # | # | Not assigned | Service | 11/19/2025 | Not Relevant | Free carrier | 1 | EA | 3 | 5692 | 17076
15360 | Fermi Frame 6B PGP - TO#4 - Civil Supplies | 11/14/2025 | Follow-Up Document Created | Civil Supplies | 1 | 15360 - 1 | 0255-F6B-015 | 0 | General Site Supplies, Tools, Consumables | Follow-Up Document Created | 12/17/2025 12:18:07 CST | White Cap | CPSO-0255-4-9 | Civil Supplies | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/21/2025 | Not Relevant | Ex works | 1 | EA | 0 | 0 | 80000
15374 | Fermi Frame 6B PGP - TO#4 - (6) Last Chance Gas Fuel Filters | 11/14/2025 | Follow-Up Document Created | (6) Last Chance Gas Fuel Filters | 1 | 15374 - 1 | 0255-F6B-016 | 0 | Major Equipment | Follow-Up Document Created | 12/22/2025 07:18:41 CST | Gaumer Company, Inc. | CPSO-0255-4-1 | Last Chance Gas Fuel Filter | One fuel gas conditioning system to include duplex filter coalescer with nozzles Fuel Gas Filter (304 SS Vessels) 275 – 315 psig operating pressure;13.5 MMSCFD flow rate. | # | # | Not assigned | # | # | Not assigned | Material | 03/10/2026 | Not Delivered | Ex works | 1 | EA | 6 | 57970 | 347820
15374 | Fermi Frame 6B PGP - TO#4 - (6) Last Chance Gas Fuel Filters | 11/14/2025 | Follow-Up Document Created | (6) Last Chance Gas Fuel Filters | 2 | 15374 - 2 | 0255-F6B-016 | 0 | Major Equipment | Sent | 12/22/2025 07:18:41 CST | Gaumer Company, Inc. | CPSO-0255-4-1 | PSV (Bolts/Studs/Nuts and Gasket) - CO#1 | # | # | # | Not assigned | # | # | Not assigned | Material | 03/10/2026 | Not Delivered | Ex works | 2 | EA | 1 | 24684 | 24684
15382 | Fermi Frame 6B PGP - TO#4 - Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 11/17/2025 | Follow-Up Document Created | Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 1 | 15382 - 1 | - | 0 | Facilities - Burden | Follow-Up Document Created | 01/02/2026 15:57:51 CST | Panhandle Portables, LLC | CPSO-0255-4-9 | Day Tank/Water Tank for Trailers | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/24/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 15000
15382 | Fermi Frame 6B PGP - TO#4 - Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 11/17/2025 | Follow-Up Document Created | Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 2 | 15382 - 2 | - | 0 | Facilities - Burden | Follow-Up Document Created | 11/17/2025 16:16:46 CST | Panhandle Portables, LLC | CPSO-0255-4-9 | Plumbing Work | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/24/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 8000
15382 | Fermi Frame 6B PGP - TO#4 - Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 11/17/2025 | Follow-Up Document Created | Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 3 | 15382 - 3 | - | 0 | Facilities - Burden | Follow-Up Document Created | 01/02/2026 15:57:51 CST | Panhandle Portables, LLC | CPSO-0255-4-9 | Porta Potties/Hand Wash Rental (18) | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/24/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 10000
15382 | Fermi Frame 6B PGP - TO#4 - Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 11/17/2025 | Follow-Up Document Created | Porta Potties/Hand Wash Stations, Plumbing, Day/Water tank for trailers | 4 | 15382 - 4 | - | 0 | Facilities - Burden | Follow-Up Document Created | 01/02/2026 15:57:51 CST | Panhandle Portables, LLC | CPSO-0255-4-9 | Misc Charges/Fees | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/24/2025 | Not Relevant | Free carrier | 4 | EA | 0 | 0 | 8000
15399 | Fermi Frame 6B PGP - TO#4 - Tanks (DW, Service, WW, Slop) | 11/18/2025 | Not Yet Acknowledged | Tanks (Demin Water, Service Water, Waste Water, Oily Water Slop) | 1 | 15399 - 1 | 0255-F6B-017 | 0 | Major Equipment | Not Yet Acknowledged | 12/17/2025 12:01:35 CST | CST Industries | CPSO-0255-4-1 | Demin Water Tank (135,447 Gal) TK-400 | Datasheet: P02.03-ME-120-120-DTS-00004 P&ID: 12224A25-120-PP-3018 Configuration #: 30331-X8G0-0-19; Dated: 11/12/2025 HydroTec CS - 29.709FT (9055mm) x 26.12FT (7961mm) | # | # | Not assigned | # | # | Not assigned | Material | 02/03/2026 | Not Delivered | Free carrier | 1 | EA | 1 | 184774 | 184774
15399 | Fermi Frame 6B PGP - TO#4 - Tanks (DW, Service, WW, Slop) | 11/18/2025 | Not Yet Acknowledged | Tanks (Demin Water, Service Water, Waste Water, Oily Water Slop) | 2 | 15399 - 2 | 0255-F6B-017 | 0 | Major Equipment | Not Yet Acknowledged | 12/17/2025 12:01:35 CST | CST Industries | CPSO-0255-4-1 | Service Water Tank (176,065 Gal) TK-600 | Datasheet: P02.03-ME-120-120-DTS-00006 P&ID: 12224A25-120-PP-3016 Configuration #: 30331-X8G0-1-22; Dated: 11/12/2025 HydroTec CS - 32.68FT (9961mm) x 28.06FT (8553mm) | # | # | Not assigned | # | # | Not assigned | Material | 02/03/2026 | Not Delivered | Free carrier | 2 | EA | 1 | 174959 | 174959
15399 | Fermi Frame 6B PGP - TO#4 - Tanks (DW, Service, WW, Slop) | 11/18/2025 | Not Yet Acknowledged | Tanks (Demin Water, Service Water, Waste Water, Oily Water Slop) | 3 | 15399 - 3 | 0255-F6B-017 | 0 | Major Equipment | Not Yet Acknowledged | 12/17/2025 12:01:35 CST | CST Industries | CPSO-0255-4-1 | Waste Water Tank (320,986 Gal) TK-300 | Datasheet: P02.03-ME-120-120-DTS-00005 P&ID: 12224A25-120-PP-3019 Configuration #: 30331-X8G0-2-12; Dated: 11/12/2025 HydroTec CS - 47.534FT (14488mm) x 24.18FT (7370mm) | # | # | Not assigned | # | # | Not assigned | Material | 02/17/2026 | Not Delivered | Free carrier | 3 | XPK | 1 | 267119 | 267119
15399 | Fermi Frame 6B PGP - TO#4 - Tanks (DW, Service, WW, Slop) | 11/18/2025 | Not Yet Acknowledged | Tanks (Demin Water, Service Water, Waste Water, Oily Water Slop) | 4 | 15399 - 4 | 0255-F6B-017 | 0 | Major Equipment | Not Yet Acknowledged | 12/17/2025 12:01:35 CST | CST Industries | CPSO-0255-4-1 | Slop Water Tank (7,174 Gal) TK-100 | Datasheet: P02.03-ME-120-120-DTS-00012 P&ID: 12224A25-120-PP-3014 Configuration #: 30331-X8G0-3-6; Dated: 11/12/2025 HydroTec CS - 12.308FT (3751mm) x 8.06FT (2457mm) | # | # | Not assigned | # | # | Not assigned | Material | 02/17/2026 | Not Delivered | Free carrier | 4 | EA | 1 | 51164 | 51164
15400 | Fermi Frame 6B - TO#4 - Dumpster Rental | 11/18/2025 | Follow-Up Document Created | Dumpster Rental | 1 | 15400 - 1 | - | 0 | Facilities - Burden | Follow-Up Document Created | 12/11/2025 12:20:55 CST | A-1 Rocket Industries, INC | CPSO-0255-4-9 | Dumpsters Rental | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/25/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 40000
15401 | Fermi Frame 6B PGP - TO#4 - Water Frac Tanks (Equipment Delivery, Water Haulage) | 11/18/2025 | Follow-Up Document Created | Water Frac Tanks (Equipment Delivery, Water Haulage) | 1 | 15401 - 1 | - | 0 | Facilities - Water | Follow-Up Document Created | 12/16/2025 14:19:58 CST | Flatland Dirt Works, LLC | CPSO-0255-4-9 | Frac Tanks Rental, Trucking & Water | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/25/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 100000
15402 | Fermi TM2500 - TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 11/18/2025 | Not Yet Acknowledged | TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 1 | 15402 - 1 | 0255-TM-018 | 0 | Major Equipment | Not Yet Acknowledged | 12/02/2025 12:58:35 CST | Equisales Associates | CPSO-0255-5-1 | Black Start System | Tag #: Manual Transfer Switch: MTS-TM1001 Blackstart Generator: BSDG-TM1001 Black Start System for TM Units 1-6 (includes the BSDG and the manual 1000A transfer switch For one system of 6 x TM2500, EQS will provide the black start capability consisting of the generator (Rating: 600 kW / 750 kVA @ 277/480V 3Ø, 902 Full Load Amps) with a manual 1000A 15kV transfer switch. The other five (5) systems will include the transfer switch, however the emergency feed will be wired for utility power. (Normal feed to be from the Aux transformer) | # | # | Not assigned | # | # | Not assigned | Material | 02/18/2026 | Not Relevant | Delivered at place | 1 | EA | 1 | 242529 | 242529
15402 | Fermi TM2500 - TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 11/18/2025 | Not Yet Acknowledged | TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 2 | 15402 - 2 | 0255-TM-018 | 0 | Major Equipment | Not Yet Acknowledged | 12/02/2025 12:58:35 CST | Equisales Associates | CPSO-0255-5-1 | GSU Christmas Tree /Cable Structure | Skids with switchboards for the balance of the 3x TM sets (powered by utility feed) | # | # | Not assigned | # | # | Not assigned | Material | 04/08/2026 | Not Relevant | Delivered at place | 2 | EA | 7 | 40084 | 280588
15402 | Fermi TM2500 - TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 11/18/2025 | Not Yet Acknowledged | TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 3 | 15402 - 3 | 0255-TM-018 | 0 | Major Equipment | Not Yet Acknowledged | 12/02/2025 12:58:35 CST | Equisales Associates | CPSO-0255-5-1 | Station Service XFMR, LDP | Tag #: Manual Transfer Switch: MTS-TM1001 Blackstart Generator: BSDG-TM1001 Black Start System for TM Units 1-6 (includes the BSDG and the manual 1000A transfer switch For one system of 6 x TM2500, EQS will provide the black start capability consisting of the generator (Rating: 600 kW / 750 kVA @ 277/480V 3Ø, 902 Full Load Amps) with a manual 1000A 15kV transfer switch. The other five (5) systems will include the transfer switch, however the emergency feed will be wired for utility power. (Normal feed to be from the Aux transformer) | # | # | Not assigned | # | # | Not assigned | Material | 04/08/2026 | Not Relevant | Delivered at place | 3 | XPK | 7 | 8871 | 62097
15402 | Fermi TM2500 - TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 11/18/2025 | Not Yet Acknowledged | TO#5 - Electrical Equipment (MV/LV Skid, Blackstart System, GSU Christmas Tree /Cable Structure, Station Service XFMR + Lighting Dist. Panel) | 4 | 15402 - 4 | 0255-TM-018 | 0 | Major Equipment | Not Yet Acknowledged | 12/02/2025 12:58:35 CST | Equisales Associates | CPSO-0255-5-1 | MV LV Skid to support 7 sets of 3xTM2500 | Tag #: Manual Transfer Switch: MTS-TM1001 Blackstart Generator: BSDG-TM1001 Black Start System for TM Units 1-6 (includes the BSDG and the manual 1000A transfer switch For one system of 6 x TM2500, EQS will provide the black start capability consisting of the generator (Rating: 600 kW / 750 kVA @ 277/480V 3Ø, 902 Full Load Amps) with a manual 1000A 15kV transfer switch. The other five (5) systems will include the transfer switch, however the emergency feed will be wired for utility power. (Normal feed to be from the Aux transformer) | # | # | Not assigned | # | # | Not assigned | Material | 04/08/2026 | Not Relevant | Delivered at place | 4 | EA | 7 | 392836 | 2749852
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 1 | 15408 - 1 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-9 | LG 33 in. Top Freezer Refrigerator | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 1 | EA | 2 | 699 | 1398
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 2 | 15408 - 2 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-6 | Frigidaire 30 in. Microwave | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 2 | EA | 2 | 268 | 536
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 3 | 15408 - 3 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-6 | Whirlpool 30 in. Microwave | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 3 | XPK | 1 | 238 | 238
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 5 | 15408 - 5 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-6 | LG NeoChef 1100-Watt Microwave | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 5 | EA | 1 | 238 | 238
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 6 | 15408 - 6 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-6 | KENMORE 33 in. Top Freezer Refrigerator | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 6 | EA | 4 | 749.99 | 2999.96
15408 | 255 Fermi, Appliances for Office Trailers and Lunch Tent | 11/18/2025 | Follow-Up Document Created | # | 7 | 15408 - 7 | 0255-F6B-042 | 0 | Facilities | Follow-Up Document Created | 12/26/2025 13:59:02 CST | Home Depot Store 0568 Spring | CPSO-0255-4-6 | GE 1200-Watt Countertop Microwave | # | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Delivered | Free carrier | 7 | EA | 1 | 355 | 355
15423 | Fermi Frame 6B PGP - TO#4 - Inlet Air Filters | 11/19/2025 | Not Yet Acknowledged | Inlet Air Filters | 1 | 15423 - 1 | 0255-F6B-019 | 0 | Major Equipment | Not Yet Acknowledged | 11/20/2025 14:19:02 CST | Camfil Power Systems NA | CPSO-0255-4-1 | Inlet Air Filters | Part Number: 223141001GTA Tenkay HemiPleat/F9/GTC /Galv /26,L Cylindrical, 188 pleats 14.25" 16.00" x 34"L 12.75" Diameter | # | # | Not assigned | # | # | Not assigned | Material | 12/26/2025 | Not Delivered | Free carrier | 1 | EA | 1154 | 109 | 125786
15441 | Fermi Frame 6B PGP - TO#4 - Switchgear and MCC Re-Purposing & Modernization | 11/20/2025 | Follow-Up Document Created | Switchgear and MCC Re-Purposing & Modernization | 1 | 15441 - 1 | 0255-F6B-020 | 0 | Major Equipment | Follow-Up Document Created | 12/28/2025 15:47:04 CST | Shermco Systems Integration LLC | CPSO-0255-4-1 | Swgr Relay Doors & Gear Modernization | Switchgear and MCC Re-Purposing & Modernization - Fully refurbished and modernized switchgear and MCC lineup ready for installation and service. - Updated documentation package (drawings, test reports, configuration files). - Recommendations for future maintenance intervals. | # | # | Not assigned | # | # | Not assigned | Service | 12/12/2025 | Not Relevant | Ex works | 1 | EA | 1 | 566833 | 566833
15441 | Fermi Frame 6B PGP - TO#4 - Switchgear and MCC Re-Purposing & Modernization | 11/20/2025 | Follow-Up Document Created | Switchgear and MCC Re-Purposing & Modernization | 2 | 15441 - 2 | 0255-F6B-020 | 0 | Major Equipment | Sent | 12/12/2025 11:24:25 CST | Shermco Systems Integration LLC | CPSO-0255-4-2 | GE VB1 -4.16-250-3 Breaker | 4160V Gear GE VB1 -4.16-250-3 Breaker (SN: 0351A3219-001-01) - Remanufacture GE VB1 -4.16-250-3 Breaker (SN: 0328A4658-001-01) - Remanufacture GE VB1 -4.16-250-3 Breaker (SN: 0328A4658-001-02) - Remanufacture | # | # | Not assigned | # | # | Not assigned | Material | 01/30/2026 | Not Delivered | Ex works | 2 | EA | 3 | 12495 | 37485
15441 | Fermi Frame 6B PGP - TO#4 - Switchgear and MCC Re-Purposing & Modernization | 11/20/2025 | Follow-Up Document Created | Switchgear and MCC Re-Purposing & Modernization | 3 | 15441 - 3 | 0255-F6B-020 | 0 | Major Equipment | Sent | 12/16/2025 12:11:51 CST | Shermco Systems Integration LLC | CPSO-0255-4-2 | GE Limit Amp Contactor | 4160V Gear GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : BFWP-2B) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : BFWP-3A) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : BFWP-2A) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : BFWP-1B) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : BFWP-3B) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : M687) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : M667) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : M666) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Cat #: 0551X0509B03 / Contactor ID : M686) - Limited Overhaul w/ Silver Plating GE Limit Amp Contactor (Catalog Number 0551X0509R02. Contactor | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Ex works | 3 | XPK | 14 | 8495 | 118930
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 1 | 15446 - 1 | - | 0 | Labor - Admin | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Procurement-Specialist | RPS Billable Title: Materials Manager (ST) | # | PROC0001 | Procurement-Specialist | # | # | Hour(s) | Service | 11/27/2025 | Not Relevant | N/A | 1 | EA | 1120 | 75 | 84000
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 2 | 15446 - 2 | - | 0 | Labor - Admin | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Procurement-Specialist | RPS Billable Title: Materials Manager (OT) | # | PROC0001 | Procurement-Specialist | # | # | Hour(s) | Service | 11/27/2025 | Not Relevant | N/A | 2 | EA | 896 | 112.5 | 100800
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 3 | 15446 - 3 | - | 0 | Expenses | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Contractor Per Diem Service | # | # | SVC000015 | Contractor Per Diem Service | # | # | Day(s) | Service | 11/27/2025 | Not Relevant | N/A | 3 | XPK | 360 | 178 | 64080
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 4 | 15446 - 4 | - | 0 | Labor - Admin | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Office Manager/Proc Support (ST) | RPS Billable Title: Office Manager (ST) | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 4 | EA | 1120 | 52 | 58240
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 5 | 15446 - 5 | - | 0 | Labor - Admin | Sent | 12/16/2025 12:18:09 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Office Manager/Proc Support (OT) | RPS Billable Title: Office Manager (OT) | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 5 | EA | 896 | 78 | 69888
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 6 | 15446 - 6 | - | 0 | Expenses | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | T&E Expenses | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/27/2025 | Not Relevant | N/A | 6 | EA | 0 | 0 | 50000
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 7 | 15446 - 7 | - | 0 | Labor - Admin | Follow-Up Document Created | 01/02/2026 11:35:13 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Mileage | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/27/2025 | Not Relevant | N/A | 7 | EA | 0 | 0 | 5000
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 8 | 15446 - 8 | - | 0 | Labor - Admin | Sent | 12/16/2025 12:18:09 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Office Clerk (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 8 | EA | 1120 | 43 | 48160
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 9 | 15446 - 9 | - | 0 | Labor - Admin | Sent | 12/16/2025 12:18:09 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Office Clerk (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 9 | EA | 896 | 67.5 | 60480
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 10 | 15446 - 10 | - | 0 | Labor - Admin | Sent | 12/16/2025 12:18:09 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Document Control Clerk (ST) | # | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 10 | EA | 1120 | 37 | 41440
15446 | Fermi Frame 6B PGP - TO#4 - Labor: Procurement, Office Personnel | 11/20/2025 | Follow-Up Document Created | TO#4 - Labor: Procurement, Office Personnel | 11 | 15446 - 11 | - | 0 | Labor - Admin | Sent | 12/16/2025 12:18:09 CST | Sigma Oilfield USA Inc | CPSO-0255-4-8 | Document Control Clerk (OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 11/27/2025 | Not Relevant | N/A | 11 | EA | 896 | 55.5 | 49728
15450 | Fermi Frame 6B PGP - TO#4 - Air Compressor Package | 11/21/2025 | Follow-Up Document Created | Air Compressor Package | 1 | 15450 - 1 | 0255-F6B-021 | 0 | Major Equipment | Follow-Up Document Created | 12/28/2025 16:41:08 CST | Atlas Copco Compressors, LLC | CPSO-0255-4-1 | Air Compressor Package | Plot Plan Item 43: Air Compressor Package Spec: P.02.03-ME-120-SPC-00001 Scope: Design, fabrication, and assembly of a fully engineered outdoor-rated compressed air skid. The skid will house the following Atlas Copco equipment: (2) ZT 90 Compressors (1) CD 530+ Dryer (2) 660-Gallon Air Receiver Tanks The system shall be constructed as a complete, self-contained compressed air package designed for continuous industrial service. All fabrication, electrical, and mechanical components shall meet or exceed applicable codes and standards. | # | # | Not assigned | # | # | Not assigned | Material | 01/30/2026 | Not Delivered | Free carrier | 1 | EA | 1 | 545408 | 545408
15450 | Fermi Frame 6B PGP - TO#4 - Air Compressor Package | 11/21/2025 | Follow-Up Document Created | Air Compressor Package | 2 | 15450 - 2 | 0255-F6B-021 | 0 | Major Equipment | Follow-Up Document Created | 12/28/2025 16:41:08 CST | Atlas Copco Compressors, LLC | CPSO-0255-4-1 | Atlas Copco Start-Up | # | # | # | Not assigned | # | # | Not assigned | Service | 01/30/2026 | Not Delivered | Free carrier | 2 | EA | 1 | 1800 | 1800
15450 | Fermi Frame 6B PGP - TO#4 - Air Compressor Package | 11/21/2025 | Follow-Up Document Created | Air Compressor Package | 3 | 15450 - 3 | 0255-F6B-021 | 0 | Freight | Follow-Up Document Created | 12/28/2025 16:41:08 CST | Atlas Copco Compressors, LLC | CPSO-0255-4-1 | Freight | # | # | # | Not assigned | # | # | Not assigned | Service | 01/30/2026 | Not Relevant | Free carrier | 3 | XPK | 1 | 3500 | 3500
15460 | Fermi Frame 6B PGP - TO#4 - Plant Cathodic Protection Design | 11/21/2025 | Not Yet Acknowledged | Plant Cathodic Protection Design | 1 | 15460 - 1 | 0255-F6B-022 | 0 | Major Equipment | Not Yet Acknowledged | 11/25/2025 13:01:04 CST | Corrpro Companies, Inc | CPSO-0255-4-4 | Plant Cathodic Protection Design | Task 1: Document Review and Project Preparation Activities • Review and identify proposed pipeline locations. • Identify pipeline characteristics and appurtenances including any planned HDDs and Bores. • Determine design preferences, requirements, and specifications. • Constructability assessment. Task 2: Data Analysis and CP Design Submittal • Analysis of field data that is to be provided to Corrpro. • Current requirement calculations. • Basis of design. • Preparation of deliverables. Task 3: Cathodic Protection Deliverables • CP design recommendations • Test station schedule • Detailed design drawings, equipment location schedules, and bill of materials. | # | # | Not assigned | # | # | Not assigned | Service | 11/28/2025 | Not Relevant | N/A | 1 | EA | 1 | 30750 | 30750
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 1 | 15461 - 1 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | U/G Piping BOM (11/07/25) | # | # | # | Not assigned | # | # | Not assigned | Material | 12/12/2025 | Not Delivered | Ex works | 1 | EA | 1 | 0.01 | 0.01
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 2 | 15461 - 2 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1" PIPE, XS, PE, CS | 1" PIPE, XS, PE, CS, SMLS, ASTM A53-B, TYPE S | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 2 | EA | 1440 | 11.6 | 16704
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 3 | 15461 - 3 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" PIPE, SDR-11, PE, HDPE | 1.5" PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 3 | XPK | 1000 | 1.84 | 1840
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 4 | 15461 - 4 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" PIPE, SEAMLESS, 1 1/2" ND | 1.5" PIPE, SEAMLESS, 1 1/2" ND, PE, ASME B36.19 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 4 | EA | 680 | 14.27 | 9703.6
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 5 | 15461 - 5 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" PIPE, XS, BE, CS, SMLS | 2" PIPE, XS, BE, CS, SMLS, ASTM A53-B, TYPE S | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 5 | EA | 300 | 14.44 | 4332
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 6 | 15461 - 6 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" PIPE, SDR-11, PE, HDPE, ASTM | 2" PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 6 | EA | 1500 | 1.71 | 2565
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 7 | 15461 - 7 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" PIPE, SDR-11, PE, HDPE, ASTM | 3" PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 7 | EA | 1500 | 3.08 | 4620
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 8 | 15461 - 8 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" PIPE, SDR-11, PE, HDPE, ASTM | 6" PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 8 | EA | 1520 | 9.57 | 14546.4
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 9 | 15461 - 9 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" PIPE, STD, BE, CS, ERW, ASTM | 6" PIPE, STD, BE, CS, ERW, ASTM A53-B, TYPE E (Ej=0.85) | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 9 | EA | 40 | 112 | 4480
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 10 | 15461 - 10 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" PIPE, SDR-11, PE, HDPE, ASTM | 8"PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 10 | EA | 40 | 14.7 | 588
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 11 | 15461 - 11 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" PIPE, SDR-11, PE, HDPE | 10" PIPE, SDR-11, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM F714 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 11 | EA | 80 | 22.79 | 1823.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 12 | 15461 - 12 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" PIPE, STD, BE, CS, ERW | 10"PIPE, STD, BE, CS, ERW, ASTM A53-B, TYPE E (Ej=0.85) | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 12 | EA | 40 | 199.23 | 7969.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 13 | 15461 - 13 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" FLANGE BLIND, CLASS 150 | 6" FLANGE BLIND, CLASS 150, RF, CS, ASTM A105, ASME B16.5 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 13 | EA | 22 | 44.76 | 984.72
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 14 | 15461 - 14 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" FLANGE BLIND, CLASS 150 | 10" FLANGE BLIND, CLASS 150, RF, CS, ASTM A105, ASME B16.5 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 14 | EA | 1 | 148 | 148
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 15 | 15461 - 15 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1" COUPLING, CLASS 3000 | 1" COUPLING, CLASS 3000, SW, CS, ASTM A105, ASME B16.11 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 15 | EA | 6 | 5.98 | 35.88
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 16 | 15461 - 16 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" UNION, 1 1/2" ND | 1.5" UNION, 1 1/2" ND, 3000 LB, FPT, MSS-SP-83 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 16 | EA | 25 | 34.25 | 856.25
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 17 | 15461 - 17 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1" 90 ELL, CLASS 3000, SW | 1" 90 ELL, CLASS 3000, SW, CS, ASTM A105, ASME B16.11 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 17 | EA | 39 | 9.98 | 389.22
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 18 | 15461 - 18 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1" 45 ELL, CLASS 3000, SW | 1" 45 ELL, CLASS 3000, SW, CS, ASTM A105, ASME B16.11 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 18 | EA | 2 | 13.45 | 26.9
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 19 | 15461 - 19 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" ELL 90, 1 1/2" ND | 1.5" ELL 90, 1 1/2" ND, 3000 LB, FPT, ASME B16.11 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 19 | EA | 32 | 31.65 | 1012.8
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 20 | 15461 - 20 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" 90 ELL, MOLDED, 200 PSI, PE | 1.5" 90 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 20 | EA | 2 | 9.7 | 19.4
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 21 | 15461 - 21 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 90 LR ELL, XS, BW | 2" 90 LR ELL, XS, BW, CS, ASTM A234-WPB-S, ASME B16.9 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 21 | EA | 20 | 9.12 | 182.4
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 22 | 15461 - 22 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 45 ELL, FABRICATED | 2" 45 ELL, FABRICATED, 3-SEGMENT, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 22 | EA | 7 | 11.12 | 77.84
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 23 | 15461 - 23 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 90 ELL, MOLDED, 200 PSI, PE | 2" 90 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 23 | EA | 19 | 10.87 | 206.53
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 24 | 15461 - 24 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 45 LR ELL, XS, BW | 2" 45 LR ELL, XS, BW, CS, ASTM A234-WPB-S, ASME B16.9 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 24 | EA | 2 | 6.63 | 13.26
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 25 | 15461 - 25 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" 90 ELL, MOLDED, 200 PSI | 3" 90 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 25 | EA | 7 | 18.76 | 131.32
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 26 | 15461 - 26 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 90 ELL, MOLDED, 200 PSI | 6" 90 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 26 | EA | 29 | 51.69 | 1499.01
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 27 | 15461 - 27 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 45 ELL, MOLDED, 200 PSI | 6" 45 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 27 | EA | 9 | 51.69 | 465.21
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 28 | 15461 - 28 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 45 ELL, FABRICATED, 3-SEG | 6" 45 ELL, FABRICATED, 3-SEGMENT, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 28 | EA | 6 | 51.69 | 310.14
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 29 | 15461 - 29 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 90 LR ELL, STD, BW | 6" 90 LR ELL, STD, BW, CS, ASTM A234-WPB-W, ASME B16.9 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 29 | EA | 6 | 68.63 | 411.78
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 30 | 15461 - 30 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" 90 ELL, MOLDED, 200 PSI | 8" 90 ELL, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 30 | EA | 21 | 137.51 | 2887.71
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 31 | 15461 - 31 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" 90 LR ELL, SCH 80, BW | 10" 90 LR ELL, SCH 80, BW, CS, ASTM A234-WPB-S, ASME B16.9 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 31 | EA | 3 | 261.25 | 783.75
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 32 | 15461 - 32 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" PIPE NIPPLE, LONG TYPE | 1.5" PIPE NIPPLE, LONG TYPE, 1 1/2" ND, TBE, 3" LG | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 32 | EA | 18 | 23.15 | 416.7
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 33 | 15461 - 33 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8x6" REDUCER (CONC), MOLDED | 8x6" REDUCER (CONC), MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 33 | EA | 4 | 100.55 | 402.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 34 | 15461 - 34 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2x1" SWAGE (CONC), XS, BLE | 2x1" SWAGE (CONC), XS, BLE X PSE, CS, SMLS, ASTM A234-WPB-S, MSS SP-95 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 34 | EA | 2 | 75 | 150
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 35 | 15461 - 35 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" TEE, MOLDED, 200 PSI, | 1.5" TEE, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 35 | EA | 5 | 12.39 | 61.95
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 36 | 15461 - 36 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" TEE, XS, BW, CS | 2" TEE, XS, BW, CS, ASTM A234-WPB-S, ASME B16.9 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 36 | EA | 21 | 15.25 | 320.25
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 37 | 15461 - 37 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" TEE, 2" ND, CL 200 | 2" TEE, 2" ND, CL 200, HDPE, PE, IPS, FM MOLDED | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 37 | EA | 6 | 13.3 | 79.8
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 38 | 15461 - 38 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" TEE, 3" ND, CL 200 | 3" TEE, 3" ND, CL 200, HDPE, PE, IPS, FM MOLDED | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 38 | EA | 6 | 21.27 | 127.62
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 39 | 15461 - 39 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" TEE, MOLDED, 200 PSI, PE | 6" TEE, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 39 | EA | 11 | 100.69 | 1107.59
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 40 | 15461 - 40 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6x2x6" SADDLE, 200 PSI, PE | 6x2x6" SADDLE, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 40 | EA | 35 | 165.67 | 5798.45
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 41 | 15461 - 41 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" TEE, MOLDED, 200 PSI, PE | 8" TEE, MOLDED, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 41 | EA | 5 | 179.1 | 895.5
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 42 | 15461 - 42 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10x6x10" SADDLE, 200 PSI, PE | 10x6x10" SADDLE, 200 PSI, PE, HDPE, ASTM D3350 CLASS PE445574C GRADE PE4710 TO ASTM D3261 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 42 | EA | 30 | 589.55 | 17686.5
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 43 | 15461 - 43 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1.5" BACK UP RING, CLASS 150 | 1.5" BACK UP RING, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12 FOR USE W/HDPE FLANGE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 43 | EA | 10 | 26.87 | 268.7
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 44 | 15461 - 44 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" BACK UP RING, CLASS 150 | 2" BACK UP RING, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12 FOR USE W/HDPE FLANGE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 44 | EA | 18 | 27.39 | 493.02
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 45 | 15461 - 45 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 22:34:04 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" BACK UP RING, CLASS 150 | 3" BACK UP RING, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12 FOR USE W/HDPE FLANGE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 45 | EA | 1 | 40.3 | 40.3
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 46 | 15461 - 46 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" FLANGE LAP JOINT, CLASS 150 | 6" FLANGE LAP JOINT, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12, ASME B16.42 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 46 | EA | 2 | 134.33 | 268.66
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 47 | 15461 - 47 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" BACK UP RING, CLASS 150 | 6" BACK UP RING, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12 FOR USE W/HDPE FLANGE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 47 | EA | 24 | 74.63 | 1791.12
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 48 | 15461 - 48 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" FLANGE LAP JOINT, CLASS 150 | 8" FLANGE LAP JOINT, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12, ASME B16.42 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 48 | EA | 192 | 119.37 | 22919.04
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 49 | 15461 - 49 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" BACK UP RING, CLASS 150 | 8" BACK UP RING, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12 FOR USE W/HDPE FLANGE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 49 | EA | 24 | 116.06 | 2785.44
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 50 | 15461 - 50 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" FLANGE LAP JOINT, CLASS150 | 10" FLANGE LAP JOINT, CLASS 150, DI, ASTM A536, GRADE RANGE 60/40/18 TO 65/45/12, ASME B16.42 | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 50 | EA | 6 | 276.12 | 1656.72
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 51 | 15461 - 51 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 5/8x3.25" STUD BOLT, ASTM A307 | 5/8x3.25" STUD BOLT, ASTM A307, GR B WITH ASTM A563, GR A HEAVY HEX NUTS AND USS 18-8 SS FLAT WASHERS | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 51 | EA | 19 | 6.25 | 118.75
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 52 | 15461 - 52 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 22:56:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3/4x5" STUD BOLT, ASTM A307 | 3/4x5" STUD BOLT, ASTM A307, GR B WITH ASTM A563, GR A HEAVY HEX NUTS AND USS 18-8 SS FLAT WASHERS | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 52 | EA | 5 | 9.15 | 45.75
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 53 | 15461 - 53 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" PIPE, XS, BE, CS, SMLS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 53 | EA | 540 | 13 | 7020
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 54 | 15461 - 54 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" PIPE, STD, BE, CS, ERW | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 54 | EA | 40 | 50.67 | 2026.8
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 55 | 15461 - 55 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" PIPE, STD, BE, CS, ERW, | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 55 | EA | 240 | 31.83 | 7639.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 56 | 15461 - 56 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" PIPE, SCH 80, BE, CS, SMLS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 56 | EA | 1480 | 96 | 142080
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 57 | 15461 - 57 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" PIPE, SDR-11, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 57 | EA | 1050 | 14.7 | 15435
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 58 | 15461 - 58 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" PIPE, SDR-11, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 58 | EA | 1200 | 22.75 | 27300
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 59 | 15461 - 59 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 45 ELL, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 59 | EA | 10 | 51.69 | 516.9
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 60 | 15461 - 60 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" 90 ELL, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 60 | EA | 8 | 137.51 | 1100.08
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 61 | 15461 - 61 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" 90 ELL, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 61 | EA | 23 | 18.76 | 431.48
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 62 | 15461 - 62 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 90 ELL, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 62 | EA | 25 | 10.87 | 271.75
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 63 | 15461 - 63 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1 1/2" 90 ELL, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 63 | EA | 25 | 9.7 | 242.5
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 64 | 15461 - 64 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 22:34:04 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" BACK UP RING, CLASS 150, DI | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 64 | EA | 4 | 40.3 | 161.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 65 | 15461 - 65 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" BACK UP RING, CLASS 150, DI | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 65 | EA | 9 | 27.39 | 246.51
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 66 | 15461 - 66 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1 1/2" BACK UP RING, CLASS 150, DI | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 66 | EA | 1 | 26.87 | 26.87
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 67 | 15461 - 67 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3" FLANGE ADAPTER, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 67 | EA | 4 | 0.01 | 0.04
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 68 | 15461 - 68 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" FLANGE ADAPTER, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 68 | EA | 9 | 0.01 | 0.09
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 69 | 15461 - 69 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1 1/2" FLANGE ADAPTER, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 69 | EA | 1 | 0.01 | 0.01
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 70 | 15461 - 70 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" FLANGE LAP JOINT, CLASS 150, DI | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 70 | EA | 13 | 74.63 | 970.19
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 71 | 15461 - 71 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8x6" REDUCER (CONC), 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 71 | EA | 2 | 100.55 | 201.1
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 72 | 15461 - 72 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 8" TEE, MOLDED, 200 PSI, PE, HDPE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 72 | EA | 1 | 179.1 | 179.1
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 73 | 15461 - 73 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 90 LR ELL, XS, BW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 73 | EA | 20 | 7.01 | 140.2
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 74 | 15461 - 74 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2" 90 LR ELL, XS, BW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 74 | EA | 1 | 7.01 | 7.01
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 75 | 15461 - 75 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 1" COUPLING, CLASS 3000, SW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 75 | EA | 59 | 4.67 | 275.53
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 76 | 15461 - 76 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 2x1" SWAGE (CONC), XS, BLEXPSE, CS, SMLS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 76 | EA | 19 | 88.57 | 1682.83
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 77 | 15461 - 77 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" 90 LR ELL, STD, BW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 77 | EA | 1 | 65.88 | 65.88
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 78 | 15461 - 78 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" 90 LR ELL, STD, BW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 78 | EA | 3 | 249.96 | 749.88
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 79 | 15461 - 79 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" 90 LR ELL, SCH 80, BW, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 79 | EA | 3 | 451.12 | 1353.36
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 80 | 15461 - 80 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" FLANGE BLIND, CLASS 150, RF, CS | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 80 | EA | 1 | 126.8 | 126.8
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 81 | 15461 - 81 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" GASKET, 1/8" THICK PTFE, FULL FACE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 81 | EA | 17 | 116.67 | 1983.39
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 82 | 15461 - 82 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" GASKET, 1/8" THICK PTFE, FULL FACE | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 82 | EA | 1 | 255 | 255
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 83 | 15461 - 83 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" GASKET, CLASS 150, SPIRAL-WOUND | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 83 | EA | 5 | 14.29 | 71.45
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 84 | 15461 - 84 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 10" GASKET, CLASS 150, SPIRAL-WOUND | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 84 | EA | 1 | 31.67 | 31.67
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 85 | 15461 - 85 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 6" GATE VALVE, 150 LB, RF | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 85 | EA | 6 | 0.01 | 0.06
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 86 | 15461 - 86 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 7/8x4 1/2" STUD BOLT, ASTM A193-B7 | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 86 | EA | 12 | 7 | 84
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 87 | 15461 - 87 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3/4x4" STUD BOLT, ASTM A193-B7 | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 87 | EA | 40 | 5.49 | 219.6
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 88 | 15461 - 88 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Sent | 12/31/2025 15:36:46 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 7/8x4 1/2" STUD BOLT, ASTM A307 | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 88 | FOT | 12 | 7 | 84
15461 | Fermi Frame 6B PGP - TO#4 - U/G Piping BOM (11/07/25) | 11/21/2025 | Follow-Up Document Created | U/G Piping BOM (11/07/25) | 89 | 15461 - 89 | 0255-F6B-023A,B,C | 0 | Bulks - Piping | Follow-Up Document Created | 01/02/2026 13:04:19 CST | Magnatex Pumps, Inc. | CPSO-0255-4-4 | 3/4x4" STUD BOLT, ASTM A307, GR B | # | # | # | Not assigned | # | # | Not assigned | Material | 12/03/2025 | Not Delivered | Ex works | 89 | EA | 136 | 5.49 | 746.64
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 1 | 15462 - 1 | 0255-F6B-024 | 0 | Major Equipment | Follow-Up Document Created | 01/02/2026 10:42:45 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Glycol CW Pump (WSAC) (P-200A/B) | PUMP MODEL: 3596X 8X10-13 WCB-21 | # | # | Not assigned | # | # | Not assigned | Material | 12/29/2025 | Not Delivered | Ex works | 1 | EA | 2 | 47580 | 95160
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 2 | 15462 - 2 | 0255-F6B-024 | 0 | Major Equipment | Follow-Up Document Created | 01/02/2026 10:42:45 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Waste Water Pumps (WSAC) (P-201A/B) | PUMP MODEL: 3596M 1.5X3-13 316-21 | # | # | Not assigned | # | # | Not assigned | Material | 01/07/2026 | Not Delivered | Ex works | 2 | EA | 2 | 13820 | 27640
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 3 | 15462 - 3 | 0255-F6B-024 | 0 | Major Equipment | Follow-Up Document Created | 01/02/2026 10:42:45 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Demin Water Pumps (P-400A/B) | PUMP MODEL: 3596M 2X3-13 316-22 | # | # | Not assigned | # | # | Not assigned | Material | 01/07/2026 | Not Delivered | Ex works | 3 | XPK | 2 | 16750 | 33500
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 4 | 15462 - 4 | 0255-F6B-024 | 0 | Major Equipment | Follow-Up Document Created | 01/02/2026 10:42:45 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Service Water Pumps (P-600A/B) | PUMP MODEL: 3596M 3X4-13 WCB-21 | # | # | Not assigned | # | # | Not assigned | Material | 01/07/2026 | Not Delivered | Ex works | 4 | EA | 2 | 17055 | 34110
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 5 | 15462 - 5 | 0255-F6B-024 | 0 | Major Equipment | Sent | 12/02/2025 06:07:02 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Sump Pumps (P-101/102/103) | INCLUDES OPTIONAL METAL MUFFLER AND SOLENOID KIT FOR 24VDC EXP COIL PUMP MODEL: S15B1ABAARS6E1 | # | # | Not assigned | # | # | Not assigned | Material | 12/29/2025 | Not Delivered | Ex works | 5 | EA | 3 | 5241 | 15723
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 6 | 15462 - 6 | 0255-F6B-024 | 0 | Major Equipment | Sent | 12/29/2025 10:15:41 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Ammonia Inj Pump (P-1301/2301/3301) | INCLUDES OPTIONAL METAL MUFFLER AND SOLENOID KIT FOR 24VDC EXP COIL PUMP MODEL: S15B1ABAARS6E1 | # | # | Not assigned | # | # | Not assigned | Material | 01/07/2026 | Not Delivered | Ex works | 6 | EA | 3 | 5241 | 15723
15462 | Fermi Frame 6B PGP - TO#4 - Pumps | 11/21/2025 | Follow-Up Document Created | Pumps | 7 | 15462 - 7 | 0255-F6B-024 | 0 | Major Equipment | Sent | 12/31/2025 11:31:09 CST | Magnatex Pumps, Inc. | CPSO-0255-4-1 | Waste Water Pumps (P-300A/B) | PUMP MODEL: 3596M 3X4-8 316-14 | # | # | Not assigned | # | # | Not assigned | Material | 01/07/2026 | Not Delivered | Ex works | 7 | EA | 2 | 13330 | 26660
15463 | Fermi Frame 6B PGP - TO#4 - Tools & Consumables | 11/22/2025 | Follow-Up Document Created | Tools & Consumables | 1 | 15463 - 1 | 0255-F6B-025 | 0 | Consumables, Tooling | Follow-Up Document Created | 12/12/2025 11:06:34 CST | Momentum Rental and Sales | CPSO-0255-4-9 | Consumables | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/29/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 20000
15463 | Fermi Frame 6B PGP - TO#4 - Tools & Consumables | 11/22/2025 | Follow-Up Document Created | Tools & Consumables | 2 | 15463 - 2 | 0255-F6B-025 | 0 | Consumables, Tooling | Finished | 01/03/2026 08:11:59 CST | Momentum Rental and Sales | CPSO-0255-4-9 | General Tooling | # | # | # | Not assigned | # | # | Not assigned | Limit | 11/29/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 30000
15464 | Fermi Frame 6B PGP - TO#4 - (4) 40' HC Used Shipping/Storage Containers | 11/22/2025 | Finished | (4) 40' HC Used Shipping/Storage Containers | 1 | 15464 - 1 | 0255-F6B-026 | 0 | Facilities - Laydown | Finished | 12/21/2025 15:17:30 CST | West Gulf Containers LLC. | CPSO-0255-4-9 | 40' HC Used Shipping Container | # | # | # | Not assigned | # | # | Not assigned | Material | 11/29/2025 | Delivered | Free carrier | 1 | EA | 6 | 2150 | 12900
15464 | Fermi Frame 6B PGP - TO#4 - (4) 40' HC Used Shipping/Storage Containers | 11/22/2025 | Finished | (4) 40' HC Used Shipping/Storage Containers | 2 | 15464 - 2 | 0255-F6B-026 | 0 | Facilities - Laydown | Finished | 12/21/2025 15:17:30 CST | West Gulf Containers LLC. | CPSO-0255-4-9 | Delivery to site | # | # | # | Not assigned | # | # | Not assigned | Service | 11/29/2025 | Not Relevant | Free carrier | 2 | EA | 4 | 1200 | 4800
15464 | Fermi Frame 6B PGP - TO#4 - (4) 40' HC Used Shipping/Storage Containers | 11/22/2025 | Finished | (4) 40' HC Used Shipping/Storage Containers | 3 | 15464 - 3 | 0255-F6B-026 | 0 | Facilities - Laydown | Finished | 12/21/2025 15:17:30 CST | West Gulf Containers LLC. | CPSO-0255-4-9 | Delivery to site | # | # | # | Not assigned | # | # | Not assigned | Service | 11/29/2025 | Not Relevant | Free carrier | 3 | XPK | 2 | 1200 | 2400
15492 | Fermi Frame 6B PGP - TO#4 - Bottled Water/Ice Supply | 11/25/2025 | Follow-Up Document Created | Bottled Water/Ice Supply | 1 | 15492 - 1 | 0255-F6B-043 | 0 | Facilities - Botled Water | Follow-Up Document Created | 01/04/2026 15:23:59 CST | AquaOne, Inc | CPSO-0255-4-9 | Bottled Water | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/02/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 20000
15492 | Fermi Frame 6B PGP - TO#4 - Bottled Water/Ice Supply | 11/25/2025 | Follow-Up Document Created | Bottled Water/Ice Supply | 2 | 15492 - 2 | 0255-F6B-043 | 0 | Facilities - Botled Water | Sent | 11/25/2025 22:30:21 CST | AquaOne, Inc | CPSO-0255-4-9 | Ice | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/02/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 7000
15496 | Fermi Frame 6B PGP - TO#4 - Concrete Supply | 11/25/2025 | Follow-Up Document Created | Concrete Supply | 1 | 15496 - 1 | - | 0 | Civil - Aggregates | Follow-Up Document Created | 12/06/2025 15:35:00 CST | Amarillo Redi-Mix, LLC | CPSO-0255-4-9 | 4000 psi Concrete ($155.00/yard) | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/02/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 400000
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 1 | 15510 - 1 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | CONTROL VALVE-LESLIE, 1”-600#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 1 | EA | 1 | 762 | 762
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 2 | 15510 - 2 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | CONTROL VALVE-ROBERT SHAW, 2”-150#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 2 | EA | 1 | 762 | 762
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 3 | 15510 - 3 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | CONTROL VALVE-ROBERT SHAW, 3”-150#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 3 | XPK | 5 | 762 | 3810
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 4 | 15510 - 4 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | CONTROL VALVE-ROBERT SHAW, 4”-150#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 4 | EA | 3 | 762 | 2286
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 5 | 15510 - 5 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | REGULATOR-FISHER, 1”-150#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 5 | EA | 3 | 649 | 1947
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 6 | 15510 - 6 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | REGULATOR-FISHER, 2”-300#RF | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 6 | EA | 3 | 723 | 2169
15510 | Fermi Frame 6B PGP - TO#4 - IMTT Control Valves Inspection and Refurbishment | 11/28/2025 | Sent | IMTT Control Valves Inspection and Refurbishment | 7 | 15510 - 7 | 0255-F6B-027 | 0 | Refurb | Sent | 11/28/2025 15:12:39 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | PILOT VALVE-CROSBY, 2” X 3” | # | # | # | Not assigned | # | # | Not assigned | Service | 12/05/2025 | Not Relevant | Ex works | 7 | EA | 3 | 464 | 1392
15511 | Fermi Frame 6B PGP - TO#4 - Lunch Tent Rental | 11/28/2025 | Follow-Up Document Created | Lunch Tent Rental | 1 | 15511 - 1 | - | 0 | Equipment Rental - Tent | Acknowledgement Received | 12/29/2025 14:13:00 CST | United Rentals | CPSO-0255-4-9 | HVAC Rental | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/08/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 80000
15511 | Fermi Frame 6B PGP - TO#4 - Lunch Tent Rental | 11/28/2025 | Follow-Up Document Created | Lunch Tent Rental | 2 | 15511 - 2 | - | 0 | Equipment Rental - Tent | Follow-Up Document Created | 12/29/2025 14:19:37 CST | United Rentals | CPSO-0255-4-9 | Lunch Tent Rental BT20/400 (65.6'x32.8') | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/08/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 70000
15511 | Fermi Frame 6B PGP - TO#4 - Lunch Tent Rental | 11/28/2025 | Follow-Up Document Created | Lunch Tent Rental | 3 | 15511 - 3 | - | 0 | Equipment Rental - Tent | Follow-Up Document Created | 12/29/2025 14:19:37 CST | United Rentals | CPSO-0255-4-9 | Delivery and Installation | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/08/2025 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 90000
15575 | Fermi Frame 6B PGP - TO#4: Construction Supplies | 12/04/2025 | Follow-Up Document Created | TO#4: Construction Supplies | 1 | 15575 - 1 | 0255-F6B-028 | 0 | Consumables, Tooling | Follow-Up Document Created | 12/28/2025 14:26:04 CST | WT Supply Company LLC | CPSO-0255-4-9 | Construction Supplies | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/11/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 150000
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 1 | 15582 - 1 | 0255-F6B-029 | 0 | Major Equipment | Sent | 12/16/2025 12:15:39 CST | Lynn Energy Services | CPSO-0255-4-1 | BOP PLC-100 Panel | - Provision of all Panel Components - Assembly and Wiring for the Panel - Perform In-House FAT Verification Test of the Panel assembly - Assist RPS performed Panel Functional Test Tag# PLC-50591 Drwg: 12224A25-120-IN-2000, 2001, 2002, 2003 | # | # | Not assigned | # | # | Not assigned | Material | 01/22/2026 | Not Delivered | Free on board | 1 | EA | 1 | 246235 | 246235
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 2 | 15582 - 2 | 0255-F6B-029 | 0 | Major Equipment | Sent | 12/16/2025 12:15:39 CST | Lynn Energy Services | CPSO-0255-4-2 | BOP NETWORK CABINET | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 2 | EA | 1 | 92871 | 92871
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 3 | 15582 - 3 | 0255-F6B-029 | 0 | Major Equipment | Sent | 12/16/2025 12:15:39 CST | Lynn Energy Services | CPSO-0255-4-2 | BOP RIO 100 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 3 | XPK | 1 | 151182 | 151182
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 4 | 15582 - 4 | 0255-F6B-029 | 0 | Major Equipment | Sent | 12/16/2025 12:15:39 CST | Lynn Energy Services | CPSO-0255-4-2 | BOP SERVER CABINET | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 4 | EA | 1 | 86616 | 86616
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 5 | 15582 - 5 | - | 0 | Major Equipment | Canceled | 12/23/2025 19:25:24 CST | Lynn Energy Services | CPSO-0255-4-2 | TURB PLC 100 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Relevant | Free on board | 5 | EA | 1 | 198247 | 198247
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 6 | 15582 - 6 | - | 0 | Major Equipment | Canceled | 12/23/2025 19:25:24 CST | Lynn Energy Services | CPSO-0255-4-2 | TURB RIO 100 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Relevant | Free on board | 6 | EA | 1 | 71676 | 71676
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 7 | 15582 - 7 | - | 0 | Major Equipment | Canceled | 12/23/2025 19:25:24 CST | Lynn Energy Services | CPSO-0255-4-2 | TURB RIO 101 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Relevant | Free on board | 7 | EA | 1 | 89328 | 89328
15582 | Fermi Frame 6B PGP - TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 12/04/2025 | Sent | TO#4: BOP PLC Cabinet, BOP Network Cabinet, BOP RIO 100 Panel, and OP Server Cabinet | 8 | 15582 - 8 | #N/A | #N/A | #N/A | Sent | 12/27/2025 17:15:22 CST | Lynn Energy Services | CPSO-0255-4-2 | Change Processor 1756-L81E to 1756-L85EP | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 8 | EA | 2 | 25535.14 | 51070.28
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 1 | 15605 - 1 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG2A2B21AS5B4Y2Q4M5 PIT-100 PIT-110 PIT-200 PIT-201 PIT-202 PIT-203 PIT-204 PIT-205 PIT-206 PIT-207 PIT-210 PIT-210 PIT-230 PIT-310 PIT-401 PIT-402 PIT-403 PIT-404 PIT-411 PIT-412 PIT-413 PIT-501 PIT-601 PIT-603 PIT-612 PIT-613 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 1 | EA | 22 | 3383.32 | 74433.04
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 2 | 15605 - 2 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 2 | EA | 22 | 367.48 | 8084.56
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 3 | 15605 - 3 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG3A2B21AS5B4Y2Q4M5 PIT-602 PIT-604 PIT-1102 PIT-2102 PIT-3102 PIT-5010 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 3 | XPK | 6 | 3383.32 | 20299.92
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 4 | 15605 - 4 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 4 | EA | 6 | 367.48 | 2204.88
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 5 | 15605 - 5 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG4A2B21AS5B4Y2Q4M5 PIT-940 PIT-941 PIT-942 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 5 | EA | 3 | 3383.32 | 10149.96
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 6 | 15605 - 6 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Relevant | Ex works | 6 | EA | 3 | 367.48 | 1102.44
15605 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/05/2025 | Canceled | TO#4: Plant Instrumentation | 7 | 15605 - 7 | #N/A | #N/A | #N/A | Canceled | 12/16/2025 07:00:40 CST | Emerson Process Management | CPSO-0255-4-2 | IMP-TARIFF-M:SURCHARGE | # | # | # | Not assigned | # | # | Not assigned | Service | 12/12/2025 | Not Relevant | Ex works | 7 | EA | 1 | 6278.84 | 6278.84
15608 | Fermi: Hot water pressure washer (Online order) | 12/08/2025 | Finished | # | 1 | 15608 - 1 | 0255-F6B-044 | 0 | Tooling | Finished | 12/29/2025 08:33:13 CST | CREDIT CARD- CC | CPSO-0255-4-1 | KOHLER Hot Water Pressure Washer | # | # | # | Not assigned | # | # | Not assigned | Material | 12/17/2025 | Delivered | Delivered at place | 1 | EA | 1 | 4599 | 4599
15639 | Fermi Frame 6B PGP - TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 12/09/2025 | Sent | TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 1 | 15639 - 1 | 0255-CC-030 | 0 | Refurb | Sent | 12/10/2025 14:59:37 CST | SULZER PUMP SERVICES (US) INC | CPSO-0255-4-2 | Boiler FW Pump Inspection/Refurbishment | Sulzer Bingham 3X6X9 13 Stage MSD Boiler Feed Pump Shop: 11521 Industriplex Blvd Baton Rouge, LA 70809 Job #: 1006911908, 100611909, 100611910 | # | # | Not assigned | # | # | Not assigned | Service | 12/02/2025 | Not Relevant | Ex works | 1 | EA | 3 | 12500 | 37500
15639 | Fermi Frame 6B PGP - TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 12/09/2025 | Sent | TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 2 | 15639 - 2 | 0255-CC-030 | 0 | Refurb | Sent | 12/10/2025 14:59:37 CST | SULZER PUMP SERVICES (US) INC | CPSO-0255-4-2 | Boiler FW Pump Inspection/Refurbishment | Sulzer Bingham 3X6X9 13 Stage MSD Boiler Feed Pump Shop: 340 S. Meadow, Odessa TX 79761 Job #: 100612235, 100612000 | # | # | Not assigned | # | # | Not assigned | Service | 12/02/2025 | Not Relevant | Ex works | 2 | EA | 2 | 12500 | 25000
15639 | Fermi Frame 6B PGP - TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 12/09/2025 | Sent | TO# Combined Cycle: IMTT BFW Pumps Refurbishment | 3 | 15639 - 3 | 0255-CC-030 | 0 | Refurb | Sent | 12/10/2025 14:59:37 CST | SULZER PUMP SERVICES (US) INC | CPSO-0255-4-2 | Baseplate | Duplicate per original skid (CS) | # | # | Not assigned | # | # | Not assigned | Material | 12/02/2025 | Not Relevant | Ex works | 3 | XPK | 5 | 28963.95 | 144819.75
15640 | Fermi Frame 6B PGP - TO#4 - Pipe Rack Helical Piles | 12/09/2025 | Follow-Up Document Created | TO#4 - Pipe Rack Helical Piles Change Orders | 1 | 15640 - 1 | - | 0 | Labor - Civil | Finished | 01/03/2026 11:09:14 CST | Audubon Companies, LLC. | CPSO-0255-4-9 | Pipe Rack Helical Piles (8) | Predrilling, helical pile, and concrete pedestal. Design, supply and install Eight (8) piles and associated caps across the facility for support of pipe rack and other structures. ACS scope also includes concrete pedestals after the helicals have been installed. | # | # | Not assigned | # | # | Not assigned | Service | 12/16/2025 | Not Relevant | N/A | 1 | EA | 1 | 42752 | 42752
15640 | Fermi Frame 6B PGP - TO#4 - Pipe Rack Helical Piles | 12/09/2025 | Follow-Up Document Created | TO#4 - Pipe Rack Helical Piles Change Orders | 2 | 15640 - 2 | - | 0 | Labor - Civil | Finished | 01/03/2026 11:09:14 CST | Audubon Companies, LLC. | CPSO-0255-4-9 | Anchor Bolts | Anchor Bolts (48) 5/8” dia x 1’-10” long (18) ¾” dia x 2’-0” long | # | # | Not assigned | # | # | Not assigned | Material | 12/16/2025 | Delivered | N/A | 2 | EA | 1 | 2849 | 2849
15640 | Fermi Frame 6B PGP - TO#4 - Pipe Rack Helical Piles | 12/09/2025 | Follow-Up Document Created | TO#4 - Pipe Rack Helical Piles Change Orders | 3 | 15640 - 3 | #N/A | #N/A | #N/A | Follow-Up Document Created | 01/02/2026 12:32:04 CST | Audubon Companies, LLC. | CPSO-0255-4-9 | CO - Added 2 piles | Due to the nature of the Piperack moving, the Engineers added two piles on the west end to tie the project together. This change order includes all of the labor, material, and time to complete the additional (2). | # | # | Not assigned | # | # | Not assigned | Material | 12/16/2025 | Not Delivered | N/A | 3 | XPK | 1 | 11219 | 11219
15640 | Fermi Frame 6B PGP - TO#4 - Pipe Rack Helical Piles | 12/09/2025 | Follow-Up Document Created | TO#4 - Pipe Rack Helical Piles Change Orders | 4 | 15640 - 4 | #N/A | #N/A | #N/A | Follow-Up Document Created | 01/02/2026 12:32:04 CST | Audubon Companies, LLC. | CPSO-0255-4-9 | CO - Shift in elevation | (4) sections of Sonotube for the additional length needed to build the pedestals up to the correct elevation. Additional Concrete considered for the 1.5' extra length for each Sonotube for 28 Pedestals. | # | # | Not assigned | # | # | Not assigned | Material | 12/16/2025 | Not Delivered | N/A | 4 | EA | 1 | 19683 | 19683
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 1 | 15670 - 1 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | ENDURANCE 5110 SERVER WITH 128 GB MEMORY | ZEN5110-128 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 1 | EA | 1 | 42186.67 | 42186.67
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 2 | 15670 - 2 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | 1.6 TB U.3 NVME SSD WITH CARRIER | ZEN-NVME-1.6 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 2 | EA | 2 | 992 | 1984
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 3 | 15670 - 3 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | BLANK DRIVE CARRIER | ZEN-NVME-BLNK | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 3 | XPK | 10 | 9 | 90
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 4 | 15670 - 4 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | DUAL-PORT 10 GBPS COPPER PCIE | DUAL-PORT 10 GBPS COPPER PCIE NETWORK ADAPTER CAR ZEN-X550-T2 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 4 | EA | 2 | 1070 | 2140
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 5 | 15670 - 5 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | LOW VOLTAGE POWER CABLE | ZEN-PWR-222 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 5 | EA | 2 | 82 | 164
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 6 | 15670 - 6 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | CUSTOMER-SUPPLIED VMWARE VSPHERE | CUSTOMER-SUPPLIED VMWARE VSPHERE HOST OS SOFTWARE ZEN-OS-VMW-CS | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 6 | EA | 1 | 0.01 | 0.01
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 7 | 15670 - 7 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | MS WINDOWS SERVER 2025 STANDARD EDITION | MICROSOFT WINDOWS SERVER 2025 STANDARD EDITION ZEN-OS-W25-STD-24C | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 7 | EA | 3 | 1870 | 5610
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 8 | 15670 - 8 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | MS WINDOWS SERVER USER CALS | MICROSOFT WINDOWS SERVER USER CALS O INCLUDES 5 U ZEN-OS-W25-CALU | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 8 | EA | 1 | 296 | 296
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 9 | 15670 - 9 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | MS WINDOWS SERVER 2025 RDS | MICROSOFT WINDOWS SERVER 2025 RDS USER CALZEN-OS-W25-CALU-RD | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 9 | EA | 1 | 1281 | 1281
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 10 | 15670 - 10 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | ZTC ENDURANCE JUMPSTART INST | ZTC ENDURANCE JUMPSTART INSTALLATION SERVICE ZEN-SVC-INST-JMP | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 10 | EA | 1 | 4695 | 4695
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 11 | 15670 - 11 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | ZTC ENDURANCE TOTAL ASSURANCE SUPPORT | ZTC ENDURANCE TOTAL ASSURANCE SUPPORT 12 MO ZEN-SVC-TOTAL | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 11 | EA | 1 | 10125 | 10125
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 12 | 15670 - 12 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | ZTC ENDURANCE SHIPPING | ZTC ENDURANCE SHIPPING ZEN-SHIPPING | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 12 | EA | 1 | 1378 | 1378
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 13 | 15670 - 13 | 0255-F6B-031 | 0 | Major Equipment | Not Yet Acknowledged | 12/12/2025 11:27:47 CST | The Reynolds Company | CPSO-0255-4-2 | BOXPC-138-H01B-00F NON STOCK | # | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 13 | EA | 3 | 3175 | 9525
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 14 | 15670 - 14 | 0255-F6B-031 | 0 | Major Equipment | Follow-Up Document Created | 12/30/2025 15:10:18 CST | The Reynolds Company | CPSO-0255-4-2 | STUDIO 5000 PROFESSIONAL EDITION | Studio 5000 Professional Edition ID: 9324M-RLDT31 DS: E3/590 Agreement No: 4000773852 Annual Cost: $3,172.70 One Time Cost: $16,996.63 Prorated Annual Cost @ 365 days: $3,172.70 Quantity: 2 Prorated Bundle Total: $20,169.32 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 14 | EA | 2 | 10084.66 | 20169.32
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 15 | 15670 - 15 | 0255-F6B-031 | 0 | Major Equipment | Follow-Up Document Created | 12/30/2025 15:10:18 CST | The Reynolds Company | CPSO-0255-4-2 | FactoryTalk View Studio Enterprise | FactoryTalk View Studio Enterprise Perpetual ID: 9701M-VWSTDENTT61 DS: S2/93F Agreement No: 4000773852 Annual Cost: $500.26 One Time Cost: $2,501.32 Prorated Annual Cost @365 days: $500.26 Qty 1 Prorated Bundle Total: $3,001.58 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 15 | EA | 1 | 3001.58 | 3001.58
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 16 | 15670 - 16 | 0255-F6B-031 | 0 | Major Equipment | Follow-Up Document Created | 12/30/2025 15:10:18 CST | The Reynolds Company | CPSO-0255-4-2 | PlantPAx PASS Small 5 Client | PlantPAx PASS Small 5 Client ID: 9528M-PASS05T31 DS: S3/81H Agreement No: 4000773852 Annual Cost: $4,656.91 One Time Cost: $23,285.34 Prorated Annual Cost @ 365 days: $4,656.91 Quantity: 1 PlantPAx PASS Small 5 Client ID: 9528M-PASS05T31 DS: S3/81H Agreement No: 4000773852 Prorated Bundle Total: $27,942.25 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 16 | EA | 1 | 27942.25 | 27942.25
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 17 | 15670 - 17 | 0255-F6B-031 | 0 | Major Equipment | Follow-Up Document Created | 12/30/2025 15:10:18 CST | The Reynolds Company | CPSO-0255-4-2 | Historian SE - 5,000 tags | Historian SE - 5,000 tags Perpetual ID: 9518M-HST5KT41 DS: S3/80H Agreement No: 4000773852 Annual Cost: $6,638.02 One Time Cost: $33,182.90 Prorated Annual Cost @ 365 days: $6,638.02 Quantity: 1 Prorated Bundle Total: $39,820.92 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 17 | EA | 1 | 39820.92 | 39820.92
15670 | Fermi Frame 6B PGP - TO#4 - PlantPAx control system server and server software | 12/11/2025 | Follow-Up Document Created | TO#4 - PlantPAx control system server and server software | 18 | 15670 - 18 | 0255-F6B-031 | 0 | Major Equipment | Follow-Up Document Created | 12/30/2025 15:10:18 CST | The Reynolds Company | CPSO-0255-4-2 | ThinManager V-FLEX 1 | ThinManager V-FLEX 1 Perpetual ID: 9541M-TMFT11 DS: S2/91F Agreement No: 4000773852 Annual Cost: $848.45 One Time Cost: $4,242.26 Prorated Annual Cost @ 365 days: $848.45 Quantity: 2 Prorated Bundle Total: $5,090.71 | # | # | Not assigned | # | # | Not assigned | Material | 12/18/2025 | Not Delivered | Free carrier | 18 | EA | 2 | 2545.35 | 5090.7
15677 | Fermi Frame 6B PGP - TO#Comb Cycle: IMTT Hot Well Pumps Refurbishment (Dooling) | 12/12/2025 | Sent | TO#Comb Cycle: IMTT Hot Well Pumps Refurbishment (Dooling) | 1 | 15677 - 1 | 0255-CC-030 | 0 | Refurb | Sent | 12/12/2025 15:30:29 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | Inspection for Multi-Stage Lift Pump(s) | Pump #1 TX252218 - Worthington/Ingersoll Rand Pump #2 TX252219 - Worthington/Ingersoll Rand 3-5 days for inspection Notes: • Inspection for each Multi-Stage Lift Pumps consists of match mark the unit and photograph. Inventory, document, and photograph all customer-supplied components. Perform and document pre-disassembly checks. • Disassemble the unit completely. Clean all components using media blast, hydro blast, or solvent clean. Conduct and document a complete dimensional inspection along with all visual observations. • Compile findings into an inspection report to formulate a repair scope and estimated cost. No repairs will begin until the customer approves the proposed scope and costs. | # | # | Not assigned | # | # | Not assigned | Service | 12/19/2025 | Not Relevant | Free carrier | 1 | EA | 2 | 5200 | 10400
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 1 | 15692 - 1 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Materials Manager-ST) | Contractor Billable Title: Material Manager RPS Billable Title: Sr. Material Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 1 | EA | 1120 | 76.85 | 86072
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 2 | 15692 - 2 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Materials Manager-OT) | Contractor Billable Title: Material Manager RPS Billable Title: Sr. Material Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 2 | EA | 1232 | 104.2 | 128374.4
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 3 | 15692 - 3 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (GF Site Work-ST) | Contractor Billable Title: GF Site Work RPS Billable Title: General Foreman - Site Work | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 3 | XPK | 1120 | 76.85 | 86072
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 4 | 15692 - 4 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (GF Site Work-OT) | # | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 4 | EA | 1232 | 104.2 | 128374.4
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 5 | 15692 - 5 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Riggers - ST) | Contractor Billable Title: Riggers RPS Billable Title: Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 5 | EA | 3360 | 64.04 | 215174.4
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 6 | 15692 - 6 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Riggers - OT) | Contractor Billable Title: Riggers RPS Billable Title: Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 6 | EA | 3696 | 86.83 | 320923.68
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 7 | 15692 - 7 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Material Yard - ST) | Contractor Billable Title: Material Yard RPS Billable Title: Warehouseman | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 7 | EA | 2240 | 57.63 | 129091.2
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 8 | 15692 - 8 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Material Yard - OT) | Contractor Billable Title: Material Yard RPS Billable Title: Warehouseman | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 8 | EA | 2464 | 78.15 | 192561.6
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 9 | 15692 - 9 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (WH Crane Operator-ST) | Contractor Billable Title: Warehouse/Crane Operator RPS Billable Title: Crane Operator 1 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 9 | EA | 2880 | 83.25 | 239760
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 10 | 15692 - 10 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (WH Crane Operator-OT) | Contractor Billable Title: Warehouse/Crane Operator RPS Billable Title: Crane Operator 1 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 10 | EA | 2792 | 112.88 | 315160.96
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 11 | 15692 - 11 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor -Laydown(CDL,Forklift Op-ST) | Contractor Billable Title: CDL Driver, Forklift Operator RPS Billable Title: Forklift Operator | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 11 | EA | 2240 | 60.84 | 136281.6
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 12 | 15692 - 12 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (CDL,Forklift Op-OT) | Contractor Billable Title: CDL Driver, Forklift Operator RPS Billable Title: Forklift Operator | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 12 | EA | 2464 | 82.49 | 203255.36
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 13 | 15692 - 13 | - | 0 | Expenses | Follow-Up Document Created | 12/31/2025 11:24:19 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contractor Per Diem | # | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 13 | EA | 2214 | 178 | 394092
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 14 | 15692 - 14 | - | 0 | Labor - Laydown | Sent | 12/22/2025 07:11:40 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Operator J2-ST) | Contractor Billable Title: Operator J2 RPS Billable Title: Crane Operator 2 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 14 | EA | 360 | 80.05 | 28818
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 15 | 15692 - 15 | - | 0 | Labor - Laydown | Follow-Up Document Created | 12/30/2025 08:57:06 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Operator J2-OT) | Contractor Billable Title: Operators J2 RPS Billable Title: Crane Operator 2 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 15 | EA | 180 | 108.54 | 19537.2
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 16 | 15692 - 16 | - | 0 | Labor - Laydown | Sent | 12/22/2025 07:11:40 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Operator J3-ST) | Contractor Billable Title: Operators J3 RPS Billable Title: Crane Operator 3 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 16 | EA | 360 | 60.84 | 21902.4
15692 | Fermi Frame 6B PGP - TO#4: Labor - Laydown, Operators | 12/13/2025 | Follow-Up Document Created | TO#4: Labor - Laydown, Operators | 17 | 15692 - 17 | - | 0 | Labor - Laydown | Sent | 12/22/2025 07:11:40 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Laydown (Operator J3-OT) | Contractor Billable Title: Operators J3 RPS Billable Title: Crane Operator 3 | # | # | Not assigned | # | # | Not assigned | Service | 12/20/2025 | Not Relevant | N/A | 17 | EA | 180 | 82.49 | 14848.2
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 1 | 15702 - 1 | 0255-F6B-033 | 0 | Refurb | Finished | 01/02/2026 16:16:57 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Philadelphia Gearbox Inspection | QUOTE: Q800030797, Q800030821, Q800030829 PROJECT: P014708, P014709, P014710 SHOP: 3382 Bird Drive Gillette, Wyoming, 82718 | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 1 | EA | 3 | 21700 | 65100
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 2 | 15702 - 2 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Inspection 480V Gear Inspection | QUOTE: 34121 PROJECT: SHOP: 620 S Rancho Ave Colton, California, 92324 ID Unit ScanUID SubSystem Scanner_Comments Crate 264 MCC MCC-0001 MCC 480 MCC NID 480 (1-6) 265 MCC MCC-0002 MCC 480 MCC NID 480 (1-6) 266 MCC MCC-0003 MCC 480 MCC NID 480 (1-6) 267 MCC MCC-0004 MCC 480 MCC NID 480 (1-6) 268 MCC MCC-0005 MCC 480 MCC NID 480 (1-6) 269 MCC MCC-0006 MCC 480 MCC NID 480 (1-6) 270 MCC MCC-0007 MCC 480 MCC NID 480 (7&8) 272 MCC MCC-0008 MCC 480 MCC NID 480 (7&8) 345 MCC MCC-0042 MCC 480 MCC Not Crated, Solo 346 MCC MCC-0043 MCC 480 MCC Not Crated, Solo 347 MCC MCC-0049 MCC 480 Tr MCC In MCCs 348 MCC MCC-0050 MCC 480 Tr MCC In MCCs 349 MCC MCC-0051 MCC 480 Tr MCC In MCCs 350 MCC MCC-0052 MCC 480 Tr MCC In MCCs 351 MCC MCC-0053 MCC 480 Tr MCC In MCCs 352 MCC MCC-0054 MCC 480 Tr MCC In MCCs 353 MCC MCC-0055 MCC 480 Tr MCC In MCCs 354 MCC MCC-0044 MCC 480 MCC Not Crated Solo 355 MCC MCC-0045 MCC 480 MCC Junction Box Not Crated Solo 356 MCC MCC-0046 MCC 480 MCC Not Crated Solo 357 MCC MCC-0047 MCC 480 MCC Not Crate | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 2 | EA | 1 | 10000 | 10000
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 3 | 15702 - 3 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Water Injection Skid Inspection | QUOTE: PROJECT: SHOP: 620 S Rancho Ave Colton, California, 92324 | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 3 | XPK | 3 | 9957.62 | 29872.86
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 4 | 15702 - 4 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: Q80003080 JOB: P014851 SHOP: 3904 Tulane RD. Orange, Texas, 77630 Replace both bearings with new: DE: SKF 6312 2ZJEM ODE: SKF 6312 2ZJEM | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 4 | EA | 1 | 18901 | 18901
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 5 | 15702 - 5 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: 800030805 JOB: P014852 SHOP: 3904 Tulane RD. Orange, Texas, 77630 Replace both bearings with new: DE: SKF 6312 C3 ODE: SKF 6312 C3 | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 5 | EA | 1 | 17062 | 17062
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 6 | 15702 - 6 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: Q800030962 JOB: P014856 SHOP: 3904 Tulane RD. Orange, Texas, 77630 | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 6 | EA | 1 | 18111 | 18111
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 7 | 15702 - 7 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: Q800031016 JOB: P014857 SHOP: 3904 Tulane RD. Orange, Texas, 77630 Replace both bearings with new: DE: SKF 6313 C3 ODE: SKF 6211 C3 Replace external cooling fan with new; Aluminum. | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 7 | EA | 1 | 16614 | 16614
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 8 | 15702 - 8 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: Q800031025 JOB: P014861 SHOP: 3904 Tulane RD. Orange, Texas, 77630 Replace both bearings with new: DE: SKF 6312 C3 ODE: SKF 6210 C3 | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 8 | EA | 1 | 13479 | 13479
15702 | Fermi Frame 6B PGP - TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 12/16/2025 | Follow-Up Document Created | TO#4: Inspections (Gearbox, Water Injection, 480V Swithchear), Refurbishment (Blower) | 9 | 15702 - 9 | 0255-F6B-033 | 0 | Refurb | Sent | 12/16/2025 17:50:38 CST | Sulzer Electro Mechanical Services Inc. | CPSO-0255-5-2 | Blower Inspection/Refurbishment | QUOTE: Q800030970 JOB: P014862 SHOP: 3904 Tulane RD. Orange, Texas, 77630 Replace both bearings with new: DE: SKF 6312 C3 ODE: SKF 6210 C3 Replace V-ring rubber seal with new. | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | Ex works | 9 | EA | 1 | 17156 | 17156
15703 | Fermi Frame 6B PGP - TO#4: Surveying Equipment Calibration | 12/16/2025 | Sent | TO#4: Surveying Equipment Calibration | 1 | 15703 - 1 | - | 0 | Calibration Services | Sent | 12/16/2025 01:46:58 CST | Bayshore Surveying Instrument CO Inc. | CPSO-0255-4-8 | Surveying Equipment Calibration Services | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/23/2025 | Not Relevant | Ex works | 1 | EA | 0 | 0 | 5000
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 1 | 15704 - 1 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/29/2025 10:12:38 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-1102 | Tag: PCV-1102 GT1 F-101A FUEL GAS SUPPLY PCV-1102 PRESSURE CONTROL NPS 3 ET 667 Size 40i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 12/23/2025 | Not Delivered | Free carrier | 1 | EA | 1 | 24462.52 | 24462.52
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 2 | 15704 - 2 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-230 | Tag: PCV-230 GLYCOL COOLING WATER PUMPS DISCHARGE PRESSURE CONTROL NPS 10 V150 2052 Size 3 Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 2 | EA | 1 | 25241.95 | 25241.95
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 3 | 15704 - 3 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-413 | Tag: PCV-413 DEMIN. WATER PUMPS DISCHARGE PRESSURE CONTROL NPS 4 ET 667 Size 45i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/10/2026 | Not Delivered | Free carrier | 3 | XPK | 1 | 33694.73 | 33694.73
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 4 | 15704 - 4 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-613 | Tag: PCV-613 MOBILE DEMIN TRAILER SERVICE WATER INLET PRESSURE CONTROL NPS 4 ET 667 Size 45i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 4 | EA | 1 | 19905.38 | 19905.38
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 5 | 15704 - 5 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-942 | Tag: PCV-942 FUEL GAS SUPPLY PRESSURE CONTROL NPS 6 ET 667 Size 70i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/24/2026 | Not Delivered | Free carrier | 5 | EA | 1 | 51467.38 | 51467.38
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 6 | 15704 - 6 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-2102 | Tag: PCV-2102 GT1 F-201A FUEL GAS SUPPLY PCV-2102 PRESSURE CONTROL NPS 3 ET 667 Size 40i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 6 | EA | 1 | 24462.52 | 24462.52
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 7 | 15704 - 7 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Control Valve - PCV-3102 | Tag: PCV-3102 GT3 F-301A FUEL GAS SUPPLY PCV-3102 PRESSURE CONTROL NPS 4 ET 667 Size 45i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/17/2026 | Not Delivered | Free carrier | 7 | EA | 1 | 29760.84 | 29760.84
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 8 | 15704 - 8 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Flow Control Valve - FCV-202 | Tag: FCV-202 REJECT DEMIN. WATER FLOW CONTROL NPS 2 ET 667 Size 40i Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 ASCO Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 8 | EA | 1 | 17975.89 | 17975.89
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 9 | 15704 - 9 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Level Control Valve - LCV-220 | Tag: LCV-220 REJECT DEMIN. WATER TANK TK-300 LEVEL CONTROL NPS 2 V150 2052 Size 1 Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/10/2026 | Not Delivered | Free carrier | 9 | EA | 1 | 9849.08 | 9849.08
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 10 | 15704 - 10 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Level Control Valve - LCV-410 | Tag: LCV-410 DEMIN. WATER STORAGE TK-400 LEVEL CONTROL NPS 2 V150 2052 Size 1 Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/10/2026 | Not Delivered | Free carrier | 10 | EA | 1 | 11313.93 | 11313.93
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 11 | 15704 - 11 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Level Control Valve - LCV-611 | Tag: LCV-611 MUNICIPAL WATER STORAGE TK-600 LEVEL CONTROL NPS 4 V150 2052 Size 1 Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 02/10/2026 | Not Delivered | Free carrier | 11 | EA | 1 | 15423.96 | 15423.96
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 12 | 15704 - 12 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Flow Control Valve - FCV-220A | Tag: FCV-220A WSAC-001 COOLING WATER INLET FCV-220A FLOW CONTROL NPS 2 V150 2052 Size 1 Special Tagging DVC6200 Factory Mtgs DVC7K/DVC6200/DVC2000 ASCO Process Level 3 Global Drawings | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 12 | EA | 1 | 12228.07 | 12228.07
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 13 | 15704 - 13 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-200A | TAG# XV-200A MAKE-UP CITY WATER XV-200A KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 13 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 14 | 15704 - 14 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-200B | TAG# XV-200B MAKE-UP CITY WATER XV-200B KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 14 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 15 | 15704 - 15 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-200C | TAG# XV-200C MAKE-UP CITY WATER XV-200C KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 15 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 16 | 15704 - 16 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-201A | TAG#: XV201A RO TRAILER REJECT WATER XV-201A KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 16 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 17 | 15704 - 17 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-201B | TAG#: XV201B RO TRAILER REJECT WATER XV-201B KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 17 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 18 | 15704 - 18 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Block Valve - XV-201C | TAG#: XV201C RO TRAILER REJECT WATER XV-201C KTM EB1 SERIES, SPLIT BODY FLOATING BALL VALVES | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 18 | EA | 1 | 4262 | 4262
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 19 | 15704 - 19 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/27/2025 16:46:26 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Shut Down Valve - SDV-941A | TAG#: SOV-941A FUEL GAS SUPPLY SHUT DOWN SDV-941A COMMAND SOLENOID TRIPLE OFF SET | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 19 | EA | 1 | 31173 | 31173
15704 | Fermi Frame 6B PGP - TO#4: Control Valves | 12/16/2025 | Not Yet Acknowledged | TO#4: Control Valves | 20 | 15704 - 20 | 0255-F6B-034 | 0 | Major Equipment | Not Yet Acknowledged | 12/29/2025 10:12:38 CST | Puffer-Sweiven LP | CPSO-0255-4-2 | Pressure Safety Valve - PSV-940 | (4" EMERSON N6JOS-E35X-SPL) | # | # | Not assigned | # | # | Not assigned | Material | 01/19/2026 | Not Delivered | Free carrier | 20 | EA | 1 | 4885.56 | 4885.56
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 1 | 15705 - 1 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:12:08 CST | Emerson LLLP | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG2A2B21AS5B4Y2Q4M5 PIT-100 PRESSURE TRANSMITTER GAS TURBINES GLYCOL COOLING WATER LINE PRESSURE 12224A25-120-PR-3004 PIT-200 PRESSURE INDICATING TRANSMITTER WSAC COOLING WATER P-201A DISCHARGE PRESSURE 12224A25-120-PR-3005 PIT-201 PRESSURE INDICATING TRANSMITTER WSAC COOLING WATER P-201A SUCTION PRESSURE 12224A25-120-PR-3005 PIT-202 PRESSURE INDICATING TRANSMITTER WSAC COOLING WATER P-201B DISCHARGE PRESSURE 12224A25-120-PR-3005 PIT-203 PRESSURE INDICATING TRANSMITTER WSAC COOLING WATER P-201B SUCTION PRESSURE 12224A25-120-PR-3005 PIT-204 PRESSURE INDICATING TRANSMITTER WSAC GLYCOL P-200A SUCTION PRESSURE 12224A25-120-PR-3005 PIT-205 PRESSURE INDICATING TRANSMITTER WSAC GLYCOL P-200A DISCHARGE PRESSURE 12224A25-120-PR-3005 PIT-206 PRESSURE INDICATING TRANSMITTER WSAC GLYCOL P-200B SUCTION PRESSURE 12224A25-120-PR-3005 PIT-207 PRESSURE INDICATING TRANSMITTER WSAC GLYCOL P-200B DISCHARGE PRESSURE 12224A25-120-PR-3005 PIT-210 PRESSURE INDICATING TRANSMITTER WSAC WASTE WATER PUMPS DISCHARGE PRESSURE 12224A25 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 1 | EA | 22 | 3383.32 | 74433.04
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 2 | 15705 - 2 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:02:57 CST | Emerson LLLP | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 - for PO line item 1 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 2 | EA | 22 | 367.48 | 8084.56
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 3 | 15705 - 3 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:12:08 CST | Emerson LLLP | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG3A2B21AS5B4Y2Q4M5 PIT-1102 PRESSURE INDICATING TRANSMITTER PCV-1102 PRESSURE FEEDBACK 12224A25-120-PR-3009 PIT-2102 PRESSURE INDICATING TRANSMITTER PCV-2102 PRESSURE FEEDBACK 12224A25-120-PR-3009 PIT-3102 PRESSURE INDICATING TRANSMITTER PCV-3102 PRESSURE FEEDBACK 12224A25-120-PR-3009 PIT-5010 PRESSURE INDICATING TRANSMITTER GAS TURBINE AIR HEADER LINE PRESSURE 12224A25-120-PR-3011 PIT-602 PRESSURE INDICATING TRANSMITTER SERVICE WATER P-600A DISCHARGE PRESSURE 12224A25-120-PR-3016 PIT-604 PRESSURE INDICATING TRANSMITTER SERVICE WATER P-600B DISCHARGE PRESSURE 12224A25-120-PR-3016 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 3 | XPK | 6 | 3383.32 | 20299.92
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 4 | 15705 - 4 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:02:57 CST | Emerson LLLP | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 - for PO line item 3 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 4 | EA | 6 | 367.48 | 2204.88
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 5 | 15705 - 5 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:12:08 CST | Emerson LLLP | CPSO-0255-4-2 | Inline Pressure Transmitter | 3051TG4A2B21AS5B4Y2Q4M5 PIT-940 PRESSURE INDICATING TRANSMITTER FUEL GAS SUPPLY LINE PRESSURE 12224A25-120-PR-3009 PIT-941 PRESSURE INDICATING TRANSMITTER LINE PRESSURE SDV-941 SHUTDOWN 12224A25-120-PR-3009 PIT-942 PRESSURE INDICATING TRANSMITTER PCV-942 PRESSURE FEEDBACK 12224A25-120-PR-3009 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 5 | EA | 3 | 3383.32 | 10149.96
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 6 | 15705 - 6 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/20/2025 11:02:57 CST | Emerson LLLP | CPSO-0255-4-2 | Rosemount R306 In-Line Manifold | R306ET12AA11 - for PO line item 5 | # | # | Not assigned | # | # | Not assigned | Material | 01/16/2026 | Not Delivered | Free carrier | 6 | EA | 3 | 367.48 | 1102.44
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 7 | 15705 - 7 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/16/2025 17:54:08 CST | Emerson LLLP | CPSO-0255-4-2 | IMP-TARIFF-M:SURCHARGE | # | # | # | Not assigned | # | # | Not assigned | Service | 12/12/2025 | Not Relevant | Free carrier | 7 | EA | 1 | 6278.84 | 6278.84
15705 | Fermi Frame 6B PGP - TO#4: Plant Instrumentation | 12/16/2025 | Not Yet Acknowledged | TO#4: Plant Instrumentation | 8 | 15705 - 8 | 0255-F6B-035 | 0 | Major Equipment | Not Yet Acknowledged | 12/16/2025 17:54:08 CST | Emerson LLLP | CPSO-0255-4-2 | RMT-DOC-CERT-Q1 | # | # | # | Not assigned | # | # | Not assigned | Material | 12/12/2025 | Not Relevant | Free carrier | 8 | EA | 1 | 67.29 | 67.29
15721 | Fermi Frame 6B PGP - TO#4 - Rebar | 12/17/2025 | Follow-Up Document Created | TO#4 - Rebar | 1 | 15721 - 1 | 0255-F6B-012 | 0 | Bulks - Civil | Follow-Up Document Created | 01/02/2026 13:41:48 CST | Katy Steel Co. Inc. | CPSO-0255-4-9 | Rebar (Foundations) | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/28/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 50000
15737 | Fermi Frame 6B PGP - TO#4 - Glycol CW Expansion Tanks | 12/17/2025 | Follow-Up Document Created | TO#4 - Glycol CW Expansion Tanks | 1 | 15737 - 1 | 0255-F6B-038 | 0 | Major Equipment | Follow-Up Document Created | 12/28/2025 12:00:13 CST | JWWTEW, LLC WILTEW | CPSO-0255-4-2 | Glycol CW Expansion Tank (V-200) | # | # | # | Not assigned | # | # | Not assigned | Material | 01/26/2026 | Not Relevant | Ex works | 1 | EA | 1 | 48477 | 48477
15746 | Fermi Frame 6B PGP - TO#4 - Yard Mule Rental | 12/17/2025 | Sent | TO#4 - Yard Mule Rental | 1 | 15746 - 1 | 0255-F6B-045 | 0 | Major Equipment | Sent | 12/17/2025 23:18:46 CST | Yard Mule Specialist INC | CPSO-0255-4-9 | Delivery | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/24/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 3800
15746 | Fermi Frame 6B PGP - TO#4 - Yard Mule Rental | 12/17/2025 | Sent | TO#4 - Yard Mule Rental | 2 | 15746 - 2 | - | 0 | Equipment Rental - Laydown | Sent | 12/17/2025 23:18:46 CST | Yard Mule Specialist INC | CPSO-0255-4-9 | Yard Mule Rental (6 months) | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/24/2025 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 24000
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 1 | 15747 - 1 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. Project Management (ST) | Contractor Billable Title: Sr. Project Management RPS Billable Title: Sr. Project Management | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 1 | EA | 120 | 136.08 | 16329.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 2 | 15747 - 2 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. Project Management (OT) | Contractor Billable Title: Sr. Project Management RPS Billable Title: Sr. Project Management | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 2 | EA | 132 | 184.52 | 24356.64
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 3 | 15747 - 3 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Management (ST) | Contractor Billable Title: Project Management RPS Billable Title: Project Management | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 3 | XPK | 120 | 124.07 | 14888.4
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 4 | 15747 - 4 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Management (OT) | Contractor Billable Title: Project Management RPS Billable Title: Project Management | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 4 | EA | 132 | 168.24 | 22207.68
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 5 | 15747 - 5 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Construction Manager (ST) | Contractor Billable Title: Construction Manager RPS Billable Title: Construction Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 5 | EA | 240 | 108.87 | 26128.8
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 6 | 15747 - 6 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Construction Manager (OT) | Contractor Billable Title: Construction Manager RPS Billable Title: Construction Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 6 | EA | 264 | 147.62 | 38971.68
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 7 | 15747 - 7 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Superintendent - Piping (ST) | Contractor Billable Title: Superintendent - Piping RPS Billable Title: Superintendent - Piping | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 7 | EA | 240 | 89.65 | 21516
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 8 | 15747 - 8 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Superintendent - Piping (OT) | Contractor Billable Title: Superintendent - Piping RPS Billable Title: Superintendent - Piping | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 8 | EA | 264 | 121.57 | 32094.48
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 9 | 15747 - 9 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. Quality Manager (ST) | Contractor Billable Title: Sr. Quality Manager RPS Billable Title: Sr. Quality Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 9 | EA | 488 | 108.87 | 53128.56
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 10 | 15747 - 10 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. Quality Manager (OT) | Contractor Billable Title: Sr. Quality Manager RPS Billable Title: Sr. Quality Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 10 | EA | 616 | 147.62 | 90933.92
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 11 | 15747 - 11 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Field Engineer I (ST) | Contractor Billable Title: Field Engineer I RPS Billable Title: Field Engineer I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 11 | EA | 364 | 76.85 | 27973.4
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12 | 15747 - 12 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Field Engineer I (OT) | Contractor Billable Title: Field Engineer I RPS Billable Title: Field Engineer I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 12 | EA | 484 | 104.2 | 50432.8
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 13 | 15747 - 13 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman/Pipe (ST) | Contractor Billable Title: Foreman/Pipe RPS Billable Title: General Foreman - Piping | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 13 | EA | 240 | 67.24 | 16137.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 14 | 15747 - 14 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman/Pipe (OT) | Contractor Billable Title: Foreman/Pipe RPS Billable Title: General Foreman - Piping | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 14 | EA | 264 | 91.17 | 24068.88
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 15 | 15747 - 15 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Civil J1 (ST) | Contractor Billable Title: Civil J1 RPS Billable Title: Civil - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 15 | EA | 8480 | 64.04 | 543059.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 16 | 15747 - 16 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Civil J1 (OT) | Contractor Billable Title: Civil J1 RPS Billable Title: Civil - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 16 | EA | 4672 | 86.83 | 405669.76
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 17 | 15747 - 17 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - UG Pipe J1 (ST) | Contractor Billable Title: UG Pipe J1 RPS Billable Title: Pipe Fitter - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 17 | EA | 2640 | 64.04 | 169065.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 18 | 15747 - 18 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - UG Pipe J1 (OT) | Contractor Billable Title: UG Pipe J1 RPS Billable Title: Pipe Fitter - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 18 | EA | 2904 | 86.83 | 252154.32
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 19 | 15747 - 19 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - UG Pipe J2 (ST) | Contractor Billable Title: UG Pipe J2 RPS Billable Title: Pipe Fitter - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 19 | EA | 1680 | 60.84 | 102211.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 20 | 15747 - 20 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - UG Pipe J2 (OT) | Contractor Billable Title: UG Pipe J2 RPS Billable Title: Pipe Fitter - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 20 | EA | 1848 | 82.49 | 152441.52
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 21 | 15747 - 21 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Welder (ST) | Contractor Billable Title: Welder RPS Billable Title: Pipe Fitter - Welder - Single Hand Specialty | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 21 | EA | 1880 | 72.04 | 135435.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 22 | 15747 - 22 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Welder (OT) | Contractor Billable Title: Welder RPS Billable Title: Pipe Fitter - Welder - Single Hand Specialty | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 22 | EA | 2068 | 97.69 | 202022.92
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 23 | 15747 - 23 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor-Sr. Project Controls Mngr (ST) | Contractor Billable Title: Sr. Project Controls Manager RPS Billable Title: Sr. Project Controls Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 23 | EA | 320 | 120.07 | 38422.4
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 24 | 15747 - 24 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor-Sr. Project Controls Mngr (OT) | Contractor Billable Title: Sr. Project Controls Manager RPS Billable Title: Sr. Project Controls Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 24 | EA | 352 | 162.81 | 57309.12
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 25 | 15747 - 25 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. HSE Manager (ST) | Contractor Billable Title: Sr. HSE Manager RPS Billable Title: Sr. HSE Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 25 | EA | 320 | 108.87 | 34838.4
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 26 | 15747 - 26 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Sr. HSE Manager (OT) | Contractor Billable Title: Sr. HSE Manager RPS Billable Title: Sr. HSE Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 26 | EA | 352 | 147.62 | 51962.24
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 27 | 15747 - 27 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Scheduler (ST) | Contractor Billable Title: Project Scheduler RPS Billable Title: Project Scheduler | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 27 | EA | 320 | 104.06 | 33299.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 28 | 15747 - 28 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Scheduler (OT) | Contractor Billable Title: Project Scheduler RPS Billable Title: Project Scheduler | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 28 | EA | 352 | 141.1 | 49667.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 29 | 15747 - 29 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Office Manager (ST) | Contractor Billable Title: Office Manager RPS Billable Title: Office Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 29 | EA | 320 | 56.03 | 17929.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 30 | 15747 - 30 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Office Manager (OT) | Contractor Billable Title: Office Manager RPS Billable Title: Office Manager | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 30 | EA | 352 | 75.98 | 26744.96
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 31 | 15747 - 31 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Super - Structural Steel (ST) | Contractor Billable Title: Superintendent - Structural Steel RPS Billable Title: Superintendent - Structural Steel | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 31 | EA | 320 | 89.65 | 28688
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 32 | 15747 - 32 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Super - Structural Steel (OT) | Contractor Billable Title: Superintendent - Structural Steel RPS Billable Title: Superintendent - Structural Steel | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 32 | EA | 352 | 121.57 | 42792.64
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 33 | 15747 - 33 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman - Iron (ST) | Contractor Billable Title: Iron Worker - Foreman RPS Billable Title: Iron Worker - Foreman | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 33 | EA | 320 | 67.24 | 21516.8
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 34 | 15747 - 34 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman - Iron (OT) | Contractor Billable Title: Iron Worker - Foreman RPS Billable Title: Iron Worker - Foreman | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 34 | EA | 352 | 91.17 | 32091.84
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 35 | 15747 - 35 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Iron Journeyman I (ST) | Contractor Billable Title: Iron Worker - Journeyman I RPS Billable Title: Iron Worker - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 35 | EA | 1600 | 64.04 | 102464
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 36 | 15747 - 36 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Iron Journeyman I (OT) | Contractor Billable Title: Iron Worker - Journeyman I RPS Billable Title: Iron Worker - Journeyman I | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 36 | EA | 1760 | 86.83 | 152820.8
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 37 | 15747 - 37 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Iron Journeyman II (ST) | Contractor Billable Title: Iron Worker - Journeyman II RPS Billable Title: Iron Worker - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 37 | EA | 640 | 60.84 | 38937.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 38 | 15747 - 38 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Iron Journeyman II (OT) | Contractor Billable Title: Iron Worker - Journeyman II RPS Billable Title: Iron Worker - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 38 | EA | 704 | 82.49 | 58072.96
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 39 | 15747 - 39 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Engineer (ST) | Contractor Billable Title: Project Engineer RPS Billable Title: Project Engineer | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 39 | EA | 320 | 88.05 | 28176
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 40 | 15747 - 40 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Project Engineer (OT) | Contractor Billable Title: Project Engineer RPS Billable Title: Project Engineer | # | # | Not assigned | # | # | Not assigned | Service | 12/23/2025 | Not Relevant | N/A | 40 | EA | 160 | 119.4 | 19104
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 41 | 15747 - 41 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - General Foreman - Concrete (ST) | Contractor Billable Title: Labor - General Foreman - Concrete RPS Billable Title: Labor - General Foreman - Concrete | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 41 | EA | 320 | 76.85 | 24592
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 42 | 15747 - 42 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - General Foreman - Concrete (OT) | Contractor Billable Title: General Foreman - Civil RPS Billable Title: General Foreman - Civil | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 42 | EA | 160 | 104.2 | 16672
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 43 | 15747 - 43 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman/Civil (ST) | Contractor Billable Title: Foreman/Civil RPS Billable Title: Civil - Foreman | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 43 | EA | 720 | 67.24 | 48412.8
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 44 | 15747 - 44 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Foreman/Civil (OT) | Contractor Billable Title: Foreman/Civil RPS Billable Title: Civil - Foreman | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 44 | EA | 360 | 91.17 | 32821.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 45 | 15747 - 45 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Welding Materials | # | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Relevant | N/A | 45 | EA | 1 | 36108 | 36108
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 46 | 15747 - 46 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Consumables | # | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Relevant | N/A | 46 | EA | 1 | 178189.48 | 178189.48
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 47 | 15747 - 47 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Rental Equipment | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 47 | EA | 1 | 37576 | 37576
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 48 | 15747 - 48 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | NDE | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 48 | EA | 1 | 49500 | 49500
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 49 | 15747 - 49 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Training HDPE | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 49 | EA | 1 | 17000 | 17000
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 50 | 15747 - 50 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Coating | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 50 | EA | 1 | 15000 | 15000
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 51 | 15747 - 51 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Safety Supplies | # | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | N/A | 51 | EA | 1 | 8000 | 8000
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 52 | 15747 - 52 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Rental Formwork | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 52 | EA | 1 | 24665 | 24665
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 53 | 15747 - 53 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Civil J2 (ST) | Contractor Billable Title: Civil J2 RPS Billable Title: Civil - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 53 | EA | 2880 | 60.84 | 175219.2
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 54 | 15747 - 54 | - | 0 | Labor - Construction | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Labor - Civil J2 (OT) | Contractor Billable Title: Civil J2 RPS Billable Title: Civil - Journeyman II | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 54 | EA | 1440 | 82.49 | 118785.6
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 55 | 15747 - 55 | - | 0 | Expenses | Follow-Up Document Created | 12/31/2025 10:58:30 CST | E&H Excavations LLC | CPSO-0255-4-9 | Contractor Per Diem | # | # | # | Not assigned | # | # | Not assigned | Service | 12/24/2025 | Not Relevant | N/A | 55 | EA | 5114 | 178 | 910292
15747 | Fermi Frame 6B PGP - TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 12/17/2025 | Follow-Up Document Created | TO#4 - Civil Foundations, UG Piping Installation, Steel Erection | 56 | 15747 - 56 | - | 0 | Labor - Construction | Sent | 12/22/2025 07:20:12 CST | E&H Excavations LLC | CPSO-0255-4-9 | Miscellaneous - Ordered on RPS's behalf | Pump Truck - Until RPS had account setup Concrete (AMA RediMix) - Until RPS had account setup Braun Intertek | # | # | Not assigned | # | # | Not assigned | Limit | 12/24/2025 | Not Relevant | N/A | 56 | EA | 0 | 0 | 200000
15781 | Fermi Frame 6B PGP - TO#4 - Inland Freight | 12/21/2025 | Follow-Up Document Created | TO#4 - Inland Freight | 1 | 15781 - 1 | - | 0 | Freight | Follow-Up Document Created | 01/02/2026 18:16:08 CST | H&A Transportation - Aldo Global Services, Los Condores | CPSO-0255-4-5 | Freight | # | # | # | Not assigned | # | # | Not assigned | Limit | 12/28/2025 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 60000
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 1 | 15782 - 1 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | STR H46 CBL TRAY SECT 12IN X | ATKOR A620D-09-SL20-12-S STR H46 CBL TRAY SECT 12IN X 20FT | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 1 | EA | 20 | 722.71 | 14454.2
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 2 | 15782 - 2 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | STR H46 CBL TRAY SECT 24IN X | ATKOR A620D-09-SL20-24-S STR H46 CBL TRAY SECT 24IN X 20FT | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 2 | EA | 40 | 764.4 | 30576
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 3 | 15782 - 3 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | STR H46 CBL TRAY SECT 36IN X | ATKOR A620D-09-SL20-36-S STR H46 CBL TRAY SECT 36IN X 20FT | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 3 | XPK | 153 | 856.85 | 131098.05
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 4 | 15782 - 4 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL INSIDE 90D X 24 | ATKOR A63-09-90VI24-12-S 620D VERTICAL INSIDE 90D X 24R X 12IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 4 | EA | 4 | 244.64 | 978.56
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 5 | 15782 - 5 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL INSIDE 90D X 24R | ATKOR A63-09-90VI24-24-S 620D VERTICAL INSIDE 90D X 24R X 24IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 5 | EA | 2 | 254.83 | 509.66
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 6 | 15782 - 6 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL INSIDE 45D X 24R | ATKOR A63-09-45VI24-36-S 620D VERTICAL INSIDE 45D X 24R X 36IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 6 | EA | 24 | 163.49 | 3923.76
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 7 | 15782 - 7 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL INSIDE 90D X 24R | ATKOR A63-09-90VI24-36-S 620D VERTICAL INSIDE 90D X 24R X 36IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 7 | EA | 1 | 276.32 | 276.32
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 8 | 15782 - 8 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL OTSDE 90D X 24R | ATKOR A63-09-90VO24-12-S 620D VERTICAL OTSDE 90D X 24R X 12IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 8 | EA | 14 | 244.64 | 3424.96
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 9 | 15782 - 9 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL OTSDE 90D X 24 | ATKOR A63-09-90VO24-24-S 620D VERTICAL OTSDE 90D X 24R X 24IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 9 | EA | 2 | 254.83 | 509.66
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 10 | 15782 - 10 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL OTSDE 45D X 24R | ATKOR A63-09-45VO24-36-S 620D VERTICAL OTSDE 45D X 24R X 36IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 10 | EA | 24 | 163.49 | 3923.76
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 11 | 15782 - 11 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL OTSDE 90D X 24R | ATKOR A63-09-90VO24-36-S 620D VERTICAL OTSDE 90D X 24R X 36IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 11 | EA | 1 | 276.32 | 276.32
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 12 | 15782 - 12 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL INSIDE 45D X 24R | ATKOR A63-09-45VI24-24-S 620D VERTICAL INSIDE 45D X 24R X 24IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 12 | EA | 2 | 149.16 | 298.32
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 13 | 15782 - 13 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL OTSDE 45D X 24R | ATKOR A63-09-45VO24-24-S 620D VERTICAL OTSDE 45D X 24R X 24IN WIDE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 13 | EA | 2 | 149.16 | 298.32
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 14 | 15782 - 14 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | 4/0 AWG BONDING JUMPER 1600 | ATKOR GBJ-C-1600 4/0 AWG BONDING JUMPER 1600 AMP | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 14 | EA | 75 | 32.29 | 2421.75
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 15 | 15782 - 15 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D VERTICAL SPLICE PLATE | ATKOR SPV-A6-S8 620D VERTICAL SPLICE PLATE 8HOLE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 15 | EA | 8 | 47.15 | 377.2
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 16 | 15782 - 16 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | 620D EXPANSION SPLICE PLATE | ATKOR SPE-A6-S8 620D EXPANSION SPLICE PLATE 8HOLE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 16 | EA | 65 | 26.55 | 1725.75
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 17 | 15782 - 17 | 0255-F6B-037 | 0 | Bulks - Electrical | Sent | 12/22/2025 10:34:36 CST | CED Industrial, Inc | CPSO-0255-4-4 | STRAIGHT DIVIDER STRIP 10FT | ATKOR DS-A6-10 STRAIGHT DIVIDER STRIP 10FT | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 17 | EA | 40 | 44.79 | 1791.6
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 18 | 15782 - 18 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | VERT OTSDE BARRIER 90D X 24R | ATKOR DF-A6-90VO24 VERT OTSDE BARRIER 90D X 24R | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 18 | EA | 14 | 27.56 | 385.84
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 19 | 15782 - 19 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | VERT INSIDE BARRIER 90D X 24R | ATKOR DF-A6-90VI24 VERT INSIDE BARRIER 90D X 24R | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 19 | EA | 4 | 28.35 | 113.4
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 20 | 15782 - 20 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | BARR STRIP SPLICE CLIP | ATKOR DVS-5 BARR STRIP SPLICE CLIP | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 20 | EA | 20 | 0.82 | 16.4
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 21 | 15782 - 21 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:15:25 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1 PC AL CBL TRAY CLMP 3/8IN | ATKOR HDH-A 1 PC AL CBL TRAY CLMP 3/8IN HOLE | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 21 | EA | 250 | 1.35 | 337.5
15782 | Fermi Frame 6B - TO#4 - Cable Tray | 12/21/2025 | Follow-Up Document Created | TO#4 - Cable Tray | 22 | 15782 - 22 | 0255-F6B-037 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 15:01:04 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1-5/8X1-5/8 12G HDG SLOT 10FT | UNIST P1000T10HG 1-5/8X1-5/8 12G HDG SLOT 10FT METAL FRAMING, SINGLE TYPE; ASTM A1011 SS GRADE 33 LOW CARBON STEEL MATERIAL; HOT DIP GALVANIZED FINISH; 10 FOOT; 1-5/8 INCH; 1-5/8 INCH; SLOTTED CONFIGURATION; UL E19459, CSA 013669 APPLICABLE STANDARD; 12 GAUGE THICKNESS; COLD FORMED PROCESS | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 22 | EA | 1500 | 4 | 6000
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 1 | 15783 - 1 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 600P 6IN PVC SCH40 PIPE | PVC 600P 6IN PVC SCH40 PIPE Your # 6IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 1 | EA | 9020 | 410.53 | 37029.81
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 2 | 15783 - 2 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 400P 4IN SCH40 PVC PIPE | PVC 400P 4IN SCH40 PVC PIPE Your # 4IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 2 | EA | 3080 | 221.18 | 6812.34
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 3 | 15783 - 3 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 200P 2IN SCH40 PVC PIPE | PVC 200P 2IN SCH40 PVC PIPE Your # 2IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 3 | XPK | 12900 | 83.79 | 10808.91
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 4 | 15783 - 4 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GEL 600G9036R 6IN 90D 36R GAL | GEL 600G9036R 6IN 90D 36R GAL ELB 6 IN 90DEG 36RAD GALV ELBOW | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 4 | EA | 114 | 369.38 | 42109.32
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 5 | 15783 - 5 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GEL 400G9036R 4IN 90D 36R GAL | GEL 400G9036R 4IN 90D 36R GAL ELB 4 IN 90DEG 36RAD GALV ELBOW | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 5 | EA | 41 | 187.01 | 7667.41
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 6 | 15783 - 6 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GEL 200G9036R 2IN 90D 36R GAL | GEL 200G9036R 2IN 90D 36R GAL ELB 2 IN 90DEG 36RAD GALV ELBOW | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 6 | EA | 112 | 73.15 | 8192.8
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 7 | 15783 - 7 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVCFIT 600P FA 6 IN PVC COND | PVCFIT 600P FA 6 IN PVC COND FEMALE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 7 | EA | 114 | 1043.84 | 1189.98
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 8 | 15783 - 8 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVCFIT 400P FA 4 IN PVC COND | PVCFIT 400P FA 4 IN PVC COND FEMALE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 8 | EA | 41 | 317.91 | 130.34
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 9 | 15783 - 9 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVCFIT 200P FA 2 IN PVC COND | PVCFIT 200P FA 2 IN PVC COND FEMALE ADAPTER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 9 | EA | 112 | 79.29 | 88.8
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 10 | 15783 - 10 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GCP 600GC 6IN GALV COUPLNG | GCP 600GC 6IN GALV COUPLNG QTY 195 FAC STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 10 | EA | 114 | 55.65 | 6344.1
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 11 | 15783 - 11 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GCP 400GC 4IN GALV COUPLNG | GCP 400GC 4IN GALV COUPLNG GALCPLG4 ¦ QTY 2268 FAC STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 11 | EA | 41 | 19.63 | 804.83
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 12 | 15783 - 12 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GCP 200GC 2IN GALV COUPLNG | GCP 200GC 2IN GALV COUPLNG QTY 7993 FAC STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 12 | EA | 112 | 4.52 | 506.24
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 13 | 15783 - 13 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GSTRUT STRAP600 STRUT STRAP | GSTRUT STRAP600 STRUT STRAP 6 (=702-6) | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 13 | EA | 114 | 259.75 | 296.12
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 14 | 15783 - 14 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GSTRUT STRAP400 STRUT STRAP | GSTRUT STRAP400 STRUT STRAP 4 (=702-4) | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 14 | EA | 41 | 196.41 | 80.53
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 15 | 15783 - 15 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GSTRUT STRAP200 UNIVERSAL | GSTRUT STRAP200 UNIVERSAL STRUT STRAP 2 (=703-2) | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 15 | EA | 112 | 102.2 | 114.46
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 16 | 15783 - 16 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GAL 600G-US 6IN GALV CONDUIT | GAL 600G-US 6IN GALV CONDUIT 10FT | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 16 | EA | 350 | 6183.15 | 21641.03
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 17 | 15783 - 17 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GAL 400G-US 4IN GALV CONDUIT | GAL 400G-US 4IN GALV CONDUIT 10 FT | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 17 | EA | 130 | 2528.88 | 3287.54
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 18 | 15783 - 18 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | GAL 200G-US 2IN GALV CONDUIT | GAL 200G-US 2IN GALV CONDUIT 10 FT | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 18 | EA | 120 | 854.24 | 1025.09
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 19 | 15783 - 19 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | WIC. THHN 4/0 STR GRN MR | WIC. THHN 4/0 STR GRN MR Cuts: 1 @ 2000 ft | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 19 | EA | 2000 | 5408.6 | 10817.2
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 20 | 15783 - 20 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | CTX 5336040 6X3 BASE SPACER | CTX 5336040 6X3 BASE SPACER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 20 | EA | 350 | 203.28 | 711.48
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 21 | 15783 - 21 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | CTX 5335969 4X3 BASE SPACER | CTX 5335969 4X3 BASE SPACER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 21 | EA | 130 | 115.7 | 150.41
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 22 | 15783 - 22 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | CTX 5335979 2X3 BASE SPACER | CTX 5335979 2X3 BASE SPACER | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 22 | EA | 378 | 91.59 | 346.21
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 23 | 15783 - 23 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 600P 6IN PVC SCH40 PIPE | PVC 600P 6IN PVC SCH40 PIPE Your # 6IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 23 | EA | 710 | 427.68 | 3036.53
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 24 | 15783 - 24 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 400P 4IN SCH40 PVC PIPE | PVC 400P 4IN SCH40 PVC PIPE Your # 4IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 24 | EA | 320 | 231.48 | 740.74
15783 | Fermi Frame 6B PGP - TO#4 - Conduit | 12/21/2025 | Not Yet Acknowledged | TO#4 - Conduit | 25 | 15783 - 25 | 0255-F6B-039 | 0 | Bulks - Electrical | Not Yet Acknowledged | 12/22/2025 07:21:45 CST | Crawford Electric Supply Co., Inc. | CPSO-0255-4-4 | PVC 200P 2IN SCH40 PVC PIPE | PVC 200P 2IN SCH40 PVC PIPE Your # 2IN CONDUIT, SCH40, PVC | # | # | Not assigned | # | # | Not assigned | Material | 01/18/2026 | Not Delivered | Free carrier | 25 | EA | 1010 | 87.69 | 885.67
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 1 | 15809 - 1 | - | 0 | Labor - Engineering | Sent | 12/30/2025 17:02:38 CST | Stanley Consultants, LLC | CPSO-0255 | Engineer 1 | Stanley Billable Titles: Engineer 1, Consultant (E1), Architect 2, Senior Scientist 1, CAD Designer 3, Senior CAD Designer 1 RPS Billable Title: Engineer 1 | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 1 | EA | 103 | 169 | 17407
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 2 | 15809 - 2 | - | 0 | Labor - Engineering | Sent | 12/30/2025 17:02:38 CST | Stanley Consultants, LLC | CPSO-0255 | Consultant | Stanley Billable Titles: Consultant (E2), Senior Consultant (E1), Senior Scientist 2, Principal GIS Analyst RPS Billable Title: Project Management | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 2 | EA | 113 | 184 | 20792
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 3 | 15809 - 3 | - | 0 | Labor - Engineering | Sent | 12/30/2025 17:02:38 CST | Stanley Consultants, LLC | CPSO-0255 | Engineer 2 | Stanley Billable Titles: Engineer 2, Senior Consultant (E2), Senior Consultant (E3), Senior Architect 1, Senior Architect 2, Senior Scientist 3, Senior Land Acquisition Agent 1, Senior Project Controls Specialist 1 RPS Billable Title: Engineer 2 | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 3 | XPK | 111 | 198 | 21978
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 4 | 15809 - 4 | - | 0 | Labor - Engineering | Sent | 12/30/2025 17:02:38 CST | Stanley Consultants, LLC | CPSO-0255 | Senior Engineer 2, Principal Scientist 2 | Stanley Billable Titles: Senior Engineer 2, Principal Scientist 2, Project Manager 1 RPS Billable Title: Senior Engineer 2 | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 4 | EA | 40.5 | 243 | 9841.5
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 5 | 15809 - 5 | - | 0 | Labor - Engineering | Sent | 12/30/2025 17:02:38 CST | Stanley Consultants, LLC | CPSO-0255 | Principal Engineer 2 | Stanley Billable Titles: Principal Engineer 2, Senior Project Manager 1, Principal Project Controls Specialist RPS Billable Title: Principal Engineer 2 | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 5 | EA | 216 | 299 | 64584
15809 | Fermi Frame 6B PGP - TO#3 - Engineering Services (Combined Cycle) | 12/23/2025 | Sent | TO#3 - Engineering Services (Combined Cycle) | 6 | 15809 - 6 | - | 0 | Expenses | Canceled | 12/30/2025 16:54:26 CST | Stanley Consultants, LLC | CPSO-0255 | Expenses | # | # | # | Not assigned | # | # | Not assigned | Service | 12/01/2025 | Not Relevant | N/A | 6 | EA | 1 | 4000 | 4000
15810 | Fermi Matador Project - TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 12/23/2025 | Sent | TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 1 | 15810 - 1 | 0255-TM-046 | 0 | Major Equipment | Sent | 12/24/2025 15:07:49 CST | Lynn Energy Services | CPSO-0255-5-2 | TURB PLC 100 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 1 | EA | 1 | 198247 | 198247
15810 | Fermi Matador Project - TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 12/23/2025 | Sent | TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 2 | 15810 - 2 | 0255-TM-046 | 0 | Major Equipment | Sent | 12/24/2025 15:07:49 CST | Lynn Energy Services | CPSO-0255-5-2 | TURB RIO 100 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 2 | EA | 1 | 71676 | 71676
15810 | Fermi Matador Project - TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 12/23/2025 | Sent | TO#5 - PLC Panels: Turb PLC 100 Panel, Turb RIO 100 Panel & Turb RIO 101 | 3 | 15810 - 3 | 0255-TM-046 | 0 | Major Equipment | Sent | 12/24/2025 15:07:49 CST | Lynn Energy Services | CPSO-0255-5-2 | TURB RIO 101 | # | # | # | Not assigned | # | # | Not assigned | Material | 02/02/2026 | Not Delivered | Free on board | 3 | XPK | 1 | 89328 | 89328
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 1 | 15811 - 1 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 10:59:43 CST | CED Industrial, Inc | CPSO-0255-4-4 | BARE 4/0 SOFT DRAWN 19 STRANDED | WIRE BARESD4/0STR BARE 4/0 SOFT DRAWN 19 STRANDED 0.51 INCH OUTER DIAMETER; SOFT DRAWN BARE COPPER CONDUCTOR MATERIAL; 653 LB/MFT WEIGHT; 4/0 AWG CONDUCTOR SIZE; REEL PACKAGE TYPE; 7 STRANDS STRANDING; APPLICABLE STANDARD ASTM B3; RATED STRENGTH 6459 LB | # | # | Not assigned | # | # | Not assigned | Material | 12/31/2025 | Not Delivered | Free carrier | 1 | EA | 8500 | 4.98 | 42330
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 2 | 15811 - 2 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 10:59:43 CST | CED Industrial, Inc | CPSO-0255-4-4 | 4/0 STR THHN GREEN | WIRE THHN4/0STRGRN 4/0 STR THHN GREEN THHN TYPE; 500 FT; 624 MIL OUTER DIAMETER; COPPER CONDUCTOR MATERIAL; UL 83/758/1063/1581, UL (CANADA AND US) APPROVAL; 600 V VOLTAGE RATING; 195 AMPERE (60 DEG C), 230 AMPERE (75 DEG C), 260 AMPERE (90 DEG C) CURRENT RATING | # | # | Not assigned | # | # | Not assigned | Material | 12/31/2025 | Not Delivered | Free carrier | 2 | EA | 900 | 5.94 | 5346
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 3 | 15811 - 3 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 10:59:43 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2 STR THHN GREEN | WIRE THHN2STRGRN 2 STR THHN GREEN THHN TYPE; 500 FOOT; 378 MIL OUTER DIAMETER; COPPER CONDUCTOR MATERIAL; UL 83/758/1063/1581, UL (CANADA AND US), CSA C22.2 APPROVAL; 600 VOLT VOLTAGE RATING; 95 AMP (60 DEG C), 115 AMP (75 DEG C), 130 AMP (90 DEG C) CURRENT RATING | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 3 | XPK | 3500 | 2.16 | 7560
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 4 | 15811 - 4 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 7100201470 SUPER 33 3/4 X 76' | 3M 33+-3/4X76FT1 7100201470 SUPER 33 3/4 X 76' 06132 SUPER 33+ 3/4 IN X 76 FT | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 4 | EA | 20 | 6.8 | 136
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 5 | 15811 - 5 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 11:22:18 CST | CED Industrial, Inc | CPSO-0255-4-4 | ALUM CBL TRAY GROUND CLAMP | ATKOR GWC-A1-Z ALUM CBL TRAY GROUND CLAMP | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 5 | EA | 100 | 7.82 | 782
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 6 | 15811 - 6 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1-5/8X1-5/8 12G HDG SLOT 10FT | UNIST P1000T10HG 1-5/8X1-5/8 12G HDG SLOT 10FT METAL FRAMING, SINGLE TYPE; ASTM A1011 SS GRADE 33 LOW CARBON STEEL MATERIAL; HOT DIP GALVANIZED FINISH; 10 FOOT; 1-5/8 INCH; 1-5/8 INCH; SLOTTED CONFIGURATION; UL E19459, CSA 013669 APPLICABLE STANDARD; 12 GAUGE THICKNESS; COLD FORMED PROCESS | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 6 | EA | 100 | 4.29 | 429
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 7 | 15811 - 7 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1/2-13 SPRING NUT SS316 | UNIST P1010ST 1/2-13 SPRING NUT SS316 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 7 | EA | 8 | 2.45 | 19.6
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 8 | 15811 - 8 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | U-BOLT BEAM CLAMP SINGLE SS4 | UNIST P2785SS U-BOLT BEAM CLAMP SINGLE SS4 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 8 | EA | 8 | 14.41 | 115.28
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 9 | 15811 - 9 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2C 2/0-250 RA GRD CONN 5/8-3/4 | BUR GP6429 2C 2/0-250 RA GRD CONN 5/8-3/4 RD CAST HIGH COPPER ALLOY (BODY), DURIUM (U-BOLT/NUT/LOCKWASHER) MATERIAL; 2-1/8 INCH WIDTH X 2-7/8 INCH HEIGHT SIZE; (2) PARALLEL COPPER CABLE PERPENDICULAR TO COLUMN/PIPE/ROD, DIRECT BURIAL USED ON; U-BOLT TO PIPE/ROD INSTALLATION; UL 467, CSA APPROVAL | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 9 | EA | 86 | 54.34 | 4673.24
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 10 | 15811 - 10 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2AWG 1H 3/8 COMP SHORT | ILSCO CSWS238 2AWG 1H 3/8 COMP SHORT BARREL CU CMP 2 AWG 13/32 T UL CSA SHORT BARRE | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 10 | EA | 2 | 3.55 | 7.1
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 11 | 15811 - 11 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX HEAD CAP SCR SB 1/2 X 1 | HARDW HHCSSB12X1 HEX HEAD CAP SCR SB 1/2 X 1 1/2-13 X 1 HEX BOLT SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 11 | EA | 36 | 2.06 | 74.16
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 12 | 15811 - 12 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 8-2 2C SPLIT BOLT CONN 3/8 | BUR K2C23 8-2 2C SPLIT BOLT CONN 3/8 STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT/STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 15/32 INCH STUD LENGTH; UL, CSA APPROVAL; 2 CONDUCTOR(S); 10 TO 1 AWG SOLID, 8 TO 2 AWG STRANDED CONDUCTOR SIZE; 3/8 INCH-16 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 12 | EA | 102 | 27.2 | 2774.4
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 13 | 15811 - 13 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SB 3/8 | HARDW HNSB38 HEX NUT SB 3/8 3/8-16 HEX NUT SILICON BRONZE 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 13 | EA | 100 | 0.46 | 46
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 14 | 15811 - 14 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SB 3/8 | HARDW FWSB38 FLAT WASHER SB 3/8 3/8 (7/8 OD) FLAT WASHER SILICON BRONZE 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 14 | EA | 200 | 0.39 | 78
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 15 | 15811 - 15 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SB 3/8 | HARDW LWSB38 LOCK WASHER SB 3/8 3/8 LOCK WASHER SILICON BRONZE 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 15 | EA | 100 | 0.21 | 21
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 16 | 15811 - 16 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/8" BRONZE INTERNAL TOOTH | HARDW SBLWINT38 3/8" BRONZE INTERNAL TOOTH LOCK WASHER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 16 | EA | 100 | 0.15 | 15
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 17 | 15811 - 17 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/8"-16 X 1/2" SIL BRZ HEX HEAD | HARDW HHCSSB38X12 3/8"-16 X 1/2" SIL BRZ HEX HEAD CAP SCREW | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 17 | EA | 100 | 1.04 | 104
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 18 | 15811 - 18 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/8"-16 X 1 1/4" SIL BRZ HEX HEAD | HARDW HHCSSB38X114 3/8"-16 X 1 1/4" SIL BRZ HEX HEAD CAP SCREW | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 18 | EA | 100 | 1.24 | 124
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 19 | 15811 - 19 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2HOLE LUG | ILSCO CSWD4/012134 2HOLE LUG CU CMP 4/0 AWG 9/16-1-3/4 T UL CSA SHOR | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 19 | EA | 10 | 8.07 | 80.7
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 20 | 15811 - 20 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SB 1/2 | HARDW FWSB12 FLAT WASHER SB 1/2 1/2 (1-1/4 OD) FLAT WASHER SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 20 | EA | 72 | 0.76 | 54.72
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 21 | 15811 - 21 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SB 1/2 | HARDW LWSB12 LOCK WASHER SB 1/2 1/2 LOCK WASHER SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 21 | EA | 72 | 0.39 | 28.08
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 22 | 15811 - 22 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SB 5/8 | HARDW FWSB58 FLAT WASHER SB 5/8 5/8 (1-1/2 OD) FLAT WASHER SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 22 | EA | 8 | 1.65 | 13.2
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 23 | 15811 - 23 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SB 5/8 | HARDW LWSB58 LOCK WASHER SB 5/8 5/8 LOCK WASHER SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 23 | EA | 8 | 0.82 | 6.56
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 24 | 15811 - 24 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SB 5/8 | HARDW HNSB58 HEX NUT SB 5/8 5/8-11 HEX NUT SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 24 | EA | 8 | 2.18 | 17.44
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 25 | 15811 - 25 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2-2/0 2C SPLIT BOLT CONN 1/2 | BUR K2C26 2-2/0 2C SPLIT BOLT CONN 1/2 STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT/STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 17/32 INCH STUD LENGTH; UL, CSA APPROVAL; 2 CONDUCTOR(S); 2 TO 3/0 AWG SOLID, 2 TO 2/0 AWG STRANDED CONDUCTOR SIZE; 1/2 INCH-13 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 25 | EA | 59 | 34.39 | 2029.01
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 26 | 15811 - 26 | 0255-F6B-036 | 0 | Bulks - Electrical | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1/2" BRONZE INTERNAL TOOTH | HARDW SBLWINT12 1/2" BRONZE INTERNAL TOOTH LOCK WASHER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 26 | EA | 100 | 0.35 | 35
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 27 | 15811 - 27 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SB 1/2 | HARDW HNSB12 HEX NUT SB 1/2 1/2-13 HEX NUT SILICON BRONZE 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 27 | EA | 100 | 0.85 | 85
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 28 | 15811 - 28 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 8-2AWG SPLIT BOLT CONN 3/8 | BUR KC23 8-2AWG SPLIT BOLT CONN 3/8 STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT/STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 15/32 INCH STUD LENGTH; UL, CSA APPROVAL; 1 CONDUCTOR(S); 10 TO 1 AWG SOLID, 8 TO 2 AWG STRANDED CONDUCTOR SIZE; 3/8 INCH-16 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 28 | EA | 2 | 22 | 44
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 29 | 15811 - 29 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2-2/0 SPLIT BOLT 1/2 LONG STUD | BUR KC26B1 2-2/0 SPLIT BOLT 1/2 LONG STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT/STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 1-1/16 INCH STUD LENGTH; UL, CSA APPROVAL; 1 CONDUCTOR(S); 2 TO 3/0 AWG SOLID, 2 TO 2/0 AWG STRANDED CONDUCTOR SIZE; 1/2 INCH-13 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 29 | EA | 85 | 42.71 | 3630.35
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 30 | 15811 - 30 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX HEAD CAP SCR SS 3/8 X | HARDW HHCSSS38X114 HEX HEAD CAP SCR SS 3/8 X 1-1/4 3/8-16 X 1-1/4 HEX BOLT 304 STAINLESS 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 30 | EA | 200 | 0.25 | 50
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 31 | 15811 - 31 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SS 3/8 | HARDW HNSS38 HEX NUT SS 3/8 3/8-16 HEX NUT 304 STAINLESS STEEL 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 31 | EA | 200 | 0.09 | 18
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 32 | 15811 - 32 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SS 3/8 *SPO* | HARDW FWSS38 FLAT WASHER SS 3/8 *SPO* 3/8 (7/8 OD) FLAT WASHER 18-8 STAINLESS 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 32 | EA | 200 | 0.05 | 10
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 33 | 15811 - 33 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SS 3/8 *SPO* | HARDW LWSS38 LOCK WASHER SS 3/8 *SPO* 3/8 LOCK WASHER 304 STAINLESS 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 33 | EA | 200 | 0.06 | 12
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 34 | 15811 - 34 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2AWG 1H 3/8 COMP SHORT | ILSCO CSWS238 2AWG 1H 3/8 COMP SHORT BARREL CU CMP 2 AWG 13/32 T UL CSA SHORT BARRE | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 34 | EA | 1 | 3.55 | 3.55
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 35 | 15811 - 35 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 250MCM - 3/0 TO 250MCM - 3/0 | BUR YGHC29C29 250MCM - 3/0 TO 250MCM - 3/0 CONN 3/0 AWG STRANDED MIN. RUN CONDUCTOR SIZE; 250 KCMIL MAX. RUN CONDUCTOR SIZE; 3/0 AWG STRANDED MIN. TAP CONDUCTOR SIZE; 250 KCMIL MAX. TAP CONDUCTOR SIZE; C SHAPE; COPPER CONDUCTOR MATERIAL; UL 96/467, CSA APPROVAL; COPPER BODY MATERIAL; 997 DIE INDEX | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 35 | EA | 11 | 19.31 | 212.41
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 36 | 15811 - 36 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 2 - 6 TO 2 - 6 C CRIMP | BUR YGHC2C2 2 - 6 TO 2 - 6 C CRIMP 6 AWG SOLID MIN. RUN CONDUCTOR SIZE; 2 AWG STRANDED MAX. RUN CONDUCTOR SIZE; 6 AWG SOLID MIN. TAP CONDUCTOR SIZE; 2 AWG STRANDED MAX. TAP CONDUCTOR SIZE; C SHAPE; COPPER CONDUCTOR MATERIAL; UL 96/467, CSA APPROVAL; COPPER BODY MATERIAL; C DIE INDEX | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 36 | EA | 202 | 8.59 | 1735.18
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 37 | 15811 - 37 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 250MCM - 3/0 TO 2/0 - 6 C CRIMP | BUR YGHC29C26 250MCM - 3/0 TO 2/0 - 6 C CRIMP 3/0 AWG STRANDED MIN. RUN CONDUCTOR SIZE; 250 KCMIL MAX. RUN CONDUCTOR SIZE; 6 AWG SOLID MIN. TAP CONDUCTOR SIZE; 2/0 AWG STRANDED MAX. TAP CONDUCTOR SIZE; C SHAPE; COPPER CONDUCTOR MATERIAL; UL 96/467, CSA APPROVAL; COPPER BODY MATERIAL; 997 DIE INDEX | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 37 | EA | 54 | 19.31 | 1042.74
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 38 | 15811 - 38 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | STATIC DISCHRG REEL | HUBWD HBL50SD STATIC DISCHRG REEL STATIC DISCHARGE, 50FT ,SINGLE LEAD | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 38 | EA | 2 | 511.76 | 1023.52
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 39 | 15811 - 39 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/8 1H FLEX STRAP | BPT 900F 3/8 1H FLEX STRAP 3/8IN , 12/4,10/2,10/3 STRAP, BOX OF 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 39 | EA | 200 | 0.14 | 28
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 40 | 15811 - 40 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | RED INSULATORS | STAN INS38138 RED INSULATORS | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 40 | EA | 8 | 4.06 | 32.48
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 41 | 15811 - 41 | 0255-F6B-036 | 0 | Bulks - Electrical | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/8X48 CU AIR TERM | HARGR 3848CUAT 3/8X48 CU AIR TERM 3/8X48 COPPER AIR TERMINAL | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 41 | EA | 3 | 37.41 | 112.23
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 42 | 15811 - 42 | 0255-F6B-036 | 0 | Bulks - Electrical | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | CU RECTANGULAR FLAT BASE | HARGR 151381I CU RECTANGULAR FLAT BASE | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 42 | EA | 3 | 29.28 | 87.84
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 43 | 15811 - 43 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 14AWG CU LTNG CDR | HARGR 24250 14AWG CU LTNG CDR 250FT - 24X14 CU LP CONDUCTOR | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 43 | EA | 3 | 959.25 | 2877.75
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 44 | 15811 - 44 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 3/4X10FT COPPER GROUND ROD | GRNDR 3410CGR 3/4X10FT COPPER GROUND ROD COPPER-BONDED GROUND ROD, POINTED, 3/4IN DIA, 10FT , 10 MIL PLATING, 12.6 LB | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 44 | EA | 96 | 33.24 | 3191.04
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 45 | 15811 - 45 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | THREADED STUD X-BT-MR W10/15 | HILTI 2194341 THREADED STUD X-BT-MR W10/15 SN 8 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 45 | EA | 2 | 2483.53 | 4967.06
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 46 | 15811 - 46 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | U SHAPED FITTING | MISC FS-5311-4 ST4 U SHAPED FITTING | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 46 | EA | 8 | 22.22 | 177.76
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 47 | 15811 - 47 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1-IN-90D-SCH-80-COND-ELL | PVC ELS801 1-IN-90D-SCH-80-COND-ELL STANDARD RADIUS TYPE; PVC MATERIAL; 80 SCHEDULE; UL 651, ETL APPROVAL; 1 INCH TRADE SIZE; 90 DEG BEND ANGLE; PLAIN END STYLE | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 47 | EA | 23 | 4.44 | 102.12
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 48 | 15811 - 48 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1-IN SCH80 COND BELL END | PVC CONDS801 1-IN SCH80 COND BELL END 3600FT | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 48 | EA | 570 | 0.79 | 450.3
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 49 | 15811 - 49 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1 IN STL 1H RIGID COND STRAP | BPT 903S 1 IN STL 1H RIGID COND STRAP 1IN RIGID PIPE STRAP, BOX OF 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 49 | EA | 711 | 0.5 | 355.5
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 50 | 15811 - 50 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX HEAD CAP SCR ZN 14X112 | HARDW HHCSZ14X112 HEX HEAD CAP SCR ZN 14X112 *SPO* 1/4-20 X 1-1/2 HEX BOLT GRADE 2 ZINC 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 50 | EA | 700 | 0.06 | 42
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 51 | 15811 - 51 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER ZINC 1/4 *SPO* | HARDW LWZ14 LOCK WASHER ZINC 1/4 *SPO* 1/4 SPLIT LOCK WASHER ZINC 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 51 | EA | 400 | 0.02 | 8
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 52 | 15811 - 52 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | DROP IN ANCHOR ZINC 1/4 | HARDW DIAZ14 DROP IN ANCHOR ZINC 1/4 1/4-20 DROP IN ANCHORS ( STEEL ) ZINC PLATED | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 52 | EA | 637 | 0.19 | 121.03
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 53 | 15811 - 53 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX HEAD CAP SCR SS 3/8 X | HARDW HHCSSS38X112 HEX HEAD CAP SCR SS 3/8 X 1-1/2 3/8-16 X 1-1/2 HEX BOLT 304 STAINLESS 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 53 | EA | 20 | 0.3 | 6
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 54 | 15811 - 54 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SS 3/8 *SPO* | HARDW FWSS38 FLAT WASHER SS 3/8 *SPO* 3/8 (7/8 OD) FLAT WASHER 18-8 STAINLESS 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 54 | EA | 100 | 0.05 | 5
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 55 | 15811 - 55 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | FLAT WASHER SS 1/2 | HARDW FWSS12 FLAT WASHER SS 1/2 1/2 (1-1/4 OD) FLAT WASHER 18-8 STAINLESS 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 55 | EA | 8 | 0.1 | 0.8
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 56 | 15811 - 56 | 0255-F6B-036 | 0 | Bulks - Electrical | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SS 3/8 *SPO* | HARDW LWSS38 LOCK WASHER SS 3/8 *SPO* 3/8 LOCK WASHER 304 STAINLESS 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 56 | EA | 100 | 0.06 | 6
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 57 | 15811 - 57 | 0255-F6B-036 | 0 | Bulks - Electrical | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | LOCK WASHER SS 1/2 | HARDW LWSS12 LOCK WASHER SS 1/2 1/2 LOCK WASHER 304 STAINLESS 50 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 57 | EA | 8 | 0.1 | 0.8
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 58 | 15811 - 58 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SS 3/8 | HARDW HNSS38 HEX NUT SS 3/8 3/8-16 HEX NUT 304 STAINLESS STEEL 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 58 | EA | 2 | 0.09 | 0.18
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 59 | 15811 - 59 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | HEX NUT SS 1/2 | HARDW HNSS12 HEX NUT SS 1/2 1/2-13 HEX NUT 304 STAINLESS STEEL 100 | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 59 | EA | 8 | 0.18 | 1.44
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 60 | 15811 - 60 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 8X24 CLAY STUB OUT | MISC 8X24 GROUND WELL 8X24 CLAY STUB OUT | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 60 | EA | 30 | 114.12 | 3423.6
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 61 | 15811 - 61 | 0255-F6B-036 | 0 | Bulks - Electrical | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 8" POLYMER COVER | MISC 8-IN GROUND COVER 8" POLYMER COVER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 61 | EA | 30 | 54.12 | 1623.6
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 62 | 15811 - 62 | 0255-F6B-036 | 0 | 0 | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 8-2 2C SPLIT BOLT 3/8 LONG | BUR K2C23B1 8-2 2C SPLIT BOLT 3/8 LONG STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT/STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 31/32 INCH STUD LENGTH; UL, CSA APPROVAL; 2 CONDUCTOR(S); 10 TO 1 AWG SOLID, 8 TO 2 AWG STRANDED CONDUCTOR SIZE; 3/8 INCH-16 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 62 | EA | 23 | 24.91 | 572.93
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 63 | 15811 - 63 | 0255-F6B-036 | 0 | 0 | Sent | 12/27/2025 19:20:57 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1-4/0 SPLIT BOLT 5/8 LONG STUD | BUR KC28B1 1-4/0 SPLIT BOLT 5/8 LONG STUD LEADED BRONZE ALLOY MATERIAL; CABLE TO FLAT SURFACE, CABLE TO STEEL STRUCTURE/FENCE POST/TRANSFORMER USED ON; 1.25 INCH STUD LENGTH; UL, CSA APPROVAL; 1 CONDUCTOR(S); 1 TO 4/0 AWG SOLID/STRANDED CONDUCTOR SIZE; 5/8 INCH-11 TPI STUD DIAMETER | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 63 | EA | 4 | 74.71 | 298.84
15811 | Fermi Frame 6B PGP - TO#4 - Plant Grounding | 12/23/2025 | Follow-Up Document Created | TO#4 - Plant Grounding | 64 | 15811 - 64 | 0255-F6B-036 | 0 | 0 | Follow-Up Document Created | 01/02/2026 12:55:26 CST | CED Industrial, Inc | CPSO-0255-4-4 | 1/4" X 4" X 12" COPPER FLAT BAR | STAN CUBAR14 1/4" X 4" X 12" COPPER FLAT BAR | # | # | Not assigned | # | # | Not assigned | Material | 12/24/2025 | Not Delivered | Free carrier | 64 | EA | 1 | 87.41 | 87.41
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 1 | 15813 - 1 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-04; 8" TEMP CONE STRAINER | ITEM # SP-04 - SERVICE WATER TITAN PS15C0800 8 PS15-CS CARBON STEEL TEMPORARY CONE STRAINER 150 MESH LINED INSIDE CS 150 % OAR 150 LB RAISED FACE 3 INCH HANDLE | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 1 | EA | 1 | 370 | 370
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 2 | 15813 - 2 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-08; F-400A/B - 4" SS STRAINER | ITEM # SP-08 - DEMIN WATER TAG# F-400A/B TITAN BS85S0400 4 BS85-SS STAINLESS STEEL T316 150# FLANGED END BASKET STRAINER 1/16 PERF SS T304 | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 2 | EA | 2 | 3490 | 6980
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 3 | 15813 - 3 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-07; F-600A/B - 6" CS STRAINER | ITEM # SP-07 - SERVICE WATER TAG# F-600A/B TITAN BS85C0600 6 BS85-CS CARBON STEEL 150# FLANGED END BASKET STRAINER 1/8 PERF SS T304 WITH SS TAG F-600A/B WITH 1'' NPT DRAIN | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 3 | XPK | 2 | 3026 | 6052
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 4 | 15813 - 4 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-09; F-601 - 3" CS STRAINER | ITEM # SP-09 - SERVICE WATER TAG# F-601 TITAN BS85C0300 3 BS85-CS CARBON STEEL 150# FLANGED END BASKET STRAINER 1/16 PERF SS T304 WITH SS TAG F-601 WITH 1'' NPT DRAIN | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 4 | EA | 1 | 1317 | 1317
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 5 | 15813 - 5 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-02; F-201A/B,F-300A/B -3" SS STRAINER | ITEM #SP-02 - SERVICE WATER TAG# F-201A/B, F-300A/B TITAN BS85S0300 3 BS85-SS STAINLESS STEEL T316 150# FLANGED END BASKET STRAINER 1/16 PERF SS T304 WITH SS TAG F-201A/B, F-300A/B WITH 1'' NPT DRAIN | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 5 | EA | 4 | 2197 | 8788
15813 | Fermi Frame 6B PGP - TO#4 - Specialty Items List (Temporary & Basket Strainers) | 12/27/2025 | Sent | TO#4 - Specialty Items List (Temporary & Basket Strainers) | 6 | 15813 - 6 | 0255-F6B-047 | 0 | 0 | Sent | 12/28/2025 09:15:40 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | SP-03; 10" CS CONE TEMP STRAINER | ITEM # SP-03 - GLYCOL COOLING WATER TITAN PS15C1000 10IN PS15-CS CARBON STEEL TEMPORARY CONE STRAINER 150 MESH LINED INSIDE CS 150 % OAR 150 LB RAISED FACE 3 INCH HANDLE HANDLE ENGRAVED WITH SP-03 | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 6 | EA | 2 | 541 | 1082
15814 | Fermi Matador TM2500 - TO#5 - Basket Strainers | 12/27/2025 | Sent | TO#5 - Basket Strainers | 1 | 15814 - 1 | 0255-TM-048 | 0 | 0 | Sent | 12/28/2025 09:40:37 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-5-2 | 3" CS BASKET STRAINER | TAGS#: F-1420A/B, F-2420A/B, F-3420A/B - SERVICE WATER TITAN BS85C0300 3 BS85-CS CARBON STEEL 150# FLANGED END BASKET STRAINER 1/16 PERF SS T304 WITH SS TAG F-1420A/B, F-2420A/B, F-3420A/B WITH 1'' NPT DRAIN | # | # | Not assigned | # | # | Not assigned | Material | 01/20/2026 | Not Delivered | Free carrier | 1 | EA | 6 | 1317 | 7902
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 1 | 15815 - 1 | 0255-F6B-032A | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Vaults - Pre cast Standard 10x8x7' | Mfgr: Champion PreCast | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Delivered | Free carrier | 1 | EA | 3 | 14512.5 | 43537.5
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 2 | 15815 - 2 | 0255-F6B-032B | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Vault - Pre cast 6x6x7’ | Mfgr: Champion PreCast | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Delivered | Free carrier | 2 | EA | 4 | 10732.5 | 42930
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 3 | 15815 - 3 | 0255-F6B-032A | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Concrete trench 2x2' | Mfgr: Vaugh Concrete Products | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Delivered | Free carrier | 3 | XPK | 430 | 306 | 131580
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 4 | 15815 - 4 | 0255-F6B-032B | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Concrete trench 2x3' | # | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Delivered | Free carrier | 4 | EA | 300 | 390 | 117000
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 5 | 15815 - 5 | 0255-F6B-032B | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Concrete trench 2x5 | # | # | # | Not assigned | # | # | Not assigned | Material | 01/03/2026 | Not Delivered | Free carrier | 5 | EA | 30 | 543.6 | 16308
15815 | Fermi Frame 6B PGP - TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 12/27/2025 | Sent | TO#4 - Pre-Cast Duct Bank Vaults & Trenches | 6 | 15815 - 6 | 0255-F6B-032B | 0 | 0 | Sent | 12/31/2025 15:38:59 CST | Zephyr 5001, LLC | CPSO-0255-4-4 | Shipping Precast Utility Vaults | # | # | # | Not assigned | # | # | Not assigned | Service | 01/03/2026 | Not Relevant | Free carrier | 6 | EA | 7 | 3200 | 22400
15816 | Fermi Matador TM2500 - TO#5 - Pumps | 12/28/2025 | Sent | TO#5 - Pumps | 1 | 15816 - 1 | 0255-TM-049 | 0 | 0 | Sent | 12/29/2025 10:20:08 CST | Magnatex Pumps, Inc. | CPSO-0255-5-2 | Slop Water Pumps | MODEL: TE120-1041 TAG#: P-1421 THRU P-1426, P-2421 THRU P-2426, P-3421 THRU P-3429 | # | # | Not assigned | # | # | Not assigned | Material | 01/19/2026 | Not Delivered | Free carrier | 1 | EA | 21 | 8165 | 171465
15816 | Fermi Matador TM2500 - TO#5 - Pumps | 12/28/2025 | Sent | TO#5 - Pumps | 2 | 15816 - 2 | 0255-TM-049 | 0 | 0 | Sent | 12/29/2025 10:20:08 CST | Magnatex Pumps, Inc. | CPSO-0255-5-2 | Service Water Pumps | MODEL: 3596M 3X4-10H WCB-11 TAG#: P-1420A/B, P-2420A/B, P-3420A/B | # | # | Not assigned | # | # | Not assigned | Material | 01/19/2026 | Not Delivered | Free carrier | 2 | EA | 6 | 14160 | 84960
15818 | Fermi Matador TM2500 - TO#5 - Rebar | 12/29/2025 | Not Yet Acknowledged | TO#5 - Rebar | 1 | 15818 - 1 | 0255-TM-050 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:47:28 CST | Katy Steel Co. Inc. | CPSO-0255-5-9 | Foundations Rebar | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/05/2026 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 60000
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 1 | 15819 - 1 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1/2 X 10" ROD F1554 GR.36 GALV | LI 1 1/2 X 10" ROD F1554 GR.36 GALV 3"TOP 1"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01002 (QTY 4) DWG: P02.03-CV-120-DWG-01003 (QTY 4) | DWG: P02.03-CV-120-DWG-01002 Ammonia Truck Unloading DWG: P02.03-CV-120-DWG-01003 SCR Ammonia Skid | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 1 | EA | 8 | 5.32 | 42.56
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 2 | 15819 - 2 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 3/4 X 15" ROD F1554 GR.36 GALV | LI 2 3/4 X 15" ROD F1554 GR.36 GALV 3"TOP 2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01104 (QTY 8) DWG: P02.03-CV-120-DWG-01106 (QTY 4) DWG: P02.03-CV-120-DWG-01108 (QTY 4) | DWG: P02.03-CV-120-DWG-01104 STEP DOWN TRANSFORMERS AT-1&AT-2 DWG: P02.03-CV-120-DWG-01106 STEP DOWN TRANSFORMER AT-11 DWG: P02.03-CV-120-DWG-01108 STEP DOWN TRANSFORMER AT-22 | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 2 | EA | 16 | 7.85 | 125.6
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 3 | 15819 - 3 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 7/8 X 15" ROD F1554 GR.36 GALV | LI 3 7/8 X 15" ROD F1554 GR.36 GALV 3"TOP 2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01105 | DWG: P02.03-CV-120-DWG-01105 STEP DOWN TRANSFORMER AT-3 | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 3 | XPK | 4 | 9.33 | 37.32
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 4 | 15819 - 4 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1/2 X 15" ROD F1554 GR.36 GALV | ITEM 4 1/2 X 15" ROD F1554 GR.36 GALV 3"TOP 2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01107 | DWG: P02.03-CV-120-DWG-01107 STEP DOWN TRANSFORMER AT-21 | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 4 | EA | 4 | 5.78 | 23.12
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 5 | 15819 - 5 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 1 X 19-1/2" ROD F1554 GR.36 GALV | ITEM 5 1 X 19-1/2" ROD F1554 GR.36 GALV 8"TOP 1-1/2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01202 | DWG: P02.03-CV-120-DWG-01202 TEMPERING AIR FAN FOUNDATION 1 - FILTER SUPPORT ANCHOR BOLT | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 5 | EA | 16 | 14.25 | 228
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 6 | 15819 - 6 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 3/4 X 16" ROD F1554 GR.36 GALV | ITEM 6 3/4 X 16" ROD F1554 GR.36 GALV 5"TOP 1-1/2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-01202 | DWG: P02.03-CV-120-DWG-01202 TEMPERING AIR FAN FOUNDATION 2 - SKID ANCHOR BOLT | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 6 | EA | 16 | 8 | 128
15819 | Fermi Frame 6B PGP - TO#4 - Anchor Bolts (Misc Foundations) | 12/29/2025 | Not Yet Acknowledged | TO#4 - Anchor Bolts (Misc Foundations) | 7 | 15819 - 7 | 0255-F6B-051 | 0 | 0 | Not Yet Acknowledged | 12/29/2025 09:26:19 CST | Madden Bolt Corporation | CPSO-0255-4-9 | 3/4 X 12" ROD F1554 GR.36 GALV | ITEM 7 3/4 X 12" ROD F1554 GR.36 GALV 4"TOP 1-1/2"BOT W/ (1) HHN TACK 3 PLCS W/ (1) HHN & (1) F436 F/W DWG: P02.03-CV-120-DWG-04401 | DWG: P02.03-CV-120-DWG-04401 CT CONTROL MODULE | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 7 | EA | 4 | 7.42 | 29.68
15820 | Fermi Frame 6B PGP - TO#4 - Aggregates (Concrete) | 12/29/2025 | Sent | TO#4 - Aggregates (Concrete) | 1 | 15820 - 1 | - | 0 | 0 | Sent | 12/29/2025 10:21:25 CST | Amarillo Cotton Warehouse, LP | CPSO-0255-4-9 | 4000PSI Concrete ($155/yard) | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/05/2026 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 400000
15820 | Fermi Frame 6B PGP - TO#4 - Aggregates (Concrete) | 12/29/2025 | Sent | TO#4 - Aggregates (Concrete) | 2 | 15820 - 2 | - | 0 | 0 | Sent | 12/29/2025 10:21:25 CST | Amarillo Cotton Warehouse, LP | CPSO-0255-4-9 | Delivery and Misc Fees | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/05/2026 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 40000
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 1 | 15843 - 1 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" 150# GATE VALVE SW | WARREN 0.5IN 1156-S 1/2in 150# GATE VALVE, SOCKETWELD, CF3M BODY, 316L TRIM, PTFE GASKET. Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 1 | EA | 9 | 206 | 1854
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 2 | 15843 - 2 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GATE VALVE CLASS 800 THD X SW | WARREN 1/2IN 801-TS-624 1/2IN GATE VALVE, CLASS 800, THD X SW END CONNECTIONS, 316/316L BODY, BOLTED BONNET BODY STYLE, 316/HF NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 316/HF NACE WEDGE/DISC/BALL, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 2 | EA | 10 | 144 | 1440
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 3 | 15843 - 3 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GATE VALVE CLASS 800 SW | WARREN 1/2IN 801-S-624 1/2IN GATE VALVE, CLASS 800, SW END CONNECTIONS, 316/316L BODY, BOLTED BONNET BODY STYLE, 316/HF NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 316/HF NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 3 | XPK | 12 | 144 | 1728
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 4 | 15843 - 4 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GATE VALVE CLASS 800 THD X SW | WARREN 1/2IN 851-8-TS-624 1/2IN GATE VALVE, CLASS 800, THD X SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 4 | EA | 2 | 48 | 96
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 5 | 15843 - 5 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GATE VALVE CLASS 800 SW | WARREN 1/2IN 851-8-S-624 1/2IN GATE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 5 | EA | 8 | 48 | 384
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 6 | 15843 - 6 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GLOBE VALVE CLASS 800 SW | WARREN 1/2IN 852-8-S-624 1/2IN GLOBE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 6 | EA | 3 | 45 | 135
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 7 | 15843 - 7 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1/2" GATE VALVE CLASS 800 THD X SW | WARREN 1/2IN 851-8-TS-624 1/2IN GATE VALVE, CLASS 800, THD X SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 7 | EA | 18 | 48 | 864
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 8 | 15843 - 8 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3/4" GATE VALVE CLASS 800 SW | WARREN 3/4IN 801-S-624 3/4IN GATE VALVE, CLASS 800, SW END CONNECTIONS, 316/316L BODY, BOLTED BONNET BODY STYLE, 316/HF NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 316/HF NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME 6-8 WEEKS ARO.CAN MOD THR-SWE ENDS IF LEAD TIME NEEDS TO BE SHORTE | # | # | Not assigned | # | # | Not assigned | Material | 02/24/2026 | Not Delivered | Free carrier | 8 | EA | 4 | 155 | 620
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 9 | 15843 - 9 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3/4" GATE VALVE CLASS 800 THD X SW | WARREN 3/4IN 801-TS-624 3/4IN GATE VALVE, CLASS 800, THD X SW END CONFIGURATION, BOLTED BONNET BODY STYLE, 316/HF NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 316/HF NACE WEDGE/DISC/BALL, 316/316L BODY, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 9 | EA | 21 | 155 | 3255
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 10 | 15843 - 10 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3/4" GATE VALVE CLASS 800 THD X SW | WARREN 3/4IN 851-8-TS-624 3/4IN GATE VALVE, CLASS 800, THD X SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 10 | EA | 3 | 51 | 153
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 11 | 15843 - 11 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3/4" GATE VALVE CLASS 800 THD X SW | WARREN 3/4IN 851-8-TS-624 3/4IN GATE VALVE, CLASS 800, THD X SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 11 | EA | 27 | 51 | 1377
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 12 | 15843 - 12 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1" GATE VALVE CLASS 800 SW | WARREN 1IN 851-8-S-624 1IN GATE VALVE, CLASS 800, SW ENDS, CS BODY, TRIM 8, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 12 | EA | 3 | 64 | 192
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 13 | 15843 - 13 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1" GLOBE VALVE CLASS 800 SW | WARREN 1IN 852-8-S-624 1IN GLOBE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 13 | EA | 12 | 68 | 816
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 14 | 15843 - 14 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1 1/2" GATE VALVE CLASS 800 SW | WARREN 1.5IN 801-S-624 1.5IN GATE VALVE, CLASS 800, SW END CONNECTIONS, 316/316L BODY, BOLTED BONNET BODY STYLE, 316/HF NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 316/HF NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 14 | EA | 3 | 403 | 1209
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 15 | 15843 - 15 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1 1/2" GATE VALVE CLASS 800 SW | WARREN 1.5IN 851-8-S-624 1.5IN GATE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 15 | EA | 4 | 130 | 520
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 16 | 15843 - 16 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 1 1/2" GLOBE VALVE CLASS 800 SW | WARREN 1.5IN 852-8-S-624 1.5IN GLOBE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 16 | EA | 3 | 135 | 405
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 17 | 15843 - 17 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 2" 150# GATE VALVE RF | WARREN 2IN 1156-12N-624 2IN 150# GATE VALVE RF, CF8M BODY, TRIM 12, PTFE GASKET Note: LEADTIME STOCK ARO OFFERING CF8M BODY | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 17 | EA | 2 | 588 | 1176
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 18 | 15843 - 18 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 2" 150# GATE VALVE SW | WARREN 2IN 1156 2IN 150# GATE VALVE, SOCKETWELD, CF3M BODY, 316L TRIM, PTFE GASKET. Note: LEADTIME 8-10 WEEKS | # | # | Not assigned | # | # | Not assigned | Material | 03/10/2026 | Not Delivered | Free carrier | 18 | EA | 3 | 617 | 1851
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 19 | 15843 - 19 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 2" GATE VALVE CLASS 800 SW | WARREN 2IN 851-8-S-624 2IN GATE VALVE, CLASS 800, SW END CONNECTIONS, A/SA105 BODY, BOLTED BONNET BODY STYLE, 8/NACE TRIM/STEM/HINGE PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL, OS&Y, HANDWHEEL OPERATOR Note: LEADTIME STOCK | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 19 | EA | 3 | 169 | 507
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 20 | 15843 - 20 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3" GLOBE VALVE CLASS 150 RF | WARREN 3IN 2156-12N-624 3IN GLOBE VALVE, CLASS 150, RF FLANGED ENDS, CF8M/12N BODY, BOLTED BONNET, TRIM 12, OS&Y, NACE, HANDWHEEL OPERATOR Note: LEADTIME STOCK ARO OFFERING CF8M BODY | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 20 | EA | 2 | 1216 | 2432
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 21 | 15843 - 21 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3" 150# RF GATE VALVE | WARREN 3IN 1156-12N-624 3" 150# RF GATE VALVE, CF8M BODY, TRIM 12 NACE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO OFFERING CF8M BODY | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 21 | EA | 17 | 1072 | 18224
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 22 | 15843 - 22 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 3" SWING CHECK VALVE CLASS 150 | WARREN 3IN 3155-8N 3IN SWING CHECK VALVE, CLASS 150, FULL PORT, RF END CONFIGURATION, WCB BODY, FORGED BODY STYLE, 8/NACE TRIM/STEM/HING PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL Note: LEADTIME STOCK ARO OFFERING TRIM 8 | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 22 | EA | 3 | 327 | 981
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 23 | 15843 - 23 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 14" FULL PORT BALL VALVE | WARREN 4IN 6306FS D014" 300# FULL PORT BALL VALVE, RF CONNECTIONS, CF8M BODY, 316 TRIM, GRAPHITE GASKET, MPTFE SEAT, LEVER OPERATED Note: Leadtime STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 23 | EA | 3 | 2725 | 8175
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 24 | 15843 - 24 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 4" BALL VALVE CLASS 150 | WARREN 4IN 46155FS 4IN BALL VALVE, CLASS 150, FULL PORT, RF ENDS, CS BODY, SS TRIM, MPTFE SEAT, LEVER OPERATOR Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 24 | EA | 14 | 796 | 11144
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 25 | 15843 - 25 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 4" 150# RF GLOBE VALVE | WARREN 4IN 2155-8N-623 4" 150# RF FULL-PORT GLOBE VALVE, WCB BODY, TRIM 8 NACE, GRAPHITE GASKET, HANDWHEEL. Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 25 | EA | 1 | 772 | 772
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 26 | 15843 - 26 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 150# RF GATE VALE | WARREN 6IN 1156-12N-624 6" 150# RF GATE VALE, CF8M BODY, TRIM 12 NACE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 26 | EA | 1 | 2740 | 2740
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 27 | 15843 - 27 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 150# RF GATE VALVE | WARREN 6IN 1155-8N-624 6" 150# RF GATE VALVE, WCB BODY, TRIM 8 NACE, BOLTED BONNET BODY STYLE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 27 | EA | 2 | 893 | 1786
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 28 | 15843 - 28 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 300# RF GATE VALVE | WARREN 6IN 1305G-8N-RP591 6" 300# FULL PORT RF GATE VALVE, WCB BODY, TRIM 8 NACE, GEAR OPERATED Note: LEADTIME 15-17 WEEKS | # | # | Not assigned | # | # | Not assigned | Material | 04/28/2026 | Not Delivered | Free carrier | 28 | EA | 1 | 2219 | 2219
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 29 | 15843 - 29 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" CLASS 900 PRESSURE SEAL, GATE VALVE | POWELL 6IN 1903JC5GXXX 6IN CLASS 900, PRESSURE SEAL, GATE VALVE, SCH 80/80S, A216 WCB, API TRIM 5, GRAPHITE PACKING, METALLIC GASKET Note: LEADTIME 2 Pcs STOCK, 1Pc 4 WEEKS | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 29 | EA | 3 | 10399 | 31197
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 30 | 15843 - 30 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 150# LUG STYLE BUTTERFLY VALVE | WARREN 6IN 9156-26RMGLLFS 6" 150# LUG STYLE BUTTERFLY VALVE, CF8M BODY, 316SS TRIM W/ 17 4 PH STEM, MPTFE SEAT RING, GRAPHITE GASKET, LEVER OPERATED Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 30 | EA | 9 | 1214 | 10926
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 31 | 15843 - 31 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 300# RF FLANGED PLUG VALVE | DURCO 6IN G4-31C810T1M33A 6" 300# RF FLANGED PLUG VALVE, CARBON STEEL BODY, SS PLUG, TEFLON SLEEVE, GEAR OPERATED Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 31 | EA | 1 | 5066 | 5066
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 32 | 15843 - 32 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 150# RF FULL-PORT GLOBE VALVE | WARREN 6IN 2155-8N-624 6" 150# RF FULL-PORT GLOBE VALVE, WCB BODY, TRIM 8 NACE, GRAPHITE GASKET, HANDWHEEL. Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 32 | EA | 1 | 1193 | 1193
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 33 | 15843 - 33 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 300# RF FULLPORT GLOBE VALVE | WARREN 6IN 2305G-8N-623 6" 300# RF FULLPORT GLOBE VALVE, WCB BODY, TRIM 8 NACE, GRAPHITE GASKET, GEAR OPERATED Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 33 | EA | 3 | 2828 | 8484
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 34 | 15843 - 34 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 6" 600# FULL PORT RF GLOBE VALVE | WARREN 6IN 2605G-8N-623 6" 600# FULLPORT RF GLOBE VALVE, WCB BODY, TRIM 8 NACE, GRAPHITE BASKET, BOLTED BONNET, GEAR OPERATED Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 34 | EA | 1 | 5060 | 5060
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 35 | 15843 - 35 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 8" 150# RF FULLPORT BALL VALVE | WARREN 8IN 6155FS-G 8" 150# RF FULLPORT BALL VALVE, WCB BODY, F316 TRIM, MPTFE, GRAPHITE GASKET, GEAR OPERATED. Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 35 | EA | 3 | 4497 | 13491
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 36 | 15843 - 36 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 8" CLASS 150 SWING CHECK VALVE | WARREN 8IN 3155-8N 8" IN SWING CHECK VALVE, CLASS 150, FULL PORT, RF END CONFIGURATION, WCB BODY, FORGED BODY STYLE, 8/NACE TRIM/STEM/HING PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 36 | EA | 1 | 1345 | 1345
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 37 | 15843 - 37 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 8" 150# RF GATE VALVE | WARREN 8IN 1155-8N-624 8IN 150# RF GATE VALVE, WCB BODY, TRIM 8 NACE, BOLTED BONNET BODY STYLE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 37 | EA | 9 | 1396 | 12564
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 38 | 15843 - 38 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 8" CLASS 150 SWING CHECK VALVE | WARREN 8IN 3155-8N 8" IN SWING CHECK VALVE, CLASS 150, FULL PORT, RF END CONFIGURATION, WCB BODY, FORGED BODY STYLE, 8/NACE TRIM/STEM/HING PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 38 | EA | 3 | 1345 | 4035
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 39 | 15843 - 39 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 10" 600# RF GATE VALVE | WARREN 10IN 1605G-8N-624 10" 600# RF GATE VALVE, WCB BODY, TIME 8 NACE, GRAPHITE GASKET, GEAR OPPERATED. Note: LEADTIME 11-13 WEEKS | # | # | Not assigned | # | # | Not assigned | Material | 03/31/2026 | Not Delivered | Free carrier | 39 | EA | 3 | 7472 | 22416
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 40 | 15843 - 40 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 10" 300# RF GATE VALVE | WARREN 10IN 1305G-8N-624 10" 300# RF GATE VAVLE, WCB BODY, TRIM 8 NACE, GRAPHITE GASKET, GEAR OPERATED. Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 40 | EA | 1 | 5028 | 5028
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 41 | 15843 - 41 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 16" CLASS 150 SWING CHECK VALVE | WARREN 16IN 3155-8N 16" IN SWING CHECK VALVE, CLASS 150, FULL PORT, RF END CONFIGURATION, WCB BODY, FORGED BODY STYLE, 8/NACE TRIM/STEM/HING PIN, GRAPHITE GASKET, 8/NACE WEDGE/DISC/BALL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 41 | EA | 2 | 6065 | 12130
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 42 | 15843 - 42 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 16" 150# RF GATE VALVE | WARREN 16IN 1155G-8N-624 16" 150# RF GATE VALVE, WCB BODY, TRIM 8 NACE, BOLTED BONNET, GRAPHITE GASKET, GEAR OPERATED Note: LEADTIME 3-4 WEEKS ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/27/2026 | Not Delivered | Free carrier | 42 | EA | 6 | 5926 | 35556
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 43 | 15843 - 43 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 4" 150# RF GLOBE VALVE | WARREN 4IN 2156-12N-624 4" 150# RF GLOBE VALVE, CF8M BODY, TRIM 12 NACE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 43 | EA | 1 | 1753 | 1753
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 44 | 15843 - 44 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 4" 150# RF GATE VALVE | WARREN 4IN 1155-8N-624 4" 150# RF GATE VALVE, WCB BODY, TRIM 8 NACE, BOLTED BONNET BODY STYLE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 44 | EA | 16 | 568 | 9088
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 45 | 15843 - 45 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 4" 150# RF GATE VALVE | WARREN 4IN 1156-12N-624 4IN 150# RF GATE VALVE, CF8M BODY, TRIM 12 NACE, GRAPHITE GASKET, HANDWHEEL Note: LEADTIME STOCK ARO OFFERING CF8M BODY | # | # | Not assigned | # | # | Not assigned | Material | 01/05/2026 | Not Delivered | Free carrier | 45 | EA | 7 | 2234 | 15638
15843 | Fermi Frame 6B PGP - TO#4 - Manual Valves | 12/30/2025 | Sent | TO#4 - Manual Valves | 46 | 15843 - 46 | 0255-F6B-052 | 0 | 0 | Sent | 12/31/2025 15:33:32 CST | Fluid Flow Products dba New Gen Products | CPSO-0255-4-2 | 18" 150# RF GATE VALVE | WARREN 18IN 1155G-8N-624 18" 150# RF GATE VALVE, WCB BODY, TRIM 8 NACE, BOLTED BONNET, GRAPHITE GASKET, GEAR OPERATED Note: LEADTIME 1-2 WEEKS | # | # | Not assigned | # | # | Not assigned | Material | 01/13/2026 | Not Delivered | Free carrier | 46 | EA | 3 | 8157 | 24471
15844 | Fermi Frame 6B PGP - TO#4 - Soil Testing | 12/30/2025 | Sent | TO#4 - Soil Testing | 1 | 15844 - 1 | - | 0 | 0 | Sent | 12/30/2025 22:55:49 CST | Braun Intertec Corporation | CPSO-0255-4-9 | Soil Testing | 1. Soil Testing 2. Concrete Testing 3. Consulting and/or project management associated with our services | # | # | Not assigned | # | # | Not assigned | Limit | 01/06/2026 | Not Relevant | N/A | 1 | EA | 0 | 0 | 50000
15845 | Fermi Frame 6B PGP - TO#4 - Concrete Washout & Regular Dumpsters Rental | 12/30/2025 | Sent | TO#4 - Concrete Washout & Regular Dumpsters Rental | 1 | 15845 - 1 | 0255-F6B-053 | 0 | 0 | Sent | 12/31/2025 15:37:53 CST | Smash'D | CPSO-0255-4-9 | Concrete Washout Dumpster - Rental (2) | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/06/2026 | Not Relevant | Free carrier | 1 | EA | 0 | 0 | 30000
15845 | Fermi Frame 6B PGP - TO#4 - Concrete Washout & Regular Dumpsters Rental | 12/30/2025 | Sent | TO#4 - Concrete Washout & Regular Dumpsters Rental | 2 | 15845 - 2 | 0255-F6B-053 | 0 | 0 | Sent | 12/31/2025 15:37:53 CST | Smash'D | CPSO-0255-4-9 | Misc Fees, Mileage, Washout, Delivery | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/06/2026 | Not Relevant | Free carrier | 2 | EA | 0 | 0 | 40000
15845 | Fermi Frame 6B PGP - TO#4 - Concrete Washout & Regular Dumpsters Rental | 12/30/2025 | Sent | TO#4 - Concrete Washout & Regular Dumpsters Rental | 3 | 15845 - 3 | 0255-F6B-053 | 0 | 0 | Sent | 12/31/2025 15:37:53 CST | Smash'D | CPSO-0255-4-9 | 30 yard Roll Offs - Rental (4) | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/06/2026 | Not Relevant | Free carrier | 3 | XPK | 0 | 0 | 30000
15851 | Fermi Frame 6B PGP - TO#4 - Cargo Storage | 12/31/2025 | Sent | TO#4 - Cargo Storage | 1 | 15851 - 1 | #N/A | #N/A | #N/A | Sent | 12/31/2025 15:51:37 CST | Boaz Export Crating Company | CPSO-0255-4-5 | Outdoor Storage | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/07/2026 | Not Relevant | N/A | 1 | EA | 0 | 0 | 20000
15851 | Fermi Frame 6B PGP - TO#4 - Cargo Storage | 12/31/2025 | Sent | TO#4 - Cargo Storage | 2 | 15851 - 2 | #N/A | #N/A | #N/A | Sent | 12/31/2025 15:51:37 CST | Boaz Export Crating Company | CPSO-0255-4-5 | Loading/Offloading Charges | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/07/2026 | Not Relevant | N/A | 2 | EA | 0 | 0 | 10000
15851 | Fermi Frame 6B PGP - TO#4 - Cargo Storage | 12/31/2025 | Sent | TO#4 - Cargo Storage | 3 | 15851 - 3 | #N/A | #N/A | #N/A | Sent | 12/31/2025 15:51:37 CST | Boaz Export Crating Company | CPSO-0255-4-5 | Indoor Storage | # | # | # | Not assigned | # | # | Not assigned | Limit | 01/07/2026 | Not Relevant | N/A | 3 | XPK | 0 | 0 | 20000