## Sheet1
Project Phase | Package Description | Tag # | Supplier Name | PO # | Ready to Ship Date
Simple Cycle - New | SCR | Stacks - U-101, U-201, U-301 | Braden Americas | 14723 | 2026-01-20
| Upper Stack Assemblies |  | Braden Americas | 14723 | 1/20/2026 - 2/14/2026
| Lower Stack Assemblies |  | Braden Americas | 14723 | 1/22/2026 - 2/14/26
| Breach Assemblies |  | Braden Americas | 14723 | 1/20/2026 - 2/17/2026
| Inlet Spools |  | Braden Americas | 14723 | 2026-01-30
| SCR Duct |  | Braden Americas | 14723 | 1/20/2026 - 2/13/2026
| Unit 1 DG Duct |  | Braden Americas | 14723 | 2026-02-03
| Unit 1 Inlet Duct |  | Braden Americas | 14723 | 2026-02-12
| Unit 2 DG Duct |  | Braden Americas | 14723 | 2026-02-16
| Unit 2 Inlet Duct |  | Braden Americas | 14723 | 2026-03-02
| Unit 3 DG Duct |  | Braden Americas | 14723 | 2026-03-09
| Unit 3 Inlet Duct |  | Braden Americas | 14723 | 2026-03-17
| Stack Ladder, Platforms and Handrails |  | Braden Americas | 14723 | 2026-01-20
| Expansion Joints (Inlet, Breech Inlet, TA Injector) |  | Braden Americas | 14723 | 2026-01-20
| Unit 1 TA Fan, Filter House, Silencer, Support Steel, Ducting |  | Braden Americas | 14723 | 1/30/2026 - 2/23/2026
| Unit 2 TA Fan, Filter House, Silencer, Support Steel, Ducting |  | Braden Americas | 14723 | 2/6/2026 - 3/6/2026
| Unit 3 TA Fan, Filter House, Silencer, Support Steel, Ducting |  | Braden Americas | 14723 | 2/13/2026 - 3/6/2026
| Ammonia Injection Skids |  | Braden Americas | 14723 | 2026-02-09
| Ammonia Forwarding, Unloading, and tank accessories |  | Braden Americas | 14723 | 2026-02-16
| Ammonia Tank |  | Braden Americas | 14723 | 2026-03-07
| CEMS Cabinets |  | Braden Americas | 14723 | 2026-03-07
| SCR Catalyst |  | Braden Americas | 14723 | 2026-03-27
Simple Cycle - New | U1 Combustion Turbine |  | GE - Ethos | - | 2026-02-24
Simple Cycle - New | U2 Combustion Turbine |  | GE - Ethos | - | 2026-02-26
Simple Cycle - New | U3 Combustion Turbine |  | GE - Ethos | - | 2026-01-23
Simple Cycle - New | U1 Generator |  | GE - Sulzer | - | 2026-02-28
Simple Cycle - New | U2 Generator |  | GE - Sulzer | - | 2026-02-28
Simple Cycle - New | U3 Generator |  | GE - Sulzer | - | 2026-02-28
Simple Cycle - New | Bearings |  | Gulf Coast Bearing and Seal |  | 2026-04-15
Simple Cycle - New | Gearbox |  | IMTT
Simple Cycle - New | GSUs (T1, T2, T3) | T1, T2, T3 | RPS/Eltas | -
Simple Cycle - New | GSU Relay Protection Panel | T1, T2, T3 | Equisales | 14992 | 2026-02-17
Simple Cycle - New | Step Down Transformers | AT-1, AT-2, AT-11, AT-21, AT-22 | Equisales | 14795 | 2025-01-15
Simple Cycle - New | Switchboard & Transfer Switches |  | Equisales | 14795 | Delivered to Lynn
Simple Cycle - New | Wet Surface Air Cooler (WSAC) | WSAC-001 | Alfa Laval | 14986 | 2026-02-12
Simple Cycle - New | Demineralized Water Pumps | P-400A/B | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Waste Water Pumps (WSAC) | P-201A/B | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Glycol Cooling Water Pumps | P-200A/B | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Sump Pumps | P-101/102/103 | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Ammonia Injection Pumps | P-1301/2301/3301 | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Service Water Pumps | P-600A/B | Magnatex | 15462 | 2026-01-05
Simple Cycle - New | Demin. Water Storage Tank | TK-XXX (M-52) | CST | 15399 | 2026-02-17
Simple Cycle - New | Wastewater Storage Tank | TK-XXX | CST | 15399 | 2026-02-17
Simple Cycle - New | Raw / Service Water Storage Tank | TK-XXX | CST | 15399 | 2026-02-17
Simple Cycle - New | Slop Tank |  | CST | 15399 | 2026-02-17
Simple Cycle - New | Compressed Air Supply Skid Package | SK-XXX, D-20 | Atlas Copco | 15450 | 2026-02-02
Simple Cycle - New | Inlet Air Filters |  | Camfil Power | 15423 | 2026-01-10
Simple Cycle - New | Last Chance Filters | F-101A, F-101B, F-201A, F-201B, F-301A, F-301B | Gaumer | 15374 | 2026-03-02
Simple Cycle - New | Control System (Mark IV) & Control Buildings |  | Petrotech | 15330 | 2026-03-10
Simple Cycle - New | MCC Electrical Building |  | Lynn Energy | 15167 | 2026-03-20
Simple Cycle - New | Wastewater Loading Pumps |  | Magnatex | 15461 | 2026-01-30
Simple Cycle - New | Electrical Heat Trace & Insulation |  | Thermon
Simple Cycle - New | Cathodic Protection |  | Corrpro | 15460 | Pending design
Simple Cycle - New | LV MCC |  | Equisales | 15057 | Shipped to Lynn
Simple Cycle - New | Panels: BOP Network Cabinet (MCC Bldg), BOP Server Cabinet (MCC Bldg), BOP-RIO-100 (Relay Bldg) |  | Lynn Energy | 15582 | 2026-03-20
Simple Cycle - New | Cable Tray |  | CED Industrial | 15782 | 2026-01-10
Simple Cycle - New | Plant Grounding |  | CED Industrial | 15811 | 2026-01-05
Simple Cycle - New | Conduit |  | CED Industrial | 15783 | 2026-01-20
Simple Cycle - New | Cable Schedule
Simple Cycle - New | Drilled Piers |  | Tejas Drilled Piers | 15146
Simple Cycle - New | Anchor Bolts/Embedments/Plates |  | Madden Bolts | 15216, 15819 | 12/05/25; 02/01/26
Simple Cycle - New | Rebar/Cages |  | Katy Steel | 15174, 15721 | 11/05/25;11/26/25
Simple Cycle - New | Helical Piles (Pipe Rack) |  | Audubon | 15147, 15640 | Completed
Simple Cycle - New | Pipe Rack: Structural Steel Supply, Fab, & Galv. |  | USA Weld Express | 15171 | 11/28/25; 12/30/25
Simple Cycle - New | Cable Tray Support: Structural Steel Supply, Fab, & Galv.
Simple Cycle - New | Pipe Supports, Hangers, Misc. Hardware
Simple Cycle - New | UG Pipe & Fittings |  | Magnatex | 15461 | 12/05/25; 12/16/25
Simple Cycle - New | AG Pipe & Fittings |  | Magnatex | 15694 | 2026-02-15
Simple Cycle - New | Firewater System (Hydrants)
Simple Cycle - New | Manual Valves |  | Fluid Flow | 15695 | 2026-01-20
Simple Cycle - New | Control Valves |  | Puffer Sweiven | 15704 | 2026-03-02
Simple Cycle - New | Instruments |  | Emerson | 15705 | 2026-02-13
Simple Cycle - New | Specialty Items (Strainers) |  | Fluid Flow | 15812 | 2026-01-20
Simple Cycle - New | PlantPAx control system server and server software |  | The Reynolds Company | 15670 | 2026-01-20
Simple Cycle - New | Glycol Cooling Water Expansion Tank |  | Wiltew | 15737 | 2026-01-26
Simple Cycle - New | Fencing (Electrical Equipment)
Simple Cycle - New | Access Platforms and Stairs
Simple Cycle - New | Plant Lighting
Simple Cycle - Refurb | Switchgear & MCC |  | Shermco | 15441 | 2026-02-10
Simple Cycle - Refurb | IMTT Meefog Skid |  | Meefog
Simple Cycle - Refurb | IMTT Water Injection Skid | SK-1000, SK-2000, SK-3000 | Sulzer Electro Machinery | 15702
Simple Cycle - Refurb | IMTT Water Wash Skid | SK-4000 | Sulzer Electro Machinery
Simple Cycle - Refurb | IMTT Package Control Valves |  | Dooling Machines/Fluid Flow | 15510
Simple Cycle - Refurb | IMTT 480V Swgr |  | Sulzer Electro Machinery | 15702
Simple Cycle - Refurb | 480V Swgr and MCC |  | Crawford
Simple Cycle - Refurb | Bearings |  | Sulzer Electro Machinery
TM2500 | MV/LV Skid |  | Equisales | 15402 | 2025-04-08
TM2500 | Blackstart System |  | Equisales | 15402 | 2025-02-18
TM2500 | GSU Christmas Tree/Cable Structure |  | Equisales | 15402 | 2025-04-08
TM2500 | Station Service Transformer/LDP |  | Equisales | 15402 | 2025-04-08
TM2500 | Last Chance Fuel Filter |  | Modgas
TM2500 | Instruments |  | Emerson
TM2500 | Control Valves
TM2500 | Manual Valves
TM2500 | U/G Piping
TM2500 | A/G Piping
TM2500 | Specialty Items (Strainers) |  | Fluid Flow | 15814 | 2026-01-20
TM2500 | Specialty Items (Hydrants, Safety Showers, Hoses..)
TM2500 | PLC Panels (Turbine PLC-100, Turbine RIO-101, Turbine RIO-100) |  | Lynn Energy | 15810 | 2026-02-06
TM2500 | Slop Water, Service Water Pumps |  | Magnatex | 15816 | 2026-01-30
TM2500 | Rebar/Cages |  | Katy Steel | 15818 | 2026-01-07
TM2500 | Fencing (Electrical Equipment)
TM2500 | Access Platforms and Stairs
TM2500 | Cable Schedule
TM2500 | Grounding
TM2500 | Conduit
TM2500 | Glycol Tank |  | CST
TM2500 | Plant Lighting