## Civ Audit
REC_NO | DWG | REV_NO | SCHED_ID | CAREA | CODE | SYSTEM | LINE_AREA | DESC_ | SZE | FLD_QTY | UOM | FLD_WHRS | SPEC | ERN_QTY | EARN_WHRS | M1_PCT | M1_DESC | M2_PCT | M2_DESC | M3_PCT | M3_DESC | M4_PCT | M4_DESC | M5_PCT | M5_DESC | M6_PCT | M6_DESC | M7_PCT | M7_DESC | M8_PCT | M8_DESC | TEST_PKG1 | CWP | IWP_PLAN_NO | SPL_CNT | IWP_FOREMAN | IWP_GEN_FOREMAN | WHRS_UNIT | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | VAR_AREA | VAR2 | INSU_SPEC | HEAT_TRACE_SPEC | TA_BANK | TA_BAY | TA_LEVEL | PSLIP
1 | P02.03-CV-120-DWG-01104 | 0 | CN-3110 |  | 04110 | *S |  | CONC FDN |  | 9.59 | CY |  |  |  |  | 100% | Exavation | 50% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | AT-1 FDN
2 | P02.03-CV-120-DWG-01104 | 0 | CN-3150 |  | 04110 | *S |  | CONC FDN |  | 9.59 | CY |  |  |  |  | 100% | Exavation | 50% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | AT-2 FDN
3 | P02.03-CV-120-DWG-01105 | 0 | CN-3070 |  | 04110 | *S |  | CONC FDN |  | 9.19 | CY |  |  |  |  | 100% | Exavation | 50% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | AT-3 FDN
4 | P02.03-CV-120-DWG-00101 | 0 | *C |  | 04130 | *S |  | CONC FDN |  | 76.61 | CY |  |  |  |  | 100% | Exavation | 75% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | GTG-1 FOUNDATION
5 | P02.03-CV-120-DWG-00101 | 0 | *C |  | 04130 | *S |  | CONC FDN |  | 76.61 | CY |  |  |  |  | 100% | Exavation | 75% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | GTG-2 FOUNDATION
6 | P02.03-CV-120-DWG-00101 | 0 | *C |  | 04130 | *S |  | CONC FDN |  | 76.61 | CY |  |  |  |  | 100% | Exavation | 75% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | GTG-3 FOUNDATION
7 | P02.03-CV-120-DWG-01106 | 0 | *C |  | 04110 | *S |  | CONC FDN |  | 5.62 | CY |  |  |  |  | 100% | Exavation | 50% | Formwork | 75% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | AT-11 FDN STEP DOWN TRANSFORMER
8 | P02.03-CV-120-DWG-01107 | 0 | *C |  | 04110 | *S |  | CONC FDN |  | 5.96 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | AT-21 FDN STEP DOWN TRANSFORMER
9 | P02.03-CV-120-DWG-01108 | 0 | *C |  | 04110 | *S |  | CONC FDN |  | 6.47 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | AT-22 FDN STEP DOWN TRANSFORMER
10 | P02.03-CV-120-DWG-03001 | 0 | *C |  | 04120 | *S |  | CONC FDN |  | 11.36 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | WASH WATER SKID FDN
11 | P02.03-CV-120-DWG-01501 | 0 | *C |  | 04110 | *S |  | CONC FDN |  | 8.03 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | WATER INJECTION SKID FDN 1
12 | P02.03-CV-120-DWG-01501 | 1 | *C |  | 04110 | *S |  | CONC FDN |  | 8.03 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | WATER INJECTION SKID FDN 2
13 | P02.03-CV-120-DWG-01501 | 1 | CN-4250 |  | 04110 | *S |  | CONC FDN |  | 8.03 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | WATER INJECTION SKID FDN 3
14 | P02.03-CV-120-DWG-05001 | 1 | CN-5300 |  | 04110 | *S |  | CONC FDN |  | 6.74 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | MEEFOG PUMP SKID FDN 1
15 | P02.03-CV-120-DWG-05001 | 1 | CN-5300 |  | 04110 | *S |  | CONC FDN |  | 6.74 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | MEEFOG PUMP SKID FDN 2
16 | P02.03-CV-120-DWG-05001 | 1 | CN-5300 |  | 04110 | *S |  | CONC FDN |  | 6.74 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | MEEFOG PUMP SKID FDN 3
17 | P02.03-CV-120-DWG-04401 | 0 | CN-5000 |  | 04120 | *S |  | CONC FDN |  | 13.86 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | CT CONTROL MODULE AT-1
18 | P02.03-CV-120-DWG-04401 | 0 | CN-5000 |  | 04120 | *S |  | CONC FDN |  | 13.86 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | CT CONTROL MODULE AT-2
19 | P02.03-CV-120-DWG-04401 | 0 | CN-5000 |  | 04120 | *S |  | CONC FDN |  | 13.86 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | CT CONTROL MODULE AT-3
20 | P02.03-CV-120-DWG-00401 | 1 | *C |  | 04130 | *S |  | CONC FDN |  | 115.71 | CY |  |  |  |  | 100% | Exavation | 100% | Formwork | 100% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | SCR FDN AT-1
21 | P02.03-CV-120-DWG-00401 | 1 | *C |  | 04130 | *S |  | CONC FDN |  | 115.71 | CY |  |  |  |  | 100% | Exavation | 100% | Formwork | 100% | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | SCR FDN AT-2
22 | P02.03-CV-120-DWG-00401 | 1 | *C |  | 04130 | *S |  | CONC FDN |  | 115.71 | CY |  |  |  |  | 100% | Exavation | 100% | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | SCR FDN AT-3
23 | P02.03-CV-120-DWG-01301 | 1 | *C |  | 04110 | *S |  | CONC FDN |  | 3.25 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | SCR AMMONIA INJECTION SKID AT-1
24 | P02.03-CV-120-DWG-01301 | 1 | *C |  | 04110 | *S |  | CONC FDN |  | 3.25 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | SCR AMMONIA INJECTION SKID AT-2
25 | P02.03-CV-120-DWG-01301 | 1 | *C |  | 04110 | *S |  | CONC FDN |  | 3.25 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | SCR AMMONIA INJECTION SKID AT-3
26 | P02.03-CV-120-DWG-01002 | 0 | *C |  | 04110 | *S |  | CONC FDN |  | 0.4 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | SCR AMMONIA TRUCK UNLOADING SKID
27 | P02.03-CV-120-DWG-01003 | 0 | CN-4300 |  | 04110 | *S |  | CONC FDN |  | 1.05 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | SCR AMMONIA FORWARDING SKID
28 | P02.03-CV-120-DWG-01101 | 0 | CN-3310 |  | 04120 | *S |  | CONC FDN |  | 16.36 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 404 | WEST STEP DOWN TRANSFORMER FDN
29 | P02.03-CV-120-DWG-01101 | 0 | CN-3310 |  | 04110 | *S |  | CONC CURB |  | 1.51 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 404 | WEST STEP DOWN TRANSFORMER CONC CURB
30 | P02.03-CV-120-DWG-01102 | 0 | CN-5350 |  | 04120 | *S |  | CONC FDN |  | 13.37 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 404 | EAST STEP DOWN TRANSFORMER FDN
31 | P02.03-CV-120-DWG-01102 | 0 | CN-5350 |  | 04110 | *S |  | CONC CURB |  | 1.24 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 404 | EAST STEP DOWN TRANSFORMER CONC CURB
32 | P02.03-CV-120-DWG-01201 | 0 | CN-3900 |  | 04120 | *S |  | CONC FDN |  | 31.41 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 401 | TEMPERING AIR FAN FDN (3 @ 10.47 EA)
33 | P02.03-CV-120-DWG-01201 | 0 | CN-3900 |  | 04120 | *S |  | CONC FDN |  | 31.41 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 402 | TEMPERING AIR FAN FDN (3 @ 10.47 EA)
34 | P02.03-CV-120-DWG-01201 | 0 | CN-3900 |  | 04120 | *S |  | CONC FDN |  | 31.41 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 403 | TEMPERING AIR FAN FDN (3 @ 10.47 EA)
35 | 1224A25-120-CV-1017 | 0 | CN-1990 |  | 04110 | *S |  | CONC FDN |  | 42.56 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 200 | PIPE RACK 200 FDN (38 @ 1.12 CY EA)
36 | 1224A25-120-CV-1018 | 0 | CN-1990 |  | 04110 | *S |  | CONC FDN |  | 11.2 | CY |  |  |  |  | 100% | Exavation |  | Formwork |  | Rebar |  | Concrete Placement |  | Strip Forms |  | Rub/Patch |  | Backfill/Compact | [9 empty] | 0.05 | 0.3 | 0.25 | 0.1 | 0.1 | 0.1 | 0.1 |  | 300 | PIPE RACK 300 FDN (10 @ 1.12 CY EA)
37 | Seal Slab | 0 | *C |  | 04700 | *S |  | SEAL SLAB |  | 195 | CY. |  |  | 195 |  | 100% | Complete | [30 empty] | AREA SEAL SLAB | bar: M1
38 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-98
39 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-99
40 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-100 (TYPE 1)
41 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-101 (TYPE 1)
42 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-102 (TYPE 1)
43 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-103 (TYPE 1)
44 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-104 (TYPE 1)
45 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-105 (TYPE 1)
46 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-106 (TYPE 1)
47 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-107 (TYPE 1)
48 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-108 (TYPE 1)
49 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-109 (TYPE 1)
50 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-110 (TYPE 1)
51 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-111 (TYPE 1)
52 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-112 (TYPE 1)
53 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-113 (TYPE 1)
54 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-114 (TYPE 2)
55 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-115 (TYPE 2)
56 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | TURBINE DP-116 (TYPE 3)
57 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | TURBINE DP-117 (TYPE 3)
58 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | TURBINE DP-118 (TYPE 3)
59 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | TURBINE DP-119 (TYPE 3)
60 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | AUX COMP 1 DP-120 (TYPE 4)
61 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | AUX COMP 1 DP-121 (TYPE 4)
62 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | AUX COMP 1 DP-122 (TYPE 4)
63 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | AUX COMP 1 DP-123 (TYPE 4)
64 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | MISC DP-124 (TYPE 1)
65 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | MISC DP-125 (TYPE 1)
66 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | MISC DP-126 (TYPE 5A)
67 | 12224A25-120-CV-1011 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 401 | MISC DP-127 (TYPE 5B)
68 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-200 (TYPE 2)
69 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-201 (TYPE 2)
70 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-202 (TYPE 1)
71 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-203 (TYPE 1)
72 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-204 (TYPE 1)
73 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-205 (TYPE 1)
74 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-206 (TYPE 1)
75 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-207 (TYPE 1)
76 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-208 (TYPE 1)
77 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-209 (TYPE 1)
78 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-210 (TYPE 1)
79 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-211 (TYPE 1)
80 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-212 (TYPE 1)
81 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-213 (TYPE 1)
82 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-214 (TYPE 1)
83 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-215 (TYPE 1)
84 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-216 (TYPE 2)
85 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 101 | PIPE RACK 100 DP-217 (TYPE 2)
86 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-218 (TYPE 1)
87 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-219 (TYPE 1)
88 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-220 (TYPE 1)
89 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-221 (TYPE 1)
90 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-222 (TYPE 1)
91 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-223 (TYPE 1)
92 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 404 | MCC DP-224 (TYPE 1)
93 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | TURBINE DP-225 (TYPE 3)
94 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | TURBINE DP-226 (TYPE 3)
95 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | TURBINE DP-227 (TYPE 3)
96 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | TURBINE DP-228 (TYPE 3)
97 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | AUX COMP 2 DP-229 (TYPE 4)
98 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | AUX COMP 2 DP-230 (TYPE 4)
99 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | AUX COMP 2 DP-231 (TYPE 4)
100 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | AUX COMP 2 DP-232 (TYPE 4)
101 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | MISC DP-233 (TYPE 5A)
102 | 12224A25-120-CV-1012 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 402 | MISC DP-234 (TYPE 5B)
103 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-300 (TYPE 2)
104 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-301 (TYPE 2)
105 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-302 (TYPE 1)
106 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-303 (TYPE 1)
107 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-304 (TYPE 1)
108 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-305 (TYPE 1)
109 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-306 (TYPE 1)
110 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-307 (TYPE 1)
111 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-308 (TYPE 1)
112 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-309 (TYPE 1)
113 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-310 (TYPE 1)
114 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-311 (TYPE 1)
115 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-312 (TYPE 1)
116 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-313 (TYPE 1)
117 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-314 (TYPE 1)
118 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-315 (TYPE 1)
119 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-316 (TYPE 2)
120 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-317 (TYPE 2)
121 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-318 (TYPE 1)
122 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-319 (TYPE 1)
123 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-320 (TYPE 1)
124 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-321 (TYPE 1)
125 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-322 (TYPE 1)
126 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-323 (TYPE 1)
127 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | TURBINE DP-324 (TYPE 3)
128 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | TURBINE DP-325 (TYPE 3)
129 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | TURBINE DP-326 (TYPE 3)
130 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  | EMU | 1 | EMU | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | TURBINE DP-327 (TYPE 3)
131 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  | EMU | 1 | EMU | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | AUX COMP 3 DP-328 (TYPE 4)
132 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  | EMU | 1 | EMU | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | AUX COMP 3 DP-329 (TYPE 4)
133 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | AUX COMP 3 DP-330 (TYPE 4)
134 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | AUX COMP 3 DP-331 (TYPE 4)
135 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | MISC DP-332 (TYPE 1)
136 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | MISC DP-333 (TYPE 1)
137 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | MISC DP-334 (TYPE 5A)
138 | 12224A25-120-CV-1013 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 403 | MISC DP-335 (TYPE 5B)
139 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-400 (TYPE 2)
140 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-401 (TYPE 2)
141 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-402 (TYPE 1)
142 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-403 (TYPE 1)
143 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-404 (TYPE 1)
144 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-405 (TYPE 1)
145 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-406 (TYPE 1)
146 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-407 (TYPE 1)
147 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-408 (TYPE 1)
148 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-409 (TYPE 1)
149 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-410 (TYPE 1)
150 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-411 (TYPE 1)
151 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-412 (TYPE 1)
152 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-413 (TYPE 1)
153 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-414 (TYPE 1)
154 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 100 | PIPE RACK 100 DP-415 (TYPE 1)
155 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-416 (TYPE 1)
156 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-417 (TYPE 1)
157 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-418 (TYPE 1)
158 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-419 (TYPE 1)
159 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-420 (TYPE 1)
160 | 12224A25-120-CV-1014 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-421 (TYPE 1)
161 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-700 (TYPE 2)
162 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-701 (TYPE 2)
163 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-702 (TYPE 2)
164 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-703 (TYPE 2)
165 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-704 (TYPE 1)
166 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-705 (TYPE 1)
167 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-706 (TYPE 1)
168 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-707 (TYPE 1)
169 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-708 (TYPE 1)
170 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-709 (TYPE 1)
171 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-710 (TYPE 1)
172 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-711 (TYPE 1)
173 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-712 (TYPE 1)
174 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-713 (TYPE 1)
175 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-714 (TYPE 1)
176 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-715 (TYPE 1)
177 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-716 (TYPE 1)
178 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-717 (TYPE 1)
179 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-718 (TYPE 1)
180 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-719 (TYPE 1)
181 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-720 (TYPE 1)
182 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-721 (TYPE 1)
183 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-722 (TYPE 1)
184 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-723 (TYPE 1)
185 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-724 (TYPE 1)
186 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-725 (TYPE 1)
187 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-726 (TYPE 1)
188 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-727 (TYPE 1)
189 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-728 (TYPE 1)
190 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-729 (TYPE 1)
191 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-730 (TYPE 1)
192 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-731 (TYPE 1)
193 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-732 (TYPE 1)
194 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-733 (TYPE 1)
195 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-734 (TYPE 1)
196 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-735 (TYPE 1)
197 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-736 (TYPE 1)
198 | 12224A25-120-CV-1017 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 200 | PIPE RACK 200 DP-737 (TYPE 1)
199 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-800 (TYPE 1)
200 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-801 (TYPE 1)
201 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-802 (TYPE 1)
202 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-803 (TYPE 1)
203 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-804 (TYPE 1)
204 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-805 (TYPE 1)
205 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-806 (TYPE 1)
206 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-807 (TYPE 1)
207 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-808 (TYPE 1)
208 | 12224A25-120-CV-1018 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 0.55 | CY |  |  |  |  | 100% | Drill | 100% | Rebar | 100% | Formwork | 100% | Concrete | 100% | Strip Form | 100% | Rub-Patch | [11 empty] | 0.3 | 0.25 | 0.3 | 0.05 | 0.05 | 0.05 |  |  | 300 | PIPE RACK 300 DP-809 (TYPE 1)
209 | P02.03-CV-120-DWG-00009 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 17.8 | CY |  |  |  |  | 100% | Drill | 100% | Rebar |  | Formwork |  | Concrete |  | Strip Form |  | Rub-Patch | [19 empty] | 404 | MCC DRILLED PIERS (20 EA @ 0.89CY)
210 | P02.03-CV-120-DWG-00009 | 0 | *C |  | 04110 | *S |  | Drilled Pier |  | 5.34 | CY |  |  |  |  | 100% | Drill | 100% | Rebar |  | Formwork |  | Concrete |  | Strip Form |  | Rub-Patch | [19 empty] | 402 | RELAY BUILDING DRILLED PIERS (6 EA @ 0.89 CY)
211 | Backfill | 0 | CN-1780 |  | 01400 | *S |  | BACKFILL |  | 3500 | CY. |  |  | 30162 |  | 21% | Complete
212 | Crushed Rock | 0 | CN-1780 |  |  | *S |  | ROCK |  |  | EMU

## Sheet2
Type | Cost Code | Base U/R | PF Adjust | PF U/R | check
| 04110 |  |  |  | 21.2 | frac 14 | per cy.
| 04120 |  |  |  | 8.8 | frac 14 | per cy.
| 04130 |  |  |  | 6.8 | frac 14 | per cy.
| 03600 |  |  |  |  | frac 14 | per cy.
| 04700 |  |  |  | 1.5 | frac 14 | per cy.
| 04150 |  |  |  | 6.1 | frac 14 | per cy.
| 04620 |  |  |  | 7.7 | frac 14 | per cy.
non shrink | 04630 |  |  |  | 5.7 | frac 14 | per cy.
| 04210 |  |  |  | 6.66 | frac 14 | per cy.
| 04500 |  |  |  | 22.5 | frac 14 | per cy.
| 04220 |  |  |  | 5.4 | frac 14 | per cy.
| 01410 |  |  |  | 0.11 | frac 14 | per cy.
| 01420 |  |  |  | 0.1 | frac 14 | per cy.
| 01440 |  |  |  | 1.5 | frac 14 | per cy.
| 01450 |  |  |  | 0.37 | frac 14 | per cy.
| 01510 |  |  |  | 0.06 | frac 14 | per cy.
01610
| 01940 |  |  |  |  | frac 14 | per cy. | 24 & under-.5 | over 24 -.97
| 01950 |  |  |  |  | frac 14 | per cy. | small- 49 | large- 6.75
01100
01110
| 01200 | [5 empty] | emu
| 01300 | [5 empty] | emu