## Inst Audit
REC_NO | DWG | REV_NO | SCHED_ID | CAREA | CODE | SYSTEM | LINE_AREA | SPOOL_FR | SZE | FLD_QTY | FLD_WHRS | UOM | PIPE_SPEC | ERN_QTY | EARN_WHRS | M1_PCT | M1_DESC | M2_PCT | M2_DESC | M3_PCT | M3_DESC | M4_PCT | M4_DESC | M5_PCT | M5_DESC | M6_PCT | M6_DESC | M7_PCT | M7_DESC | M8_PCT | M8_DESC | TEST_PKG1 | CWP | IWP_PLAN_NO | SPL_CNT | IWP_FOREMAN | IWP_GEN_FOREMAN | WHRS_UNIT | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | VAR_AREA | PAINT_SPEC | INSU_SPEC | HEAT_TRACE_SPEC | TA_BANK | TA_BAY | TA_LEVEL | PSLIP
1 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-170-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
2 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-170-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
3 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-171-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
4 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-171-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
5 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-171-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
6 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-171-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
7 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-144-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
8 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-170-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
9 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-170-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
10 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-171-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
11 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-171-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
12 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-171-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
13 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-171-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
14 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-144-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
15 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-170-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
16 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-170-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
17 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-171-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
18 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FE-171-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
19 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-171-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
20 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-171-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
21 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-144-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
22 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-270 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
23 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-270 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
24 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-231 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
25 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-710 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
26 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-720 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
27 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TT-720 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
28 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TS-720 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
29 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-710A |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
30 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-710B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
31 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-710 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
32 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FI-710 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
33 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TT-721 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
34 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TS-721 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
35 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-721 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
36 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
37 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
38 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
39 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TT-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
40 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FI-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
41 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-711 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
42 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-180-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
43 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-180-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
44 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-181-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
45 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-181-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
46 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-181-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
47 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-181-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
48 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
49 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
50 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
51 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TS-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
52 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
53 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-242-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
54 | DWG.M201 | 0 | *C |  | 10200 | *S |  | PCV-240-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
55 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-137-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
56 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-138-1 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
57 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-180-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
58 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-180-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
59 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-181-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
60 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-181-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
61 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-181-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
62 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-181-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
63 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
64 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
65 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
66 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TS-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
67 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
68 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-242-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
69 | DWG.M201 | 0 | *C |  | 10200 | *S |  | PCV-240-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
70 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-137-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
71 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-138-2 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
72 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-180-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
73 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-180-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
74 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-181-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
75 | DWG.M201 | 0 | *C |  | 10210 | *S |  | FE-181-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
76 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-181-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
77 | DWG.M201 | 0 | *C |  | 10110 | *S |  | FT-181-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
78 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
79 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TI-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
80 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
81 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TS-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
82 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
83 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-242-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
84 | DWG.M201 | 0 | *C |  | 10200 | *S |  | PCV-240-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
85 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-137-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
86 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-138-3 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
87 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-242 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
88 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-200A |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
89 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-200B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
90 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-200C |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
91 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-200 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
92 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-200B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
93 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-200A |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
94 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-200C |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
95 | DWG.M201 | 0 | *C |  | 10110 | *S |  | TE-230 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
96 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-232 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
97 | DWG.M201 | 0 | *C |  | 10110 | *S |  | LS-280 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
98 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-204 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
99 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-210A |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
100 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-210B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
101 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-210C |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
102 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PS-210-D |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
103 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PI-210 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
104 | DWG.M201 | 0 | *C |  | 10110 | *S |  | PT-210 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
105 | DWG.M201 | 0 | *C |  | 10200 | *S |  | PCV-243 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
106 | DWG.M202 | 0 | *C |  | 10220 | *S |  | LT-300B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
107 | DWG.M202 | 0 | *C |  | 10220 | *S |  | LG-300 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
108 | DWG.M202 | 0 | *C |  | 10110 | *S |  | TE-320 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
109 | DWG.M202 | 0 | *C |  | 10110 | *S |  | TI-320 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
110 | DWG.M202 | 0 | *C |  | 10110 | *S |  | FT-120 |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
111 | DWG.M202 | 0 | *C |  | 10110 | *S |  | LS-300A |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1
112 | DWG.M202 | 0 | *C |  | 10110 | *S |  | LS-300B |  | 1 |  | EA |  |  |  |  | Receive |  | Calibrate/Spec Check |  | Stand |  | Install Device |  | Tray and Tube |  | Process Connection | [11 empty] | 0.05 | 0.1 | 0.15 | 0.3 | 0.3 | 0.1

## Sheet1
Type | Cost Code | Base U/R | PF Adjust | PF U/R | Check
Field Mounted Inst. Devices | 10110
Control Valves, Power Operators | 10210
Level gauges | 10220
Analytical Systems | 10410
Gas Detection | 10420
Threaded Air Supply | 10550
Field mounted Panels | 10620