## Mech Audit
REC_NO | DWG | REV_NO | SCHED_ID | CAREA | CODE | SYSTEM | TAG_NO | DESC_ | SZE | FLD_QTY | UOM | FLD_WHRS | PIPE_SPEC | ERN_QTY | EARN_WHR | M1_PCT | M1_DESC | M2_PCT | M2_DESC | M3_PCT | M3_DESC | M4_PCT | M4_DESC | M5_PCT | M5_DESC | M6_PCT | M6_DESC | M7_PCT | M7_DESC | M8_PCT | M8_DESC | TEST_PKG | CWP | IWP_PLAN_NO | SPL_CNT | IWP FOREMAN | IWP_GEN_FOREMAN | IFC_WHRS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | VAR AREA | SPEC | SERVICE | INSU_SPEC | TA_BANK | TA_BAY | TA_LEVEL | PSLIP
1 | DRAWING | 0 | *C |  | 07120 | *S |  | MOBILE DEMIN UNIT |  | 2 | EA | 23.8 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals |  | Inspect Button Up |  | Sell Off | [7 empty] | 0 |  |  | 23.8 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 406 | N/A | Demin Water
2 | DRAWING | 0 | *C |  | 07140 | *S |  | 100GPM SP RECOVERY |  | 1 | EA | 11.9 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 11.9 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 |  | N/A
3 | DRAWING | 0 | *C |  | 07140 | *S |  | MPW 200 GPM DPRO |  | 2 | EA | 23.8 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 23.8 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05
4 | 12224A25-120-PP-3019 | 0 | *C |  | 07140 | *S | P-201A/B | WSAC |  | 2 | EA | 571.2 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 571.2 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 406 | ASME B73.1 | Waste Water
5 | DRAWING | 0 | *C |  | 07140 | *S |  | MISC PUMP |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 47.6 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05
6 | DRAWING | 0 | *C |  | 07410 | *S | AT-1 | AT-1 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
7 | DRAWING | 0 | *C |  | 07410 | *S | AT-2 | AT-2 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
8 | DRAWING | 0 | *C |  | 07410 | *S | AT-21 | AT-21 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
9 | DRAWING | 0 | *C |  | 07410 | *S | AT-11 | AT-11 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
10 | DRAWING | 0 | *C |  | 07410 | *S | AT-22 | AT-22 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
11 | DRAWING | 0 | *C |  | 07410 | *S | AT-3 | AT-3 |  | 1 | EA | 29.75 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 29.75 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404
12 | DRAWING | 0 | *C |  | 09550 | *S |  | MCC Building |  | 1 | EA | 95.2 |  |  |  |  | Receive |  | Support |  | Install |  | Testing |  | Sell Off | [9 empty] | 0 |  |  | 95.2 | 0.05 | 0.2 | 0.6 | 0.1 | 0.05 |  |  |  | 402
13 | DRAWING | 0 | *C |  | 09550 | *S |  | MCC Building |  | 1 | EA | 95.2 |  |  |  |  | Receive |  | Support |  | Install |  | Testing |  | Sell Off | [9 empty] | 0 |  |  | 95.2 | 0.05 | 0.2 | 0.6 | 0.1 | 0.05 |  |  |  | 402
14 | DRAWING | 0 | *C |  | 07410 | *S |  | Step Down Transfomer |  | 1 | EA | 41.65 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 41.65 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1
15 | DRAWING | 0 | *C |  | 07410 | *S |  | Step Down Transfomer |  | 1 | EA | 41.65 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 41.65 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1
16 | DRAWING | 0 | *C |  | 07410 | *S | SK-4000 | Water Wash Skid SK-4000 |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 404 |  | Water Wash
17 | DRAWING | 0 | *C |  | 07410 | *S | SK-7000 | SCR Ammonia Forwarded Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
18 | DRAWING | 0 | *C |  | 07410 | *S | SK-8000 | SCR Truck Unloading Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
19 | DRAWING | 0 | *C |  | 07410 | *S |  | SCR Ammonia Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
20 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fans-1 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 401
21 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fans-2 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 401
22 | DRAWING | 0 | *C |  | 07410 | *S |  | Step Up Transformer |  | 1 | EA | 142.8 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 142.8 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
23 | DRAWING | 0 | *C |  | 07410 | *S |  | Step Up Transformer |  | 1 | EA | 142.8 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 142.8 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 402
24 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fans-1 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 402
25 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fans-2 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 402
26 | DRAWING | 0 | *C |  | 07410 | *S |  | SCR Ammonia Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 402
27 | DRAWING | 0 | *C |  | 07410 | *S |  | Meefog Pump Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
28 | DRAWING | 0 | *C |  | 07410 | *S |  | Water Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 401
29 | DRAWING | 0 | *C |  | 07410 | *S |  | Meefog Pump Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 402
30 | DRAWING | 0 | *C |  | 07410 | *S |  | Water Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 402
31 | DRAWING | 0 | *C |  | 07410 | *S |  | Meefog Pump Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 403
32 | DRAWING | 0 | *C |  | 07410 | *S |  | Water Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 403
33 | DRAWING | 0 | *C |  | 07410 | *S |  | SCR Ammonia Injection Skid |  | 1 | EA | 47.6 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 47.6 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 403
34 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fan-1 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 403
35 | DRAWING | 0 | *C |  | 07150 | *S |  | Tempering Fan-2 |  | 1 | EA | 35.7 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 35.7 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05 | 403
36 | 12224A25-120-PP-3019 | 0 | *C |  | 07185 | *S |  | WSAC |  | 3 | EA | 428.4 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals |  | Inspect Button Up |  | Sell Off | [7 empty] | 0 |  |  | 428.4 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 406 |  | Waste Water
37 | DRAWING | 0 | *C |  | 07140 | *S |  | MISC PUMPS |  | 5 | EA | 238 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Pre Align |  | Pipe Align |  | Final Align |  | Run-In |  | Sell Off |  |  |  | 0 |  |  | 238 | 0.05 | 0.05 | 0.15 | 0.25 | 0.1 | 0.25 | 0.1 | 0.05
38 | DRAWING | 0 | *C |  | 07410 | *S |  | Step Up Transformer |  | 1 | EA | 142.8 |  |  |  |  | Prep FDN |  | Receive |  | Set |  | Internals-S/C |  | inspect/Button Up |  | Sell Off | [7 empty] | 0 |  |  | 142.8 | 0.05 | 0.1 | 0.25 | 0.25 | 0.25 | 0.1 |  |  | 403

## Sheet 12.13.25
Type | Cost Code | Base U/R | PF Adjust | PF U/R
MOBILE DEMIN UNIT | 07120 | 10 | 1.19 | 11.9
100GPM SP RECOVERY | 07140 | 10 | 1.19 | 11.9
MPW 200 GPM DPRO | 07140 | 10 | 1.19 | 11.9
WSAC | 07140 | 240 | 1.19 | 285.6
MISC PUMP | 07140 | 40 | 1.19 | 47.6
AT-1 | 07410 | 25 | 1.19 | 29.75
AT-2 | 07410 | 25 | 1.19 | 29.75
AT-21 | 07410 | 25 | 1.19 | 29.75
AT-11 | 07410 | 25 | 1.19 | 29.75
AT-22 | 07410 | 25 | 1.19 | 29.75
AT-3 | 07410 | 25 | 1.19 | 29.75
MCC Building | 09550 | 80 | 1.19 | 95.2
MCC Building | 09550 | 80 | 1.19 | 95.2
Step Down Transfomer | 07410 | 35 | 1.19 | 41.65
Step Down Transfomer | 07410 | 35 | 1.19 | 41.65
Water Wash Skid SK-4000 | 07410 | 40 | 1.19 | 47.6
SCR Ammonia Forwarded Skid | 07410 | 40 | 1.19 | 47.6
SCR Truck Unloading Skid | 07410 | 40 | 1.19 | 47.6
SCR Ammonia Injection Skid | 07410 | 40 | 1.19 | 47.6
Tempering Fans-1 | 07150 | 30 | 1.19 | 35.7
Tempering Fans-2 | 07150 | 30 | 1.19 | 35.7
Step Up Transformer | 07410 | 120 | 1.19 | 142.8
Step Up Transformer | 07410 | 120 | 1.19 | 142.8
Tempering Fans-1 | 07150 | 30 | 1.19 | 35.7
Tempering Fans-2 | 07150 | 30 | 1.19 | 35.7
SCR Ammonia Injection Skid | 07410 | 40 | 1.19 | 47.6
Meefog Pump Skid | 07410 | 40 | 1.19 | 47.6
Water Injection Skid | 07410 | 40 | 1.19 | 47.6
Meefog Pump Skid | 07410 | 40 | 1.19 | 47.6
Water Injection Skid | 07410 | 40 | 1.19 | 47.6
Meefog Pump Skid | 07410 | 40 | 1.19 | 47.6
Water Injection Skid | 07410 | 40 | 1.19 | 47.6
SCR Ammonia Injection Skid | 07410 | 40 | 1.19 | 47.6
Tempering Fan-1 | 07150 | 30 | 1.19 | 35.7
Tempering Fan-2 | 07150 | 30 | 1.19 | 35.7
WSAC | 07185 | 120 | 1.19 | 142.8
MISC PUMPS | 07140 | 40 | 1.19 | 47.6
Step Up Transformer | 07410 |  | 1.19 | 0